## Cost and schedule
Cost and schedule
Problem: A new building is to be constructed by a consortium for a client. The project is divided into seven sections. The client wishes to see a risk analysis of the schedule and cost risks and how these relate to each other.
Contract award date | 2018-04-10
| Start | Duration d (weeks) |  |  |  | Finish | Probability | Start | Start lag (weeks) |  |  |  | Finish | Finish lag (weeks) |  |  |  |  | Cost |  |  |  | Probability
| Date St | Dist | Min | ML | Max | Date Fin |  | logic | Dist | Min | ML | Max | logic | Dist | Min | ML | Max |  | Dist | Min | ML | Max
DESIGN (Task1) | [17 empty] | DESIGN (Task1)
Detail (a) | 2018-04-10 | #NAME? | 12 | 16 | 25 | #NAME? | 80% | Start logic: =Start date; Finish logic: St+d | Detail | 160000 |  | 160000 |  | 80%
Rework risk (b) | #NAME? | #NAME? | 3 | 4 | 6 | #NAME? | 20% | Start logic: Fin1a; Finish logic: St+d | +Rework risk | #NAME? |  | 12000 | per week | 20%
Total (c) | [5 empty] | #NAME? |  | Finish logic: Discrete | Total | #NAME?
EARTHWORKS (Task2) | [17 empty] | EARTHWORKS (Task2)
Normal (a) | 2018-04-10 | #NAME? | 3 | 4 | 7 | #NAME? | 70% | Start logic: =Start date; Finish logic: St+d | Normal | #NAME? | 4200 | 4500 | 4700 | per week
Archaeo risk (b) | #NAME? | #NAME? | 8 | 10 | 14 | #NAME? | 30% | Start logic: Fin2a; Finish logic: St+d
Total (c) | [5 empty] | #NAME? |  | Finish logic: Discrete | FOUNDATIONS (Task3)
[18 empty] | Labour | #NAME? | 2800 | 3000 | 3300 | per week
FOUNDATIONS (Task3) | [17 empty] | Materials | #NAME? | 37000 | 38500 | 40000
| #NAME? | #NAME? | 6 | 7 | 8 | #NAME? |  | Start logic: MAX(Fin1c, Fin2c); Finish logic: St+d | Total | #NAME?
STRUCTURE (Task4) | [17 empty] | STRUCTURE (Task4)
Floor1 (a) | #NAME? | #NAME? | 4 | 4.5 | 6 | #NAME? |  | Fin3+lag | #NAME? | 6 | 7 | 8 | St+d |  |  |  |  | Floor1 labour | #NAME? | 4700 | 5200 | 5500
Floor2 (b) | #NAME? | #NAME? | 4 | 4.5 | 6 | #NAME? |  | Start logic: Fin4a; Finish logic: St+d | Floor2 labour | #NAME? | 4700 | 5200 | 5500
Floor3 (c) | #NAME? | #NAME? | 4 | 4.5 | 6 | #NAME? |  | Start logic: Fin4b; Finish logic: St+d | Floor3 labour | #NAME? | 4700 | 5200 | 5500
Roofing (d) | #NAME? | #NAME? | 7 | 8 | 10 | #NAME? |  | Finish logic: St+d | Floor materials | 52700 | 17200 | 17500 | 18000
[18 empty] | Roofing | 172000
ENVELOPE (Task5) | [17 empty] | Total | #NAME?
Brown Bros | [6 empty] | 90%
Floor1 (a) | #NAME? | #NAME? | 7 | 8 | 9 | #NAME? |  | Start logic: Fin4a+lag; Start lag (weeks) Dist: 3; Start lag (weeks) ML: 3; Finish logic: St+d | ENVELOPE (Task5)
Floor2 (b) | #NAME? | #NAME? | 7 | 8 | 9 | #NAME? |  | Start logic: Fin5a; Finish logic: St+d | Labour
Floor3 (c) | #NAME? | #NAME? | 7 | 8 | 9 | #NAME? |  | Start logic: Fin5b; Finish logic: St+d | Brown Bros | 197000 |  |  |  | 90%
Redd&Greene | [6 empty] | 10% | [10 empty] | Redd&Greene | 209000 |  |  |  | 10%
Floor1 (d) | #NAME? | #NAME? | 6 | 8 | 11 | #NAME? |  | Start logic: Fin4a+lag; Start lag (weeks) Dist: 3; Start lag (weeks) ML: 3; Finish logic: St+d | Labour total | #NAME?
Floor2 (e) | #NAME? | #NAME? | 6 | 8 | 11 | #NAME? |  | Start logic: Fin5d; Finish logic: St+d | Floor | #NAME? | 36000 | 37000 | 40000 | per floor
Floor3 (f) | #NAME? | #NAME? | 6 | 8 | 11 | #NAME? |  | Start logic: Fin5e; Finish logic: St+d | Doors | 9800 |  | 9800
Totals | Brown Bros |  |  |  |  | #NAME? | 90% | [10 empty] | Total | #NAME?
| Redd&Greene |  |  |  |  | #NAME? | 10%
(g) | Combined |  |  |  |  | #NAME? |  | Finish logic: Discrete | SERVICES AND FINISHINGS (Task6)
[18 empty] | Services | #NAME? | 82000 | 86000 | 91000
SERVICES AND FINISHINGS (Task6) | [17 empty] | Finishings | #NAME? | 92000 | 95000 | 107000
Services | [17 empty] | Total | #NAME?
Floor1 (a) | #NAME? | #NAME? | 8 | 10 | 13 | #NAME? |  | Start logic: Fin5a or 5d; Finish logic: St+d
Floor2 (b) | #NAME? | #NAME? | 8 | 10 | 13 | #NAME? |  | Start logic: Fin5b or 5e; Finish logic: St+d | COMMISSIONING (Task7)
Floor3 (c) | #NAME? | #NAME? | 8 | 10 | 13 | #NAME? |  | Start logic: Fin5c or 5f; Finish logic: St+d | Tidy up site | 4000 |  | 4000
Finishings
Floor1 (d) | #NAME? | #NAME? | 9 | 11 | 13 | #NAME? |  | St6a |  |  |  |  | Max | #NAME? | 2 | 3 | 4 | GRAND TOTAL | #NAME?
Floor2 (e) | #NAME? | #NAME? | 9 | 11 | 13 | #NAME? |  | Start logic: St6b; Finish logic: Max; Finish lag (weeks) Dist: #NAME?
Floor3 (f) | #NAME? | #NAME? | 9 | 11 | 13 | #NAME? |  | Start logic: St6c; Finish logic: Max; Finish lag (weeks) Dist: #NAME?
COMMISSIONING (Task7)
Tidy up site (a) | #NAME? | 2 | 1.5 | 2 | 2.5 | #NAME? | 60% | Start logic: Fin6f; Finish logic: St+d
1st call back (b) | #NAME? | #NAME? | 0.5 | 2 | 5 | #NAME? | 35% | Start logic: Fin7a; Finish logic: St+d
2nd call back (c) | #NAME? | #NAME? | 0.5 | 1 | 1.5 | #NAME? | 5% | Start logic: Fin7b; Finish logic: St+d
Total | [5 empty] | #NAME? |  | Finish logic: Discrete
FINISH DATE | #NAME?