## Cost model for the new bridge
Cost model for the new bridge
Problem: We need to build a cost model for the new bridge. All cost items are grouped into 8 categories. Three of these categories include a probability of occurrence of a particular event that will result in additional cost. Find the distribution of the total cost for this project.
|  | Distribution | Minimum | Most likely | Maximum | Probability
WP1 | Planning | #NAME? | 15500 | 17200 | 19100 | 0.6
R1 | Initial application refused | #NAME? | 18400 | 19700 | 21200 | 0.4
| WP1 total | #NAME?
WP2 | Earthworks | #NAME? | 72000 | 74500 | 83500 | 0.8
R2 | Water table problem | #NAME? | 81300 | 84600 | 90300 | 0.2
| WP2 total | #NAME?
WP3 | Steel | #NAME? | 56300 | 57200 | 59100
WP4 | Concrete | #NAME? | 44300 | 46700 | 51600
WP5 | Labour | #NAME? | 32300 | 33500 | 36800 | 0.75
R3 | First choice contractor not available | #NAME? | 38300 | 41200 | 44100 | 0.25
| WP5 total | #NAME?
WP6 | Plant hire | #NAME? | 29600 | 31200 | 34100
WP7 | Road surfacing | #NAME? | 22000 | 22700 | 24100
WP8 | Administration | #NAME? | 11000 | 11500 | 12400
| Total cost | #NAME?