## Cost model for the new bridge
Cost model for the new bridge
Problem: We need to build a cost model for the new bridge. All cost items are grouped into 8 categories. Three of these categories include a probability of occurrence of a particular event that will result in additional cost. Find the distribution of the total cost for this project.
|  | Distribution | Probability | Minimum | Most likely | Maximum
WP1 | Planning | 17167.3082 | 0.6 | 15500 | 17200 | 19100 | 1
R1 | Initial application refused | 18941.8502 | 0.4 | 18400 | 19700 | 21200 | 0
| WP1 total | 17167.3082
WP2 | Earthworks | 73697.7848 | 0.8 | 72000 | 74500 | 83500 | 1
R2 | Water table problem | 84508.606 | 0.2 | 81300 | 84600 | 90300 | 0
| WP2 total | 73697.7848
WP3 | Steel | 57490.8806 |  | 56300 | 57200 | 59100
WP4 | Concrete | 47445.5652 |  | 44300 | 46700 | 51600
WP5 | Labour | 34490.4254 | 0.75 | 32300 | 33500 | 36800 | 1
R3 | First choice contractor not available | 40318.4169 | 0.25 | 38300 | 41200 | 44100 | 0
| WP5 total | 34490.4254
WP6 | Plant hire | 30165.9949 |  | 29600 | 31200 | 34100
WP7 | Road surfacing | 22822.932 |  | 22000 | 22700 | 24100
WP8 | Administration | 11393.0997 |  | 11000 | 11500 | 12400
| Total cost | 294673.9908