## CLT risk portfolio
CLT risk portfolio approximation
Technique: This example illustrates the use of a Central Limit Theorem in estimating approximate ranges of the total risk impact.
| Total risk impact |  | #NAME? |  | CLT approximation: |  | #NAME?
| 90% |  | #NAME? |  | 90% |  | 256.3677 | #NAME?
CLT calculation
|  | Conditional impact parameters | [5 empty] | Conditional impact |  | Risk impact
Risk ID # | Probability occurrence | Distribution type | Mean Min | Stdev Most_Likely | Maximum | Gamma | modeled risk | Mean | Variance | Mean | Variance | Distribution list
1 | 0.05 | Lognorm | 12 | 5 |  |  | #NAME? | 12 | 25 | 0.6 | 8.09 | Lognorm
2 | 0.01 | PERT | 3 | 8 | 14 |  | #NAME? | 8.1667 | 4.3056 | 0.081667 | 0.70333 | Normal
3 | 0.01 | PERT | 2 | 3 | 11 |  | #NAME? | 4.1667 | 2.1151 | 0.041667 | 0.19303 | PERT
4 | 0.3 | PERT | 4 | 10 | 41 |  | #NAME? | 14.1667 | 38.9722 | 4.25 | 53.8375 | Triang
5 | 0.5 | PERT | 4 | 7 | 11 |  | #NAME? | 7.1667 | 1.7341 | 3.5833 | 13.7073
6 | 0.2 | Triang | 4 | 5 | 8 |  | #NAME? | 5.6667 | 0.72222 | 1.1333 | 5.2822
7 | 0.1 | PERT | 0 | 1 | 3 |  | #NAME? | 1.1667 | 0.30556 | 0.11667 | 0.15306
8 | 0.05 | PERT | 0 | 1 | 8 |  | #NAME? | 2 | 1.7143 | 0.1 | 0.27571
9 | 0.1 | PERT | 2 | 4 | 20 |  | #NAME? | 6.3333 | 8.4603 | 0.63333 | 4.456
10 | 0.01 | Triang | 1 | 3 | 14 |  | #NAME? | 6 | 8.1667 | 0.06 | 0.43807
11 | 0.05 | PERT | 3 | 9 | 35 |  | #NAME? | 12.3333 | 30.2222 | 0.61667 | 8.7364
12 | 0.05 | Triang | 3 | 7 | 40 |  | #NAME? | 16.6667 | 68.7222 | 0.83333 | 16.6306
13 | 0.05 | Triang | 4 | 14 | 82 |  | #NAME? | 33.3333 | 300.2222 | 1.6667 | 67.7889
14 | 0.5 | PERT | 3 | 6 | 6 |  | #NAME? | 5.5 | 0.17857 | 2.75 | 7.6518
15 | 0.01 | PERT | 1 | 2 | 9 |  | #NAME? | 3 | 1.7143 | 0.03 | 0.10624
16 | 0.3 | PERT | 4 | 7 | 21 |  | #NAME? | 8.8333 | 8.4008 | 2.65 | 18.9061
17 | 0.05 | Triang | 0 | 1 | 4 |  | #NAME? | 1.6667 | 0.72222 | 0.083333 | 0.16806
18 | 0.001 | PERT | 3 | 12 | 22 |  | #NAME? | 12.1667 | 12.877 | 0.012167 | 0.16076
19 | 0.2 | PERT | 1 | 3 | 3 |  | #NAME? | 2.6667 | 0.079365 | 0.53333 | 1.1537
20 | 0.001 | PERT | 0 | 0 | 7 |  | #NAME? | 1.1667 | 0.97222 | 0.0011667 | 0.002332
21 | 0.05 | PERT | 4 | 13 | 68 |  | #NAME? | 20.6667 | 112.6984 | 1.0333 | 25.9227
22 | 0.01 | Normal | 22 | 7 |  |  | #NAME? | 22 | 49 | 0.22 | 5.2816
23 | 0.6 | PERT | 4 | 14 | 55 |  | #NAME? | 19.1667 | 77.6389 | 11.5 | 134.75
24 | 0.5 | PERT | 5 | 8 | 15 | 3.5 | #NAME? | 8.6667 | 3.3175 | 4.3333 | 20.4365
25 | 0.001 | PERT | 2 | 2 | 5 |  | #NAME? | 2.5 | 0.17857 | 0.0025 | 0.0064223
26 | 0.05 | PERT | 2 | 5 | 15 | 2.5 | #NAME? | 6.1667 | 5.2579 | 0.30833 | 2.0692
27 | 0.2 | PERT | 3 | 11 | 54 |  | #NAME? | 16.8333 | 73.4484 | 3.3667 | 60.0275
28 | 0.2 | Triang | 0 | 2 | 7 |  | #NAME? | 3 | 2.1667 | 0.6 | 1.8733
29 | 0.3 | Triang | 5 | 19 | 111 |  | #NAME? | 45 | 552.6667 | 13.5 | 591.05
30 | 0.05 | PERT | 5 | 16 | 93 |  | #NAME? | 27 | 207.4286 | 1.35 | 44.9989
31 | 0.2 | PERT | 5 | 13 | 68 |  | #NAME? | 20.8333 | 106.6865 | 4.1667 | 90.7817
32 | 0.3 | PERT | 1 | 2 | 11 |  | #NAME? | 3.3333 | 2.5556 | 1 | 3.1
33 | 0.2 | PERT | 0 | 3 | 9 |  | #NAME? | 3.5 | 2.75 | 0.7 | 2.51
34 | 0.1 | Triang | 2 | 3 | 5 |  | #NAME? | 3.3333 | 0.38889 | 0.33333 | 1.0389
35 | 0.1 | PERT | 2 | 2 | 5 |  | #NAME? | 2.5 | 0.17857 | 0.25 | 0.58036
36 | 0.1 | PERT | 1 | 1 | 3 |  | #NAME? | 1.3333 | 0.079365 | 0.13333 | 0.16794
37 | 0.001 | PERT | 4 | 6 | 32 | 3 | #NAME? | 10 | 18.8571 | 0.01 | 0.11876
38 | 0.05 | PERT | 1 | 4 | 5 | 3 | #NAME? | 3.6667 | 0.50794 | 0.18333 | 0.66401
39 | 0.01 | PERT | 1 | 2 | 8 |  | #NAME? | 2.8333 | 1.3532 | 0.028333 | 0.093007
40 | 0.6 | PERT | 4 | 14 | 45 |  | #NAME? | 17.5 | 53.0357 | 10.5 | 105.3214
41 | 0.01 | PERT | 1 | 2 | 5 |  | #NAME? | 2.3333 | 0.50794 | 0.023333 | 0.058979
42 | 0.05 | PERT | 1 | 3 | 8 |  | #NAME? | 3.5 | 1.6071 | 0.175 | 0.66223
43 | 0.3 | PERT | 0 | 2 | 7 | 3 | #NAME? | 2.5 | 1.6071 | 0.75 | 1.7946
44 | 0.05 | PERT | 5 | 6 | 11 |  | #NAME? | 6.6667 | 1.0317 | 0.33333 | 2.1627
45 | 0.4 | PERT | 5 | 20 | 117 |  | #NAME? | 33.6667 | 341.2698 | 13.4667 | 408.5346
46 | 0.3 | PERT | 2 | 3 | 6 |  | #NAME? | 3.3333 | 0.50794 | 1 | 2.4857
47 | 0.2 | PERT | 2 | 7 | 14 |  | #NAME? | 7.3333 | 5.0794 | 1.4667 | 9.6203
48 | 0.001 | PERT | 0 | 0 | 19 |  | #NAME? | 3.1667 | 7.1627 | 0.0031667 | 0.01718
49 | 0.01 | PERT | 1 | 2 | 6 | 3.5 | #NAME? | 2.5 | 0.75 | 0.025 | 0.069375
50 | 0.7 | PERT | 4 | 8 | 28 |  | #NAME? | 10.6667 | 16.5079 | 7.4667 | 35.4489
51 | 0.1 | PERT | 2 | 5 | 12 | 4.5 | #NAME? | 5.6667 | 3.3175 | 0.56667 | 3.2217
52 | 0.001 | PERT | 1 | 3 | 13 |  | #NAME? | 4.3333 | 4.127 | 0.0043333 | 0.022886
53 | 0.2 | PERT | 1 | 1 | 6 |  | #NAME? | 1.8333 | 0.49603 | 0.36667 | 0.63698
54 | 0.01 | PERT | 1 | 3 | 9 | 3.5 | #NAME? | 3.6667 | 2.0317 | 0.036667 | 0.15342
55 | 0.01 | PERT | 2 | 3 | 9 |  | #NAME? | 3.8333 | 1.3532 | 0.038333 | 0.15901
56 | 0.2 | PERT | 3 | 4 | 11 |  | #NAME? | 5 | 1.7143 | 1 | 4.3429
57 | 0.1 | PERT | 2 | 7 | 18 |  | #NAME? | 8 | 8.5714 | 0.8 | 6.6171
58 | 0.2 | PERT | 4 | 4 | 13 |  | #NAME? | 5.5 | 1.6071 | 1.1 | 5.1614
59 | 0.01 | Triang | 2 | 4 | 17 |  | #NAME? | 7.6667 | 11.0556 | 0.076667 | 0.69246
60 | 0.05 | PERT | 2 | 7 | 22 |  | #NAME? | 8.6667 | 12.6984 | 0.43333 | 4.2027
61 | 0.2 | PERT | 1 | 1 | 7 |  | #NAME? | 2 | 0.71429 | 0.4 | 0.78286
62 | 0.01 | Triang | 5 | 13 | 74 |  | #NAME? | 30.6667 | 237.3889 | 0.30667 | 11.6843
63 | 0.05 | PERT | 3 | 5 | 21 |  | #NAME? | 7.3333 | 8.4603 | 0.36667 | 2.9775
64 | 0.2 | Triang | 3 | 6 | 14 |  | #NAME? | 7.6667 | 5.3889 | 1.5333 | 10.4822
65 | 0.7 | PERT | 0 | 1 | 5 |  | #NAME? | 1.5 | 0.75 | 1.05 | 0.9975
66 | 0.01 | PERT | 3 | 5 | 7 |  | #NAME? | 5 | 0.57143 | 0.05 | 0.25321
67 | 0.1 | PERT | 2 | 5 | 9 |  | #NAME? | 5.1667 | 1.7341 | 0.51667 | 2.5759
68 | 0.001 | Triang | 0 | 2 | 6 |  | #NAME? | 2.6667 | 1.5556 | 0.0026667 | 0.0086596
69 | 0.001 | Triang | 3 | 8 | 24 |  | #NAME? | 11.6667 | 20.0556 | 0.011667 | 0.15603
70 | 0.05 | Triang | 5 | 12 | 30 |  | #NAME? | 15.6667 | 27.7222 | 0.78333 | 13.0447
71 | 0.01 | PERT | 2 | 6 | 7 |  | #NAME? | 5.5 | 0.75 | 0.055 | 0.30698
72 | 0.05 | PERT | 4 | 5 | 26 |  | #NAME? | 8.3333 | 10.9365 | 0.41667 | 3.8454
73 | 0.3 | PERT | 1 | 2 | 9 |  | #NAME? | 3 | 1.7143 | 0.9 | 2.4043
74 | 0.2 | PERT | 3 | 6 | 28 |  | #NAME? | 9.1667 | 16.5913 | 1.8333 | 16.7627
75 | 0.05 | Triang | 4 | 8 | 39 |  | #NAME? | 17 | 61.1667 | 0.85 | 16.7858
76 | 0.01 | PERT | 3 | 4 | 10 |  | #NAME? | 4.8333 | 1.3532 | 0.048333 | 0.24481
77 | 0.05 | PERT | 3 | 5 | 12 |  | #NAME? | 5.8333 | 2.496 | 0.29167 | 1.7411
78 | 0.2 | PERT | 2 | 4 | 23 |  | #NAME? | 6.8333 | 11.1627 | 1.3667 | 9.7037
79 | 0.2 | PERT | 2 | 3 | 6 |  | #NAME? | 3.3333 | 0.50794 | 0.66667 | 1.8794
80 | 0.05 | Triang | 4 | 10 | 13 |  | #NAME? | 9 | 3.5 | 0.45 | 4.0225
81 | 0.001 | PERT | 0 | 1 | 100 |  | #NAME? | 17.3333 | 204.6984 | 0.017333 | 0.50484
82 | 0.7 | Triang | 4 | 4 | 9 |  | #NAME? | 5.6667 | 1.3889 | 3.9667 | 7.7156
83 | 0.05 | PERT | 3 | 10 | 37 |  | #NAME? | 13.3333 | 34.9365 | 0.66667 | 10.1913
84 | 0.05 | PERT | 2 | 3 | 9 |  | #NAME? | 3.8333 | 1.3532 | 0.19167 | 0.76564
85 | 0.4 | PERT | 4 | 13 | 40 | 3 | #NAME? | 16 | 41.1429 | 6.4 | 77.8971
86 | 0.05 | PERT | 1 | 2 | 7 | 2.5 | #NAME? | 2.6667 | 1.0317 | 0.13333 | 0.38937
87 | 0.05 | PERT | 4 | 13 | 55 |  | #NAME? | 18.5 | 75.6071 | 0.925 | 20.0372
88 | 0.8 | Triang | 2 | 2 | 10 |  | #NAME? | 4.6667 | 3.5556 | 3.7333 | 6.3289
89 | 0.1 | Triang | 1 | 2 | 8 |  | #NAME? | 3.6667 | 2.3889 | 0.36667 | 1.4489
90 | 0.05 | Triang | 5 | 16 | 90 |  | #NAME? | 37 | 356.1667 | 1.85 | 82.8358
91 | 0.001 | Triang | 5 | 19 | 100 |  | #NAME? | 41.3333 | 438.3889 | 0.041333 | 2.1451
92 | 0.001 | PERT | 5 | 16 | 82 | 2 | #NAME? | 25.1667 | 163.7341 | 0.025167 | 0.79646
93 | 0.05 | PERT | 4 | 5 | 8 | 3.5 | #NAME? | 5.3333 | 0.50794 | 0.26667 | 1.3765
94 | 0.2 | Triang | 3 | 11 | 64 |  | #NAME? | 26 | 183.1667 | 5.2 | 144.7933
95 | 0.3 | Triang | 2 | 6 | 28 |  | #NAME? | 12 | 32.6667 | 3.6 | 40.04
96 | 0.3 | PERT | 1 | 2 | 11 |  | #NAME? | 3.3333 | 2.5556 | 1 | 3.1
97 | 0.05 | Triang | 4 | 15 | 86 |  | #NAME? | 35 | 330.1667 | 1.75 | 74.6958
98 | 0.01 | PERT | 3 | 11 | 12 |  | #NAME? | 9.8333 | 2.1151 | 0.098333 | 0.97843
99 | 0.3 | PERT | 1 | 2 | 8 |  | #NAME? | 2.8333 | 1.3532 | 0.85 | 2.0918
100 | 0.1 | PERT | 2 | 6 | 25 |  | #NAME? | 8.5 | 15.3214 | 0.85 | 8.0346
101 | 0.05 | PERT | 1 | 2 | 11 |  | #NAME? | 3.3333 | 2.5556 | 0.16667 | 0.65556
102 | 0.7 | Triang | 5 | 12 | 67 |  | #NAME? | 28 | 192.1667 | 19.6 | 299.1567
103 | 0.01 | PERT | 3 | 9 | 16 |  | #NAME? | 9.1667 | 6.0198 | 0.091667 | 0.89207
104 | 0.3 | PERT | 2 | 8 | 23 |  | #NAME? | 9.5 | 14.4643 | 2.85 | 23.2918
105 | 0.01 | PERT | 1 | 2 | 11 |  | #NAME? | 3.3333 | 2.5556 | 0.033333 | 0.13556
106 | 0.1 | PERT | 3 | 7 | 12 |  | #NAME? | 7.1667 | 2.877 | 0.71667 | 4.9102
107 | 0.1 | Triang | 3 | 4 | 23 |  | #NAME? | 10 | 21.1667 | 1 | 11.1167
108 | 0.01 | PERT | 1 | 2 | 5 |  | #NAME? | 2.3333 | 0.50794 | 0.023333 | 0.058979
109 | 0.05 | PERT | 2 | 4 | 7 |  | #NAME? | 4.1667 | 0.87698 | 0.20833 | 0.8685
110 | 0.2 | PERT | 2 | 3 | 7 |  | #NAME? | 3.5 | 0.75 | 0.7 | 2.11
111 | 0.01 | PERT | 5 | 8 | 13 | 2.5 | #NAME? | 8.3333 | 2.2222 | 0.083333 | 0.70972
112 | 0.1 | Lognorm | 20 | 11 |  |  | #NAME? | 20 | 121 | 2 | 48.1
113 | 0.01 | Triang | 2 | 3 | 9 |  | #NAME? | 4.6667 | 2.3889 | 0.046667 | 0.23949
114 | 0.3 | PERT | 2 | 3 | 6 |  | #NAME? | 3.3333 | 0.50794 | 1 | 2.4857
115 | 0.05 | PERT | 3 | 3 | 7 |  | #NAME? | 3.6667 | 0.31746 | 0.18333 | 0.65448
116 | 0.2 | Triang | 1 | 2 | 5 |  | #NAME? | 2.6667 | 0.72222 | 0.53333 | 1.2822
117 | 0.5 | Triang | 3 | 3 | 8 |  | #NAME? | 4.6667 | 1.3889 | 2.3333 | 6.1389
118 | 0.1 | PERT | 2 | 5 | 12 |  | #NAME? | 5.6667 | 3.3175 | 0.56667 | 3.2217
119 | 0.4 | PERT | 5 | 5 | 22 |  | #NAME? | 7.8333 | 5.7341 | 3.1333 | 17.0203
120 | 0.01 | PERT | 5 | 5 | 15 | 3.5 | #NAME? | 6.6667 | 1.9841 | 0.066667 | 0.45984
121 | 0.1 | PERT | 2 | 3 | 8 |  | #NAME? | 3.6667 | 1.0317 | 0.36667 | 1.3132
122 | 0.05 | PERT | 4 | 11 | 36 |  | #NAME? | 14 | 31.4286 | 0.7 | 10.8814
123 | 0.01 | Triang | 3 | 11 | 17 |  | #NAME? | 10.3333 | 8.2222 | 0.10333 | 1.1393
124 | 0.05 | PERT | 0 | 2 | 9 |  | #NAME? | 2.8333 | 2.496 | 0.14167 | 0.50612
125 | 0.001 | PERT | 4 | 4 | 15 |  | #NAME? | 5.8333 | 2.4008 | 0.0058333 | 0.036395
126 | 0.01 | PERT | 1 | 2 | 3 |  | #NAME? | 2 | 0.14286 | 0.02 | 0.041029
127 | 0.01 | PERT | 1 | 2 | 8 |  | #NAME? | 2.8333 | 1.3532 | 0.028333 | 0.093007
128 | 0.7 | PERT | 4 | 4 | 6 |  | #NAME? | 4.3333 | 0.079365 | 3.0333 | 3.9989
129 | 0.1 | PERT | 2 | 3 | 13 |  | #NAME? | 4.5 | 3.0357 | 0.45 | 2.1261
130 | 0.4 | PERT | 1 | 2 | 9 | 2.5 | #NAME? | 3 | 1.7143 | 1.2 | 2.8457
131 | 0.1 | PERT | 3 | 4 | 14 |  | #NAME? | 5.5 | 3.0357 | 0.55 | 3.0261
132 | 0.01 | PERT | 2 | 7 | 22 | 3 | #NAME? | 8.6667 | 12.6984 | 0.086667 | 0.87058