## Correlated risk portfolio
Correlated risk portfolio
Problem: We have a portfolio of risks (A to J), each of which is described by a PERT distribution. The risks are correlated in the following way: a) If A or C occurs, D increases in size by 50%; b) If A or D occurs, E increases to 45% probability and c) If all of B, C, E, F occur, H increases in size by 320% and to 13% probability. Our task is to calculate the total risk of the portfolio.
Risk | Min (80%) | Most likely | Max (150%) | Distribution | Probability | Risk distribution
A | 8 | 10 | 15 | #NAME? | 30% | #NAME?
B | 9.6 | 12 | 18 | #NAME? | 20% | #NAME?
C | 10.4 | 13 | 19.5 | #NAME? | 10% | #NAME?
D | 11.2 | 14 | 21 | #NAME? | #NAME? | #NAME?
E | 6.4 | 8 | 12 | #NAME? | #NAME? | #NAME?
F | 4.8 | 6 | 9 | #NAME? | 12% | #NAME?
G | 6.4 | 8 | 12 | #NAME? | 7% | #NAME?
H | 9.6 | 12 | 18 | #NAME? | #NAME? | #NAME?
I | 8.8 | 11 | 16.5 | #NAME? | 19% | #NAME?
J | 11.2 | 14 | 21 | #NAME? | 23% | #NAME?
Sum | 86.4 | 108 | 162 | #NAME? |  | #NAME?