## Sheet3 (hidden)
0 | #NAME?

## Sheet4 (hidden)
1 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!

## Sheet6 (hidden)
1 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!

## Pylons - correlated
Pylons - correlated
Problem: Your company has been invited to bid for a project to design and construct a line of 16 electricity pylons. Estimates are based on PERT distributions (using absolute minimum, most likely and absolute maximum) unless indicated. Rerun the model Pylon, but make the design time and cost 50% correlated and the time to do the foundations 40% correlated with the associated plant cost and 50% correlated with the total foundation man hours. What is the effect of including these correlations?
Number of pylons | 16
Design: | Min | Most likely | Max | Actual |  | Summary costs: | USD
Summary costs:
In-house design | 150000 | 165000 | 190000 | #NAME? |  | Design: | #NAME?
Sub-contracted | 180000 | 200000 | 235000 | #NAME? |  | Construction foundation: | #NAME?
Prob in house |  |  |  | 60% |  | Construction pylon: | #NAME?
Prob. of French job |  | 40% |  | 40% |  | Penalty: | #NAME?
|  | Total costs |  | #NAME? |  | Sum: | #NAME?
[6 empty] | Project duration: | #NAME?
Construction foundation: | Min | Most likely | Max | Actual
Material/pylon | 6200 | 7000 | 7900 | #NAME?
Man hours for all pylons |  | 9600 |  | #NAME?
Cost/man hour |  | 7.5 |  | 7.5 |  | Total time | #NAME?
Total plant cost | 250000 | 300000 | 380000 | #NAME? |  | Over time | #NAME?
[6 empty] | Weeks | #NAME?
|  | Total costs |  | #NAME? |  | Penalty/wk | 25000
[6 empty] | Penalty | #NAME?
Construction pylon: | Min | Most likely | Max | Actual
Steel cost/pylon | 52000 | 54000 | 58500 | #NAME?
Man hours/pylon | 200 | 240 | 270 | #NAME?
Cost/man hour |  | 13 |  | 13
|  | Total costs |  | #NAME?
Time constraints: | Min | Most likely | Max | Actual
Design | 10 | 12 | 15 | #NAME?
Foundations | 14 | 16 | 21 | #NAME?
Time foundation-last pylon | 4 | 4.5 | 5.5 | #NAME?
Correlation matrix
| Design time | In-house design cost | Sub design costs | Plant cost | Foundations man hours | Foundations time
Design time | 1 | 0.5 | 0.5 | 0 | 0 | 0
Design cost | 0.5 | 1 | 0 | 0 | 0 | 0
Sub design costs | 0.5 | 0 | 1 | 0 | 0 | 0
Plant cost | 0 | 0 | 0 | 1 | 0 | 0.4
Foundations man hours | 0 | 0 | 0 | 0 | 1 | 0.5
Foundations time | 0 | 0 | 0 | 0.4 | 0.5 | 1

## Scatter plot with correlation
Run on 19-Oct-99, 01:15:15 | Simulations= 1 | Iterations= 3000
Total time | Sum
Output | Output
C35 | C40
29.0554 | 1626241.125 |  | 1594952.4222
29.1954 | 1604135.375
29.2814 | 1603278.375
29.2935 | 1536912.875
29.3152 | 1572940.125
29.3305 | 1636453.625
29.3794 | 1533280.625
29.4189 | 1638939.375
29.4471 | 1608275.75
29.4682 | 1577327.125
29.4854 | 1544161.5
29.5057 | 1571400.25
29.5179 | 1574117.625
29.6015 | 1584548.625
29.6402 | 1571747.125
29.6675 | 1584396.5
29.6983 | 1569474.125
29.7425 | 1521959.5
29.7507 | 1656062.25
29.8084 | 1527697.875
29.8135 | 1596557.75
29.8292 | 1604108.625
29.8657 | 1538860.125
29.871 | 1545629.875
29.8771 | 1558607.25
29.8988 | 1589275.25
29.9013 | 1546486.5
29.9109 | 1567918.5
29.9187 | 1567019.5
29.9263 | 1567973.125
29.9319 | 1562908.75
29.9829 | 1536011.75
30.0031 | 1558299.625
30.0361 | 1617155.625
30.0497 | 1596605.25
30.056 | 1611165.125
30.0614 | 1595464.625
30.0756 | 1528831.5
30.1024 | 1545826.125
30.109 | 1580771.75
30.1154 | 1540247.375
30.1277 | 1512388.125
30.1408 | 1579969.625
30.1471 | 1532499
30.1573 | 1577735.375
30.1639 | 1574984.125
30.1816 | 1546770.125
30.1916 | 1569248
30.2117 | 1610816.5
30.2142 | 1543880.5
30.222 | 1591250.5
30.2341 | 1542958.25
30.2345 | 1576686
30.2357 | 1540072.875
30.2364 | 1568836.875
30.2381 | 1571405.375
30.2403 | 1528552
30.2406 | 1591503.375
30.2421 | 1575665.25
30.2479 | 1596172.75
30.2502 | 1492541.25
30.2588 | 1574056.75
30.2618 | 1541582.25
30.2671 | 1543859.875
30.2765 | 1555791.5
30.2842 | 1581370.125
30.2905 | 1543971.125
30.3012 | 1666286.25
30.3097 | 1550035.375
30.3116 | 1601966.125
30.3137 | 1569519.375
30.319 | 1536893.125
30.3317 | 1601013.375
30.3363 | 1583352.375
30.3381 | 1576442.125
30.3387 | 1523423
30.339 | 1577627.75
30.3439 | 1554991.5
30.3453 | 1540518
30.354 | 1564608.75
30.3558 | 1670897
30.3564 | 1602327.375
30.3689 | 1512354
30.3746 | 1576796.125
30.3773 | 1532689
30.3775 | 1611963
30.382 | 1550962.75
30.3926 | 1565158.75
30.3941 | 1649989.875
30.3951 | 1542470.25
30.3967 | 1623464.25
30.3987 | 1552938.625
30.4009 | 1643055
30.411 | 1624398.625
30.4182 | 1587601.5
30.4254 | 1533531.625
30.4386 | 1561264.5
30.4464 | 1566495
30.4485 | 1527067.75
30.4535 | 1598396.25
30.4535 | 1522362.5
30.4539 | 1569127.75
30.46 | 1651514.375
30.4605 | 1572124.875
30.4612 | 1559840.125
30.4689 | 1552974.375
30.4797 | 1528400.875
30.4803 | 1503431.875
30.4856 | 1616610.25
30.4867 | 1582709.25
30.4895 | 1569219.5
30.4906 | 1521554.25
30.4916 | 1638825.25
30.4984 | 1638364.375
30.4985 | 1548562.5
30.5025 | 1529769.5
30.5055 | 1484454.75
30.5158 | 1589795.875
30.5241 | 1569329.125
30.5247 | 1532789.875
30.5279 | 1556301.75
30.5345 | 1626839
30.5355 | 1549920.125
30.5453 | 1569851.375
30.547 | 1548271.25
30.5475 | 1589373
30.5512 | 1617896.875
30.5525 | 1523974.875
30.554 | 1563754.875
30.5561 | 1546353.25
30.5595 | 1538461.625
30.5666 | 1609952.625
30.5673 | 1520134.875
30.5681 | 1561424.5
30.573 | 1582787.625
30.5785 | 1568593.625
30.5792 | 1551695.5
30.5795 | 1549741.5
30.5816 | 1605325.5
30.5828 | 1544003.75
30.5849 | 1584282.5
30.6092 | 1534172
30.6141 | 1595037.75
30.6249 | 1568271.75
30.6278 | 1601728
30.6296 | 1600988.125
30.6337 | 1598582.5
30.6359 | 1583764
30.638 | 1573778.625
30.6388 | 1556248.375
30.6417 | 1595908.125
30.6423 | 1629682.25
30.644 | 1608478
30.647 | 1608624.125
30.6589 | 1591293.625
30.6617 | 1562273.25
30.6698 | 1550088.5
30.6704 | 1600681
30.6781 | 1572486.25
30.6836 | 1549230.5
30.6841 | 1615961.5
30.685 | 1575960.625
30.6957 | 1530586.25
30.7008 | 1515421.5
30.7031 | 1544220.375
30.7107 | 1581500.125
30.7194 | 1590827.75
30.72 | 1613931.25
30.723 | 1518459
30.7306 | 1519245
30.7433 | 1625183.125
30.7468 | 1593015.625
30.7485 | 1525057.75
30.754 | 1603223.625
30.7623 | 1574454.125
30.7638 | 1559684.125
30.7644 | 1569576.75
30.7674 | 1567952.875
30.7692 | 1555599.5
30.7698 | 1624742.875
30.7704 | 1561273.25
30.7714 | 1565295
30.7716 | 1540585.875
30.7765 | 1564037.625
30.7835 | 1548915.5
30.7843 | 1601782.25
30.7983 | 1537214.875
30.7987 | 1667481
30.8028 | 1613592.75
30.8064 | 1639913.125
30.814 | 1510864.875
30.8165 | 1569624.625
30.8246 | 1522340.5
30.8266 | 1562881
30.8287 | 1580654
30.8312 | 1572032.75
30.8347 | 1597497
30.8377 | 1540954.25
30.8399 | 1543719.375
30.8412 | 1633491.75
30.8517 | 1547155.375
30.858 | 1590641.75
30.8688 | 1548669.75
30.8783 | 1537437
30.8794 | 1593553.5
30.8931 | 1615322.5
30.8951 | 1588131.625
30.8957 | 1589770.25
30.8971 | 1593713.625
30.9018 | 1556304.75
30.9041 | 1542955.75
30.9118 | 1615663.625
30.921 | 1595117.25
30.9234 | 1560359.625
30.9261 | 1558004.625
30.9271 | 1564588.25
30.9302 | 1546762.75
30.9386 | 1563425.875
30.9455 | 1563578.5
30.9479 | 1586121.5
30.9503 | 1576359.125
30.9509 | 1600378
30.9561 | 1560748.625
30.9578 | 1553536.25
30.9579 | 1559677.875
30.96 | 1560853.375
30.9645 | 1595979.25
30.9694 | 1607081.375
30.9729 | 1589060.875
30.9754 | 1579636.625
30.979 | 1558008.875
30.9807 | 1556582
30.9818 | 1613029.25
30.9818 | 1569967.625
30.983 | 1525157
30.9842 | 1644611.875
30.9857 | 1577303
30.9866 | 1561303.75
30.9884 | 1538877.375
30.9892 | 1652084.125
30.9899 | 1576312.25
30.9938 | 1588798.375
30.9955 | 1583756.875
30.9966 | 1557726.5
31 | 1559235.875
31.0029 | 1560817.125
31.009 | 1581828.125
31.0173 | 1605404.875
31.0175 | 1546310.125
31.0222 | 1516681.25
31.026 | 1573263.375
31.0274 | 1514341.875
31.0274 | 1571602.625
31.0311 | 1517022.625
31.0316 | 1581251.625
31.0328 | 1552481.125
31.037 | 1520745.625
31.0374 | 1637003.125
31.0393 | 1585722.375
31.0396 | 1664111.375
31.0446 | 1603698
31.0457 | 1591190.5
31.0499 | 1589285.875
31.0528 | 1601764.125
31.0538 | 1627417.5
31.0545 | 1600441
31.057 | 1527389.125
31.0613 | 1568140.875
31.0632 | 1591915.875
31.0645 | 1623821
31.0657 | 1521133.375
31.0667 | 1528101.375
31.0728 | 1604619.375
31.077 | 1532751.125
31.0771 | 1613070.5
31.078 | 1556341.625
31.0807 | 1545566.375
31.0818 | 1617624
31.0818 | 1539845.625
31.0826 | 1525367.125
31.0872 | 1591565.5
31.0904 | 1592825.5
31.0945 | 1599235.5
31.095 | 1562024.75
31.0958 | 1535981.625
31.0976 | 1550745.75
31.1004 | 1514158.25
31.101 | 1536495.5
31.1038 | 1508031.375
31.1049 | 1573955.75
31.1093 | 1558279.375
31.113 | 1603972.625
31.1135 | 1595265
31.1195 | 1568725.875
31.1206 | 1543470.625
31.1207 | 1514164.375
31.1265 | 1550481.75
31.1266 | 1560841.25
31.1322 | 1580093.75
31.1328 | 1535550.5
31.1344 | 1562980.875
31.1372 | 1575742.75
31.1379 | 1565402.125
31.1408 | 1662208.625
31.1412 | 1593558.75
31.1495 | 1615219.5
31.1528 | 1530273.5
31.155 | 1601060
31.1575 | 1563250
31.1577 | 1586118.125
31.1577 | 1510702
31.1599 | 1526797.75
31.1608 | 1637708.375
31.1618 | 1543345.875
31.1626 | 1592085
31.1636 | 1557192.375
31.166 | 1542323.5
31.166 | 1600379.5
31.1749 | 1509176.25
31.1759 | 1606583.75
31.1828 | 1571393.25
31.1838 | 1533633.375
31.1853 | 1512587.875
31.1881 | 1598899.5
31.1885 | 1575158.25
31.189 | 1629433.75
31.1899 | 1637716.375
31.1915 | 1546539.625
31.1922 | 1583807
31.1929 | 1521956.875
31.1955 | 1542231.875
31.1992 | 1537219.875
31.1993 | 1545557.75
31.1996 | 1576618.25
31.2014 | 1532308.75
31.2111 | 1539015
31.2205 | 1582668.25
31.2206 | 1558167.75
31.2225 | 1622770.75
31.2228 | 1581525.125
31.2236 | 1635065.75
31.2262 | 1569254.25
31.228 | 1590593
31.232 | 1603761.125
31.2325 | 1576393.875
31.2335 | 1522593.25
31.2367 | 1552180.375
31.2369 | 1569488.125
31.2425 | 1692519.25
31.2437 | 1591920.125
31.2454 | 1613119.375
31.2487 | 1598801.625
31.252 | 1652297.5
31.2572 | 1558585.875
31.2642 | 1590841.875
31.2662 | 1633305.375
31.2666 | 1614036.375
31.2701 | 1524329.875
31.2805 | 1526898
31.2819 | 1544605
31.2829 | 1552991
31.2834 | 1580207.875
31.2861 | 1532821
31.2884 | 1626678
31.2891 | 1591434.875
31.2893 | 1584746.625
31.2932 | 1570401.125
31.2945 | 1512407.375
31.2968 | 1634897.75
31.2979 | 1648442.75
31.3003 | 1589263.5
31.3026 | 1533018.75
31.303 | 1584795.125
31.3045 | 1521587.25
31.3075 | 1580888.625
31.3174 | 1552229.75
31.3188 | 1509864
31.32 | 1606964.625
31.32 | 1602678.875
31.3206 | 1573643.125
31.3233 | 1537493.75
31.3248 | 1551374.5
31.3285 | 1535200.875
31.3287 | 1545260.125
31.3321 | 1549105.5
31.3339 | 1512097.25
31.3345 | 1549454.875
31.3389 | 1619933.5
31.3401 | 1543946.5
31.3406 | 1575269.875
31.3461 | 1563018.25
31.3485 | 1583873.875
31.3498 | 1587927.625
31.3502 | 1596525.5
31.3521 | 1606582.625
31.3527 | 1572062.625
31.3546 | 1598920.25
31.3551 | 1563086.125
31.3576 | 1639572.75
31.3622 | 1618147.625
31.3636 | 1581274.625
31.3681 | 1575849.5
31.3695 | 1564908.625
31.37 | 1605988.875
31.3715 | 1610488.875
31.3772 | 1589730.125
31.3781 | 1545603.625
31.3799 | 1673652.625
31.38 | 1549368.25
31.3869 | 1612003.75
31.3874 | 1581991.125
31.3887 | 1584268.25
31.3917 | 1521863.875
31.3933 | 1595700
31.3984 | 1563363.25
31.3986 | 1568937.625
31.401 | 1582362.375
31.4051 | 1576265.25
31.4079 | 1573513
31.409 | 1563948
31.4096 | 1603980.25
31.4107 | 1547218.875
31.4132 | 1526502.125
31.4159 | 1560167.125
31.4173 | 1564047.375
31.4176 | 1601831.875
31.4205 | 1504357.375
31.4221 | 1569806
31.4229 | 1493326
31.4255 | 1595066.625
31.4284 | 1593415.875
31.4294 | 1538438.25
31.4296 | 1547094
31.43 | 1577457.625
31.4304 | 1578390.75
31.4363 | 1622370.625
31.4364 | 1609935.125
31.4389 | 1541358.625
31.4393 | 1532484.875
31.4398 | 1586954.375
31.4411 | 1554496
31.4447 | 1597748.75
31.4464 | 1625504
31.4472 | 1584729.625
31.4476 | 1585273.125
31.4502 | 1607342.625
31.4539 | 1584472.875
31.459 | 1563675
31.464 | 1570915.875
31.4641 | 1627322.375
31.4679 | 1521238.125
31.4679 | 1606845
31.4693 | 1569671.625
31.4701 | 1574614.25
31.4756 | 1616467.875
31.485 | 1576851
31.4864 | 1607825.125
31.4867 | 1593237.375
31.4868 | 1610916.75
31.4902 | 1571140.875
31.4916 | 1552039.75
31.4963 | 1579194.5
31.499 | 1620770.75
31.5009 | 1566510.5
31.5025 | 1615864.25
31.5031 | 1540762.375
31.5091 | 1545915.375
31.5111 | 1561197.375
31.5124 | 1547939.625
31.515 | 1655608.5
31.5159 | 1592556.5
31.5181 | 1549423
31.5212 | 1569964.125
31.5288 | 1559675.5
31.5315 | 1589308.375
31.5353 | 1552143.375
31.5424 | 1606830.625
31.5424 | 1551676.25
31.547 | 1553984.5
31.5495 | 1539445
31.5508 | 1615547.125
31.5582 | 1579849
31.5603 | 1581733.375
31.5604 | 1540930.875
31.5679 | 1559638.375
31.5686 | 1653261.375
31.569 | 1686053
31.5693 | 1578092.625
31.5748 | 1597627.875
31.5752 | 1512212.5
31.5771 | 1549985.75
31.5772 | 1572681.125
31.5805 | 1562405.25
31.5812 | 1665331.375
31.5813 | 1575044.5
31.5814 | 1551611.625
31.5816 | 1580359.5
31.5865 | 1586550.5
31.5886 | 1541035.625
31.589 | 1595049.875
31.5911 | 1576750
31.5934 | 1569159.875
31.5936 | 1532943.125
31.5951 | 1529812.125
31.5952 | 1615386.125
31.5958 | 1586220
31.5972 | 1572853.625
31.5978 | 1561442.125
31.5997 | 1526359
31.5999 | 1514748.25
31.6015 | 1518610.625
31.6034 | 1544420.375
31.6039 | 1571353.25
31.604 | 1520215.125
31.6082 | 1560863
31.6151 | 1562445.625
31.6156 | 1540939.5
31.6169 | 1656629.375
31.6179 | 1552150.375
31.6206 | 1645006.125
31.6222 | 1521480.375
31.6229 | 1619300.625
31.6294 | 1512041.25
31.6302 | 1604066.875
31.6311 | 1597331
31.6361 | 1529631.25
31.6421 | 1563721.625
31.6503 | 1597623.125
31.6515 | 1528132.125
31.6534 | 1588636.625
31.6553 | 1525189.625
31.6586 | 1515385.875
31.6601 | 1514030.75
31.6626 | 1523937.5
31.6627 | 1612643.125
31.6649 | 1547084.5
31.6655 | 1616506.75
31.6679 | 1580687.5
31.6694 | 1580814.75
31.6733 | 1598269.625
31.6784 | 1627185.375
31.6812 | 1573991.25
31.6812 | 1589675.625
31.6828 | 1549693.875
31.6848 | 1648238.875
31.6921 | 1582288.625
31.6931 | 1558561.5
31.6969 | 1537791.5
31.6979 | 1559135.5
31.6997 | 1564669.5
31.7029 | 1590973.75
31.7045 | 1599567.25
31.7048 | 1592322
31.705 | 1553806.375
31.707 | 1532672.375
31.71 | 1590677.625
31.7125 | 1629342.625
31.7149 | 1551901.375
31.715 | 1537934.875
31.717 | 1532210.75
31.7196 | 1525853.875
31.7196 | 1615196.75
31.7208 | 1540053.25
31.7214 | 1594647
31.7234 | 1557360.375
31.7306 | 1534801
31.7326 | 1591138.375
31.7326 | 1648489.375
31.737 | 1555259.5
31.7378 | 1528618.625
31.738 | 1636428.375
31.7383 | 1561503.625
31.7385 | 1578215.25
31.7393 | 1569459.5
31.74 | 1573972.625
31.7431 | 1566362.125
31.7455 | 1574784.875
31.7479 | 1604621.625
31.7485 | 1630009
31.7502 | 1595196.125
31.7511 | 1580048.875
31.7526 | 1536962.5
31.7561 | 1541264.5
31.7581 | 1583277.875
31.7587 | 1577752.5
31.7604 | 1611698.5
31.7654 | 1583605.75
31.7666 | 1584541.25
31.7687 | 1561978.5
31.7688 | 1601042.625
31.7698 | 1597669.875
31.7747 | 1564882.625
31.775 | 1619564.375
31.7761 | 1583178.75
31.7786 | 1539057.5
31.779 | 1572457.75
31.7794 | 1608564.375
31.7881 | 1555633.625
31.7899 | 1548050.375
31.791 | 1623135.5
31.793 | 1570109.625
31.7932 | 1599809.875
31.7961 | 1583572.375
31.7985 | 1565251
31.7992 | 1670568.125
31.8004 | 1627209.875
31.8028 | 1563740.25
31.8036 | 1539586.75
31.8066 | 1579917.25
31.8073 | 1598956.5
31.8078 | 1620551.625
31.8083 | 1525447.5
31.8096 | 1537883.75
31.8122 | 1599363.25
31.8167 | 1556343.75
31.8192 | 1590495.125
31.8199 | 1617368.125
31.8202 | 1534821.125
31.8211 | 1530540.25
31.8215 | 1558793.5
31.8248 | 1585181.375
31.827 | 1588080.25
31.8285 | 1588519.25
31.8299 | 1610305.25
31.8324 | 1608417.875
31.8344 | 1508841.125
31.838 | 1547707.625
31.8388 | 1626365.625
31.8407 | 1580255.25
31.842 | 1575168.75
31.8423 | 1575210.625
31.8429 | 1600398.625
31.8442 | 1590593.125
31.847 | 1637209.875
31.849 | 1563505.875
31.8498 | 1576116.375
31.8512 | 1665588.875
31.8517 | 1584505.875
31.852 | 1589928
31.8525 | 1685273.75
31.8538 | 1592557
31.8552 | 1571106.625
31.8566 | 1555895.125
31.8591 | 1621319.5
31.8603 | 1546970
31.8661 | 1660264.875
31.8675 | 1558657.375
31.8675 | 1603509.5
31.8678 | 1566786
31.8695 | 1600061.125
31.8699 | 1530629
31.8768 | 1617285.75
31.8803 | 1632680.625
31.8826 | 1570524.25
31.8826 | 1546012.875
31.8827 | 1540925.5
31.8855 | 1537115.625
31.8867 | 1563221.625
31.8879 | 1528481
31.888 | 1605909.25
31.8881 | 1598108.875
31.8892 | 1631869.375
31.891 | 1632603
31.8915 | 1579847.625
31.8918 | 1582577.875
31.893 | 1565388.875
31.8931 | 1544285.25
31.8984 | 1620682.625
31.9037 | 1643143.5
31.9052 | 1555704.75
31.9089 | 1672933.75
31.9137 | 1608502.625
31.9149 | 1570395.5
31.9221 | 1559226
31.9234 | 1621975.625
31.9252 | 1520532
31.9277 | 1638383
31.9284 | 1596952.375
31.9322 | 1547207.625
31.9367 | 1521611.75
31.9384 | 1568980.125
31.9387 | 1583292.5
31.9445 | 1555941.625
31.9451 | 1576212.375
31.946 | 1534618.625
31.9472 | 1574679.75
31.9483 | 1585911.125
31.95 | 1567253.375
31.9503 | 1621545.375
31.9508 | 1638293.75
31.953 | 1545993.5
31.956 | 1616323.875
31.9562 | 1563200.5
31.9616 | 1590049.375
31.9625 | 1555517.125
31.9631 | 1556900.875
31.964 | 1588025.625
31.9646 | 1541736.375
31.9679 | 1553739.25
31.9692 | 1604305.125
31.97 | 1620662
31.9704 | 1562896.75
31.9721 | 1552240.875
31.9731 | 1612082.875
31.9742 | 1592957.875
31.9774 | 1631906.75
31.9793 | 1540316.375
31.9807 | 1529938.125
31.981 | 1543276.125
31.9813 | 1599534.875
31.9842 | 1594889.25
31.9843 | 1540980.75
31.9872 | 1582044.625
31.9882 | 1553536.875
31.9888 | 1601606
31.994 | 1539965.75
31.9947 | 1625745.375
31.9975 | 1582722.875
31.9988 | 1528569.5
31.9989 | 1580069.125
32.0004 | 1539629.875
32.0018 | 1540882.75
32.0019 | 1575714.875
32.0029 | 1596281.875
32.0067 | 1555596.875
32.0092 | 1617282.25
32.0157 | 1584404
32.0161 | 1558510.25
32.02 | 1580054.5
32.0204 | 1568437.125
32.0229 | 1562465.375
32.0288 | 1562931
32.0288 | 1595848.125
32.0301 | 1549589
32.0306 | 1617274.125
32.0312 | 1551785.625
32.0312 | 1551258.75
32.0343 | 1584120.375
32.0347 | 1620665.75
32.035 | 1610339.75
32.0361 | 1556575.375
32.0362 | 1578304.375
32.038 | 1582129.25
32.0391 | 1565899
32.0413 | 1612436.625
32.0419 | 1619833.125
32.0431 | 1548774.375
32.0431 | 1610194.625
32.0443 | 1657722.75
32.0489 | 1558682.375
32.05 | 1543648.625
32.0507 | 1547105.75
32.0513 | 1666715.5
32.0527 | 1614963.375
32.0547 | 1645322.25
32.0565 | 1571305.375
32.0595 | 1515904.25
32.0606 | 1560494.5
32.0627 | 1525723
32.0629 | 1568743.375
32.0655 | 1534101.125
32.0661 | 1549393.375
32.0664 | 1597267.25
32.0664 | 1528025.25
32.0679 | 1634700.875
32.0679 | 1587489.875
32.0748 | 1525983.875
32.0749 | 1616529.875
32.0753 | 1601818.5
32.0753 | 1559622.875
32.0754 | 1574799.75
32.0808 | 1540840.5
32.0837 | 1576366
32.0861 | 1680871.75
32.0877 | 1580416.5
32.088 | 1658554.875
32.0932 | 1613249.625
32.0959 | 1508115.25
32.102 | 1563767.625
32.1021 | 1605093.75
32.1021 | 1552658.375
32.1028 | 1570560
32.1049 | 1579070.5
32.1053 | 1532936.75
32.1056 | 1563291.375
32.1063 | 1665072.625
32.1122 | 1598752.75
32.1136 | 1606420.5
32.1161 | 1622825.375
32.1176 | 1553831
32.118 | 1636428.25
32.1189 | 1570581.625
32.12 | 1556675.75
32.1224 | 1574314.25
32.1225 | 1600927.125
32.1232 | 1585568.75
32.1254 | 1616683.875
32.1261 | 1546356.75
32.1298 | 1591622.875
32.1317 | 1571624.875
32.1336 | 1535333.875
32.1348 | 1546385.125
32.1356 | 1593753.875
32.1375 | 1571829.875
32.14 | 1532779.5
32.1407 | 1554784.125
32.1409 | 1561728.125
32.1409 | 1615066.5
32.1413 | 1575459.875
32.1456 | 1576552.625
32.1466 | 1589117.625
32.1478 | 1537532.25
32.1492 | 1587991.5
32.1495 | 1589306.5
32.1503 | 1537375
32.151 | 1584935.375
32.1542 | 1605148.5
32.1568 | 1551787.25
32.1575 | 1651284.875
32.1591 | 1607794.75
32.1615 | 1608345.875
32.1646 | 1588628
32.1651 | 1647192
32.1655 | 1633858.375
32.166 | 1585937.75
32.1698 | 1581220.75
32.1701 | 1618934
32.1717 | 1545761.125
32.1719 | 1571717.75
32.1754 | 1528609.625
32.1755 | 1580459.25
32.1759 | 1579404.375
32.1761 | 1515438.5
32.1772 | 1583791.125
32.1785 | 1630177.125
32.1813 | 1568391.25
32.1849 | 1537411.875
32.1884 | 1521314.125
32.1888 | 1550046.25
32.1919 | 1631818.75
32.1926 | 1599828.875
32.1956 | 1546683.125
32.1991 | 1578009.875
32.2067 | 1510601
32.2067 | 1574309
32.2071 | 1528566.875
32.2092 | 1624573.375
32.2095 | 1618570
32.2104 | 1534023.25
32.2141 | 1586360.625
32.2148 | 1592600.25
32.2148 | 1521283.625
32.218 | 1592040.25
32.2211 | 1593696.5
32.2228 | 1664158.875
32.2236 | 1615732
32.2252 | 1570291.25
32.2257 | 1630679.375
32.2277 | 1551655.375
32.2283 | 1552319.125
32.2358 | 1544761.75
32.2362 | 1583375.125
32.2375 | 1623119.75
32.2392 | 1548185.25
32.241 | 1646142
32.242 | 1554868
32.2422 | 1586026.625
32.2444 | 1521553.625
32.2451 | 1633940.5
32.2517 | 1556271.75
32.2547 | 1605754
32.2567 | 1575055.625
32.2568 | 1556587.375
32.2569 | 1552679.375
32.2584 | 1576886.375
32.2586 | 1585867.75
32.2599 | 1531135.125
32.2625 | 1582468.625
32.263 | 1580640.875
32.2634 | 1532272.875
32.2659 | 1554910.5
32.2661 | 1502124.875
32.2678 | 1604441.125
32.2692 | 1616261.5
32.2736 | 1543388
32.2745 | 1582777.375
32.2758 | 1605836.375
32.2809 | 1582080.625
32.2829 | 1552559.25
32.283 | 1574516.125
32.2862 | 1525111.875
32.2902 | 1599132.625
32.2936 | 1555547.5
32.2954 | 1625729
32.296 | 1630085.75
32.2991 | 1580078.5
32.3008 | 1585013.125
32.3018 | 1568944.25
32.3049 | 1576207
32.3062 | 1558125.25
32.3064 | 1577970.625
32.3068 | 1556137.75
32.3075 | 1542277.625
32.3078 | 1626209.625
32.309 | 1611941.625
32.3102 | 1610638.25
32.3154 | 1582993
32.3169 | 1530456
32.3209 | 1596958.5
32.322 | 1605882.5
32.3223 | 1554004.875
32.3238 | 1554030.125
32.3284 | 1657097.5
32.3297 | 1576506.5
32.3349 | 1594932.5
32.3351 | 1622013.875
32.3368 | 1614243.375
32.3375 | 1634403
32.3376 | 1598275
32.3389 | 1567785.375
32.3398 | 1571582.75
32.3414 | 1600541.25
32.3418 | 1536659.875
32.342 | 1539455.125
32.3448 | 1564960.75
32.3472 | 1526033.75
32.3475 | 1587876.625
32.3495 | 1628669
32.3501 | 1516673
32.3516 | 1552226.125
32.3533 | 1611616.375
32.3539 | 1625573
32.354 | 1643534.375
32.354 | 1566737.875
32.3554 | 1600096.875
32.3582 | 1614407.75
32.3608 | 1615370.125
32.361 | 1560492.625
32.3628 | 1584876.5
32.3647 | 1614378.375
32.3673 | 1576558.125
32.368 | 1574323.375
32.3692 | 1644957.625
32.3725 | 1584810.875
32.3755 | 1618400.125
32.3776 | 1549116.75
32.378 | 1605202.875
32.379 | 1668920.125
32.379 | 1518279.25
32.3805 | 1506168
32.3812 | 1592716.25
32.3843 | 1594196.625
32.3863 | 1588343.375
32.3874 | 1583384.375
32.3883 | 1584265.375
32.3901 | 1622033.375
32.3916 | 1568525.25
32.394 | 1620329.75
32.3949 | 1584430.875
32.3973 | 1539316.5
32.3993 | 1587943.25
32.3999 | 1637477.125
32.4007 | 1595311.875
32.4008 | 1586702.875
32.401 | 1589291.5
32.4013 | 1559038.875
32.4031 | 1582795.375
32.4045 | 1597129
32.4059 | 1622148.625
32.4068 | 1548535.75
32.4123 | 1633034.875
32.4154 | 1575130.375
32.4156 | 1620810.75
32.4156 | 1549247.875
32.4175 | 1577008.75
32.4239 | 1551165.125
32.4292 | 1598864.625
32.4305 | 1538865.875
32.4308 | 1604610.125
32.4323 | 1557651.375
32.4333 | 1562737
32.4333 | 1567925.625
32.4375 | 1618677.25
32.4378 | 1577694.5
32.4379 | 1632717.625
32.438 | 1589767.75
32.4388 | 1583099.25
32.4391 | 1619012.875
32.4404 | 1592832.75
32.4431 | 1625277.625
32.4445 | 1570237.25
32.4486 | 1582057.125
32.45 | 1519429.375
32.45 | 1599910
32.4518 | 1613309.75
32.4524 | 1546303.75
32.4535 | 1562915.25
32.4537 | 1504860.125
32.4543 | 1591482.125
32.4554 | 1592146.75
32.4559 | 1568844.75
32.4576 | 1623375.75
32.4584 | 1650707
32.4593 | 1594558.875
32.4603 | 1580368.625
32.4627 | 1573744.125
32.4627 | 1597287.875
32.4707 | 1511693.75
32.4721 | 1601999.25
32.4724 | 1594028.75
32.4737 | 1604743
32.4777 | 1587863.25
32.4784 | 1501261.125
32.4789 | 1528728.5
32.4803 | 1624620
32.4805 | 1510051.125
32.4808 | 1683501.625
32.482 | 1541264
32.4842 | 1625817.875
32.4853 | 1551228.375
32.4863 | 1556369.375
32.4884 | 1556803.375
32.491 | 1583085.625
32.4928 | 1556076.375
32.4944 | 1574011
32.4944 | 1587976.125
32.4955 | 1562837.875
32.4972 | 1558440.375
32.4984 | 1565644.625
32.4999 | 1573957.75
32.5005 | 1582435.5
32.5014 | 1599561.375
32.5019 | 1555277.75
32.5028 | 1623868
32.5044 | 1582639.5
32.5046 | 1567276.75
32.5048 | 1551036.75
32.5068 | 1565174.625
32.5069 | 1620520.25
32.5096 | 1602402.875
32.5096 | 1549876.375
32.5116 | 1638384.875
32.5117 | 1578657.75
32.5161 | 1557283.75
32.5173 | 1610302.625
32.5179 | 1589233.625
32.5189 | 1551854.25
32.5197 | 1584895.25
32.5202 | 1650846.875
32.5206 | 1535858.75
32.5212 | 1582212.75
32.5228 | 1581880
32.5229 | 1569821
32.5244 | 1612652.75
32.5266 | 1550059.125
32.5276 | 1607586.375
32.529 | 1613246.875
32.5291 | 1531888.125
32.5324 | 1566459.375
32.5326 | 1589036.375
32.5343 | 1583063.375
32.5351 | 1573093
32.5371 | 1534990.125
32.5413 | 1573728
32.5425 | 1586649
32.5431 | 1696474.125
32.5485 | 1606724.25
32.5516 | 1579449.125
32.5519 | 1609834.875
32.5521 | 1518224.375
32.5548 | 1591257.5
32.5556 | 1589373
32.5625 | 1638285.5
32.5634 | 1507009.25
32.5647 | 1574892.25
32.5653 | 1589406
32.5662 | 1549177.125
32.5678 | 1573794.375
32.5692 | 1617633.75
32.5707 | 1556571.25
32.5735 | 1554010.625
32.5736 | 1559411
32.5744 | 1597295.375
32.5753 | 1563496.875
32.5755 | 1570379.125
32.5796 | 1582031.875
32.5797 | 1539810.75
32.5807 | 1615037.625
32.5818 | 1546682.75
32.5833 | 1535110.375
32.5842 | 1535433.125
32.5855 | 1579974.625
32.5873 | 1601736.125
32.5878 | 1618858.625
32.5892 | 1579557.875
32.5897 | 1554130.375
32.5902 | 1578862.375
32.5948 | 1614301
32.5949 | 1559508.625
32.5961 | 1607170.25
32.5964 | 1590626.375
32.5975 | 1631846.625
32.5985 | 1612695.375
32.6003 | 1552082.375
32.6019 | 1524115.375
32.6087 | 1586352.25
32.6089 | 1544742
32.6091 | 1564430.875
32.6111 | 1607729.125
32.6121 | 1543700
32.6139 | 1557330.375
32.6147 | 1608471.75
32.6166 | 1520893.5
32.6211 | 1547881.875
32.6216 | 1603898.375
32.6217 | 1540922.875
32.6217 | 1582994.25
32.6225 | 1643614.625
32.6271 | 1592716.375
32.628 | 1610897.5
32.63 | 1659863.75
32.6303 | 1551669.25
32.6304 | 1652602.625
32.6312 | 1535035.375
32.6319 | 1622195.125
32.6319 | 1542508.25
32.6366 | 1593634.5
32.6368 | 1593294.375
32.6376 | 1642527
32.6402 | 1587948
32.6453 | 1611353.5
32.6456 | 1610497.25
32.6486 | 1534789.75
32.6534 | 1638842.625
32.6543 | 1590423.25
32.6585 | 1543795.375
32.66 | 1622208.25
32.662 | 1601918.25
32.6641 | 1623562
32.6662 | 1563823.75
32.6666 | 1613740.75
32.6678 | 1615832.5
32.6686 | 1559095.75
32.6691 | 1573617.375
32.6705 | 1586076.25
32.6736 | 1594041.125
32.6738 | 1629690.625
32.6741 | 1538794.25
32.6746 | 1595447.625
32.6753 | 1536539.875
32.6759 | 1609492.125
32.6777 | 1571158.25
32.6795 | 1587028.125
32.6864 | 1616565.875
32.6874 | 1522283.875
32.6878 | 1569065.375
32.6886 | 1553876.625
32.6891 | 1587790.625
32.6904 | 1594872.625
32.6919 | 1563908.375
32.6931 | 1607293.75
32.6933 | 1576073.625
32.6955 | 1610682.5
32.698 | 1599772.25
32.6988 | 1607244.5
32.6989 | 1620081.25
32.6994 | 1519367.75
32.7012 | 1618989
32.7022 | 1625340.875
32.7037 | 1574740.5
32.7043 | 1528972.375
32.7045 | 1605636.375
32.705 | 1605101.875
32.7063 | 1571754.625
32.7065 | 1582221.125
32.7082 | 1581470.25
32.7106 | 1558435.5
32.7115 | 1591324.875
32.712 | 1642148
32.7133 | 1582218.5
32.7145 | 1544599.5
32.7161 | 1626603.75
32.7179 | 1556920.75
32.7203 | 1549613.875
32.7228 | 1547344.75
32.7274 | 1586854
32.7292 | 1573856.125
32.73 | 1538315.875
32.7309 | 1557022.875
32.7319 | 1571490.75
32.7332 | 1575215.875
32.7383 | 1606908.5
32.74 | 1551764.25
32.7413 | 1600203.5
32.7441 | 1582662.125
32.7444 | 1584022.5
32.7462 | 1569430.75
32.7483 | 1526677.375
32.7502 | 1591964.375
32.7503 | 1612484.5
32.7509 | 1596450
32.753 | 1603531.75
32.7563 | 1542614.75
32.7587 | 1651339.125
32.7606 | 1557187
32.7618 | 1537508.5
32.7619 | 1593063
32.7633 | 1556756.625
32.7652 | 1572446.5
32.7666 | 1552045.5
32.7676 | 1589988.5
32.77 | 1571147
32.7706 | 1609628
32.7727 | 1637514.375
32.7753 | 1615409.875
32.7781 | 1590992.75
32.7782 | 1617323.875
32.7797 | 1583343.125
32.7801 | 1588105.625
32.7805 | 1632872.75
32.7814 | 1581262.25
32.7858 | 1634810.625
32.7869 | 1594701.375
32.7878 | 1652694.875
32.788 | 1583493.25
32.795 | 1605944
32.7988 | 1569108.625
32.8022 | 1565389
32.8023 | 1565520.125
32.8027 | 1568067
32.804 | 1613264.875
32.8076 | 1576064.625
32.8076 | 1600613.5
32.8079 | 1593986.5
32.8103 | 1606545
32.8124 | 1532780.5
32.8162 | 1613472.375
32.8164 | 1555078.875
32.8168 | 1607064.125
32.8174 | 1506798.875
32.8183 | 1570473.125
32.8183 | 1610995.125
32.819 | 1595327.875
32.821 | 1593800.875
32.821 | 1676847.625
32.8217 | 1648302.25
32.8219 | 1691180.625
32.8222 | 1557965.375
32.8235 | 1597944.375
32.8239 | 1607789.375
32.8255 | 1610165.5
32.8281 | 1601774.75
32.8291 | 1569986.625
32.83 | 1531623.75
32.8349 | 1626510.875
32.8349 | 1557767
32.8365 | 1567130.5
32.8382 | 1573081.375
32.8403 | 1546326.875
32.8413 | 1572597.875
32.842 | 1516818.5
32.8426 | 1583054.875
32.8447 | 1603298
32.845 | 1555693
32.8462 | 1642755
32.8505 | 1526641.625
32.8528 | 1631295
32.8536 | 1572921.375
32.8537 | 1538156.875
32.854 | 1598285.75
32.856 | 1564209.875
32.8573 | 1548517.875
32.8573 | 1577998.875
32.8578 | 1585349
32.8585 | 1606679.25
32.8587 | 1673860.75
32.8592 | 1632595.875
32.8596 | 1580537.375
32.8598 | 1602795.625
32.8616 | 1565318.375
32.8629 | 1584249.625
32.8648 | 1592431.875
32.865 | 1614101.5
32.8666 | 1541917.5
32.8678 | 1581817.25
32.8682 | 1655486.25
32.8684 | 1495629.625
32.8694 | 1569112.5
32.8699 | 1587190.5
32.8753 | 1654332.375
32.876 | 1624975.625
32.8766 | 1555012.875
32.8766 | 1549481
32.8771 | 1614348.25
32.8788 | 1586458.75
32.8817 | 1612172.5
32.8826 | 1564168.625
32.8834 | 1594395.375
32.8848 | 1675978.125
32.8853 | 1673855.25
32.8873 | 1486950.875
32.8881 | 1600202.75
32.8886 | 1633555
32.8899 | 1648834.75
32.89 | 1529131.125
32.8937 | 1562534.375
32.8972 | 1636267.125
32.8985 | 1531638.375
32.9003 | 1498102
32.9016 | 1543169.125
32.9048 | 1542608.625
32.9075 | 1541737.875
32.9084 | 1622249
32.9115 | 1583530.5
32.9182 | 1600707.125
32.9197 | 1595391.75
32.9197 | 1582281.375
32.9199 | 1548477.625
32.9201 | 1569808.375
32.9213 | 1563131
32.924 | 1601025.875
32.9245 | 1559776.25
32.9277 | 1564355.5
32.9281 | 1624626.625
32.9309 | 1603957.25
32.9322 | 1583474.625
32.9339 | 1643241.625
32.9359 | 1559248.25
32.9362 | 1601325.125
32.9367 | 1559362.625
32.9399 | 1589864.75
32.9414 | 1567804.75
32.942 | 1583044.625
32.942 | 1569826.875
32.9428 | 1602000.75
32.9432 | 1604480.375
32.9454 | 1596423.875
32.948 | 1536712.625
32.9513 | 1601494.75
32.9524 | 1536801.75
32.9565 | 1583022.75
32.9566 | 1629145.5
32.9586 | 1588163.25
32.9604 | 1588407.875
32.9606 | 1585814.125
32.961 | 1634026.625
32.9613 | 1614586.5
32.9626 | 1620789.375
32.9654 | 1589517.25
32.9671 | 1562893.5
32.9709 | 1633867
32.9726 | 1618599.875
32.9739 | 1571466.75
32.974 | 1580378.375
32.9749 | 1637201.875
32.9762 | 1556563.75
32.9767 | 1566290.875
32.9769 | 1613694.375
32.9789 | 1554811
32.9808 | 1596360.125
32.981 | 1608881.75
32.9811 | 1599079.875
32.9812 | 1575476.375
32.9912 | 1587722.125
32.992 | 1589456.25
32.9931 | 1564216.75
32.9933 | 1605876.625
32.9942 | 1607044.25
32.9944 | 1585684.75
32.9967 | 1607704.5
32.9976 | 1614408.125
32.9976 | 1627109.125
32.9983 | 1599828.25
32.9987 | 1561462.125
32.9989 | 1579681.125
33.0119 | 1576541.625
33.0126 | 1614419.25
33.0127 | 1653186.375
33.0128 | 1524896.125
33.0128 | 1552827.375
33.014 | 1544630.75
33.0145 | 1687948
33.0173 | 1615818.375
33.0184 | 1570802.375
33.0195 | 1563401.75
33.0197 | 1575152.5
33.0209 | 1591854.75
33.0212 | 1563103.875
33.0213 | 1564664.875
33.0214 | 1544431.625
33.0226 | 1527075.125
33.0229 | 1587816.75
33.0237 | 1523703.125
33.0241 | 1584444.125
33.0252 | 1567691
33.0261 | 1574545.5
33.0266 | 1632884.5
33.027 | 1583560.625
33.0273 | 1616188.5
33.0279 | 1596036
33.0294 | 1617195.125
33.0312 | 1612259
33.0378 | 1637402.75
33.0398 | 1629507.75
33.0403 | 1530738.625
33.0416 | 1621964.5
33.0417 | 1630414.625
33.0418 | 1594050.375
33.0436 | 1592210.5
33.0438 | 1594397.5
33.0452 | 1610401.5
33.046 | 1532543.875
33.048 | 1601108.375
33.0509 | 1578363.125
33.0521 | 1558478.5
33.0541 | 1560657.375
33.0556 | 1555875.5
33.0579 | 1580912.5
33.0582 | 1586668
33.0592 | 1562170.25
33.0617 | 1591748.25
33.0637 | 1612526.375
33.0658 | 1642785
33.0662 | 1620491.25
33.069 | 1537422.125
33.0698 | 1692271
33.0701 | 1626048.375
33.0708 | 1673017.625
33.0714 | 1576243.5
33.0726 | 1589239
33.0735 | 1565406.875
33.0748 | 1528698.125
33.0766 | 1569090.25
33.0782 | 1565026.125
33.0791 | 1640297.25
33.0814 | 1569645.5
33.0827 | 1564318.125
33.083 | 1678894.125
33.0845 | 1562338.375
33.0901 | 1603978.625
33.0928 | 1579837.5
33.0933 | 1605280.125
33.0951 | 1590910.375
33.0965 | 1559735.625
33.0978 | 1540646
33.0987 | 1564850.75
33.1009 | 1596541.625
33.1013 | 1607847
33.1018 | 1547136
33.1032 | 1558443.875
33.1042 | 1582835
33.1056 | 1531663.125
33.106 | 1619166.25
33.108 | 1658800.625
33.1084 | 1573493.375
33.1092 | 1601995.125
33.1096 | 1563277.625
33.1097 | 1612576.125
33.1153 | 1609797.5
33.1189 | 1615527.5
33.1195 | 1634048.625
33.1224 | 1586023.875
33.1237 | 1680101
33.124 | 1578338.25
33.1243 | 1613745.375
33.1246 | 1608120.5
33.1258 | 1556196.625
33.126 | 1592916.875
33.1261 | 1583519.375
33.128 | 1611877.125
33.1344 | 1558467
33.1348 | 1632173.875
33.1397 | 1572356
33.1399 | 1628224.375
33.1408 | 1625162
33.1409 | 1563581.875
33.1443 | 1641140.125
33.1456 | 1596263.75
33.147 | 1580179.125
33.1505 | 1609520.75
33.1506 | 1567731.625
33.1518 | 1645656.75
33.1518 | 1594503.5
33.1526 | 1625404.625
33.1531 | 1596461.75
33.1549 | 1631625.75
33.1558 | 1560481.625
33.1572 | 1562733.5
33.1596 | 1526861.75
33.1608 | 1582711.125
33.1615 | 1573698
33.1617 | 1590710.875
33.1646 | 1519419
33.1661 | 1616805.75
33.1662 | 1615097.625
33.1674 | 1592129.75
33.1686 | 1541551.25
33.1687 | 1586503.125
33.1693 | 1566339.125
33.1725 | 1639004.875
33.173 | 1627301.875
33.1732 | 1582156.875
33.1748 | 1569507.75
33.1754 | 1606840.375
33.1783 | 1613347.75
33.1798 | 1562848
33.1809 | 1535067.875
33.1814 | 1658754.75
33.1816 | 1555939.75
33.1817 | 1635151.125
33.1818 | 1578872.75
33.1831 | 1627310
33.1862 | 1606450.5
33.1865 | 1522041.5
33.1865 | 1635089.75
33.1865 | 1618131.625
33.1879 | 1615395
33.189 | 1584543.625
33.1894 | 1563620.875
33.1897 | 1605106
33.19 | 1594666.5
33.1903 | 1562795.25
33.1908 | 1536288
33.1912 | 1613584
33.1912 | 1551323.5
33.1913 | 1654328.75
33.1914 | 1579013.375
33.1924 | 1510368.25
33.1931 | 1615079.625
33.1932 | 1657733.875
33.1934 | 1541077.25
33.194 | 1681048.125
33.1949 | 1582867.75
33.1949 | 1567668.625
33.1982 | 1549056.125
33.1985 | 1630808.125
33.2018 | 1646411.5
33.2026 | 1645433.875
33.2038 | 1568170.375
33.2043 | 1605850.75
33.2052 | 1634003.375
33.2054 | 1578227.375
33.2062 | 1647315.625
33.2066 | 1605160.875
33.2106 | 1559811.375
33.2114 | 1647966.75
33.2126 | 1584550.125
33.213 | 1559539.375
33.2147 | 1650624.375
33.2155 | 1586831.25
33.2183 | 1507480.625
33.2193 | 1599076.5
33.2194 | 1523658.5
33.2195 | 1567373.625
33.2206 | 1549040.875
33.221 | 1556219.625
33.2223 | 1626581.75
33.2229 | 1562392.625
33.2233 | 1525085.75
33.2263 | 1545648.625
33.2263 | 1645921.375
33.2287 | 1584697.625
33.234 | 1555148.125
33.234 | 1567202.875
33.2343 | 1620414.5
33.2344 | 1575057.375
33.2348 | 1573930
33.2354 | 1558713.375
33.2377 | 1576114.625
33.2379 | 1550331.875
33.2381 | 1609167
33.2394 | 1651928.375
33.2396 | 1625060.75
33.2403 | 1550571.875
33.2407 | 1596642.375
33.244 | 1619594
33.2451 | 1550416
33.2452 | 1624245
33.2471 | 1545401.5
33.2486 | 1556844.5
33.2524 | 1682907.5
33.254 | 1615764.25
33.2546 | 1623035.375
33.2562 | 1614566.625
33.2569 | 1620038.5
33.2587 | 1586459.875
33.2588 | 1620880.875
33.26 | 1596744.75
33.2613 | 1612127
33.2621 | 1594612.5
33.2651 | 1557866.875
33.2651 | 1623207.5
33.267 | 1559273.25
33.2676 | 1656749.5
33.2737 | 1664477.625
33.2752 | 1600014
33.2756 | 1645662.625
33.279 | 1553397.25
33.28 | 1567794.5
33.2813 | 1638867.625
33.2827 | 1612097.875
33.284 | 1579358.25
33.2842 | 1601971.625
33.2845 | 1633056.5
33.2849 | 1602248.125
33.2871 | 1638484.75
33.2882 | 1616669.25
33.2888 | 1561244.375
33.2901 | 1613002.25
33.2917 | 1642946.25
33.2923 | 1554881.125
33.2923 | 1606767.875
33.2946 | 1552524.25
33.2968 | 1532653.75
33.2982 | 1528947.625
33.3024 | 1536920.875
33.304 | 1576445
33.3044 | 1572487.875
33.3077 | 1630784.5
33.3084 | 1642969.125
33.3107 | 1583458.5
33.3126 | 1640698.125
33.3141 | 1597733
33.3149 | 1519147.875
33.3182 | 1643893.25
33.3188 | 1586930.625
33.3205 | 1631182.375
33.3218 | 1599234.5
33.3228 | 1580092.125
33.3242 | 1594101.625
33.3254 | 1545822.375
33.3263 | 1578312.375
33.3273 | 1602352.75
33.3285 | 1541694.875
33.329 | 1606417.75
33.3323 | 1608402.625
33.3325 | 1628938.625
33.3338 | 1584755.125
33.3344 | 1607020.375
33.3418 | 1618345
33.3419 | 1593076
33.342 | 1577612.625
33.3429 | 1610198.75
33.3431 | 1600039.75
33.3454 | 1582930.5
33.3462 | 1557947.625
33.3476 | 1594553.5
33.3498 | 1527293
33.3507 | 1615891.125
33.3523 | 1578392.75
33.3571 | 1532698.625
33.3574 | 1558187.5
33.3617 | 1577446.25
33.364 | 1613943.5
33.3646 | 1589608.375
33.365 | 1615341.375
33.3652 | 1594780.625
33.3659 | 1563778
33.3666 | 1554951.875
33.3679 | 1580739.125
33.368 | 1582361.375
33.3688 | 1624444.875
33.3695 | 1588177.25
33.3705 | 1638600.5
33.3734 | 1513035.75
33.3736 | 1598301.625
33.376 | 1616440.875
33.3768 | 1605999
33.3779 | 1527037.25
33.3805 | 1623278.375
33.3812 | 1528203
33.3839 | 1553264.875
33.3853 | 1647720.5
33.388 | 1608661.75
33.3886 | 1572376.625
33.3894 | 1588524
33.3899 | 1584262.875
33.3915 | 1576492.75
33.3957 | 1561656.75
33.3958 | 1568904.25
33.396 | 1592524.625
33.3967 | 1591475.25
33.3981 | 1672715.25
33.3982 | 1619374.125
33.3984 | 1604614.25
33.3998 | 1616398
33.3999 | 1587007.875
33.4001 | 1647705.25
33.4007 | 1568461.25
33.4065 | 1591097.5
33.4087 | 1593465.5
33.4091 | 1595117.75
33.4094 | 1619701.25
33.4098 | 1547707
33.4115 | 1571893
33.4129 | 1603210.625
33.4133 | 1598324.125
33.4133 | 1623101.25
33.4145 | 1620753.125
33.4154 | 1602813.375
33.4165 | 1554845.625
33.4167 | 1645805
33.4195 | 1588118.25
33.4197 | 1639135.25
33.4198 | 1563107.625
33.4201 | 1556618.75
33.4204 | 1560431.375
33.4208 | 1630268.25
33.4214 | 1578249.875
33.4264 | 1574372.125
33.4266 | 1541478.125
33.4268 | 1560077.875
33.4284 | 1582932.75
33.4313 | 1560113.625
33.4328 | 1530919
33.4335 | 1623376.375
33.435 | 1582811
33.4356 | 1537252.25
33.4357 | 1673486.125
33.4375 | 1619846.125
33.4387 | 1550760.125
33.441 | 1588436.5
33.4422 | 1589814
33.4449 | 1643509.625
33.445 | 1605920.25
33.4457 | 1656311.625
33.447 | 1532675
33.4484 | 1563609.625
33.4496 | 1589047.75
33.4497 | 1530342.5
33.4507 | 1595670.125
33.4509 | 1638328.875
33.4515 | 1603692.625
33.4524 | 1559719.625
33.455 | 1629611.125
33.4586 | 1583224.875
33.4633 | 1580958.5
33.4637 | 1552215.5
33.4658 | 1599512.75
33.4664 | 1556143.875
33.4692 | 1617152.625
33.4705 | 1608705.875
33.4707 | 1569692
33.4747 | 1593026.75
33.475 | 1627112.875
33.4783 | 1585807
33.4787 | 1546723.375
33.4813 | 1552842.125
33.4821 | 1627109.75
33.4829 | 1605191.875
33.4848 | 1641602
33.4875 | 1622798
33.4876 | 1624416.25
33.488 | 1556260.625
33.4892 | 1588630.875
33.4895 | 1554095.5
33.4897 | 1662216.375
33.4936 | 1617933.25
33.4952 | 1578984.25
33.4957 | 1556092.625
33.4966 | 1593880.75
33.4971 | 1568000
33.4972 | 1617441.75
33.4975 | 1595077.875
33.4988 | 1589787.25
33.4997 | 1607104.875
33.5039 | 1601022.625
33.505 | 1635889.625
33.505 | 1599869.25
33.5053 | 1640076.5
33.509 | 1563688.875
33.5124 | 1586233.875
33.5126 | 1617728.625
33.514 | 1552452.125
33.5141 | 1535604
33.5147 | 1586782.5
33.5172 | 1539547
33.5172 | 1614431
33.5173 | 1639899.125
33.5177 | 1548107.75
33.5186 | 1575620.625
33.522 | 1618016.5
33.5237 | 1605983.5
33.5245 | 1558843
33.5256 | 1605439
33.5286 | 1589509.125
33.5289 | 1571005.375
33.5291 | 1601731.625
33.5292 | 1614222.125
33.5306 | 1615075.125
33.5345 | 1577371.125
33.5356 | 1638452.875
33.5374 | 1582397.25
33.5389 | 1592422.375
33.5412 | 1597546.25
33.5414 | 1633927.125
33.5415 | 1676175.375
33.542 | 1547671.375
33.5422 | 1593041.375
33.5452 | 1636366.375
33.5455 | 1526281.875
33.5459 | 1632061.125
33.5476 | 1553624.125
33.5478 | 1656639.125
33.5487 | 1632197.25
33.5495 | 1552294
33.5499 | 1631799.25
33.5522 | 1578883.875
33.5567 | 1552039.875
33.5582 | 1573748.75
33.5584 | 1618418.375
33.559 | 1617939.75
33.5611 | 1646014.625
33.5617 | 1605785.375
33.5624 | 1576979.625
33.5642 | 1661871.625
33.5661 | 1544149.125
33.5674 | 1569828.625
33.5688 | 1578593.875
33.5714 | 1540486.75
33.5724 | 1601495.25
33.5725 | 1605795.625
33.5738 | 1592588
33.5798 | 1620893.125
33.5837 | 1569592.125
33.5839 | 1512137.375
33.584 | 1563508.375
33.5861 | 1614549.375
33.5896 | 1598647.5
33.59 | 1568316.375
33.5904 | 1614596.625
33.5917 | 1615630.5
33.5926 | 1538426.375
33.5946 | 1617181.75
33.5969 | 1617774
33.6004 | 1663976.125
33.6033 | 1561257.875
33.6038 | 1603716.75
33.6045 | 1613842.375
33.6053 | 1577145.75
33.6104 | 1574286.875
33.611 | 1587380.5
33.6145 | 1676386.75
33.618 | 1568998
33.6201 | 1597450.125
33.6207 | 1633582.5
33.6228 | 1578838.75
33.6235 | 1603334.5
33.6258 | 1607315.625
33.6265 | 1647073.875
33.6288 | 1623433.25
33.6294 | 1578810.25
33.6306 | 1577254.125
33.632 | 1589862.5
33.6335 | 1570323.625
33.6341 | 1591692.875
33.635 | 1533908
33.6356 | 1527951
33.6356 | 1579445.625
33.6362 | 1571550.125
33.6362 | 1581582.5
33.6367 | 1590928
33.6391 | 1656539.625
33.6403 | 1598643.125
33.6416 | 1516391.5
33.6431 | 1669758.875
33.645 | 1559831.5
33.646 | 1573757
33.646 | 1603347.125
33.6488 | 1609461.375
33.6491 | 1582908
33.6494 | 1593620.75
33.6502 | 1595418.75
33.6523 | 1547483.25
33.6551 | 1618299
33.6562 | 1691660.375
33.6564 | 1588085
33.6575 | 1622617.125
33.6577 | 1642219.875
33.6601 | 1698094.5
33.6626 | 1616412.625
33.6657 | 1603325.625
33.6683 | 1629776
33.67 | 1670175.875
33.6713 | 1554880.625
33.6727 | 1559823.375
33.6747 | 1620090
33.677 | 1507424.875
33.6798 | 1607485.625
33.6801 | 1593638.625
33.6812 | 1597339.625
33.6824 | 1607561.125
33.6835 | 1654928.875
33.6861 | 1602522.25
33.6867 | 1549163.875
33.6871 | 1610712.625
33.6939 | 1605919.75
33.6946 | 1602389.125
33.6976 | 1683278.375
33.6989 | 1654369.625
33.6991 | 1563786.25
33.6995 | 1586466.75
33.6997 | 1540954
33.7005 | 1571351.875
33.7008 | 1664209.625
33.704 | 1621141.125
33.7092 | 1608466.625
33.7123 | 1562839.5
33.7126 | 1599117.5
33.7138 | 1576928.25
33.7144 | 1630324
33.7148 | 1571888.875
33.7151 | 1594467.25
33.7177 | 1609787.375
33.7181 | 1603512.125
33.7207 | 1598248.125
33.7209 | 1565012
33.7218 | 1555925.5
33.7228 | 1580473.375
33.7236 | 1632972
33.725 | 1558426.5
33.7255 | 1618206.875
33.7263 | 1601443.375
33.7267 | 1604113.875
33.7283 | 1604268.75
33.7348 | 1603946.875
33.7357 | 1629531
33.7364 | 1582529.125
33.7376 | 1627488.75
33.7377 | 1576678.25
33.7392 | 1618178.125
33.7395 | 1565033.5
33.7397 | 1633603.375
33.7398 | 1614695
33.74 | 1615863.125
33.7404 | 1576607.75
33.7409 | 1587216.375
33.7411 | 1587242.25
33.7436 | 1567716
33.7465 | 1584650.5
33.7478 | 1595800.5
33.7482 | 1652961.125
33.7499 | 1611040.125
33.7505 | 1594685.875
33.7512 | 1636661.25
33.7516 | 1547811.375
33.7544 | 1561489.375
33.7546 | 1662736.25
33.7553 | 1607583.75
33.7571 | 1637651.375
33.758 | 1583653.875
33.7584 | 1616098.125
33.76 | 1579574.25
33.7619 | 1584742.75
33.7649 | 1556462.375
33.7661 | 1579958.125
33.7662 | 1616987.25
33.7682 | 1581339.25
33.7683 | 1572154
33.7721 | 1611727.875
33.7734 | 1610886.5
33.7748 | 1550158.625
33.7776 | 1597305.625
33.7785 | 1595313.625
33.7787 | 1519898.875
33.7787 | 1623213.125
33.7796 | 1595788.875
33.7801 | 1620975
33.7855 | 1626194.625
33.7865 | 1611143.125
33.7871 | 1540652.125
33.7873 | 1606165.125
33.7874 | 1542827.5
33.7882 | 1648824.25
33.7893 | 1550699.25
33.7896 | 1564329.75
33.7913 | 1634400
33.7914 | 1632927.625
33.7928 | 1659548.125
33.7961 | 1591915.75
33.7962 | 1615171.375
33.7971 | 1612699.625
33.7973 | 1590780.875
33.7976 | 1548089.625
33.8008 | 1533825.25
33.8015 | 1553121.25
33.8058 | 1592931.625
33.8104 | 1661290.125
33.8131 | 1597136.25
33.8145 | 1593750.75
33.8153 | 1599884.375
33.8158 | 1543794
33.8174 | 1568483.25
33.8209 | 1659237.625
33.8212 | 1594030
33.8215 | 1566980.625
33.8216 | 1664060
33.8224 | 1626126.125
33.8228 | 1585963.375
33.8257 | 1600595.25
33.8277 | 1657135.125
33.8325 | 1513889.875
33.8342 | 1575292.25
33.8359 | 1571301
33.8372 | 1626869.625
33.8395 | 1518386.75
33.8414 | 1576090.75
33.8424 | 1601297.25
33.8453 | 1561325.625
33.8486 | 1588272.25
33.8504 | 1558914.25
33.851 | 1627657.875
33.8528 | 1582947.75
33.8547 | 1600929.5
33.8587 | 1597497.125
33.8589 | 1636772
33.8592 | 1598141.25
33.8605 | 1573471.5
33.8666 | 1676184.875
33.8673 | 1603983.5
33.8679 | 1613157.875
33.8681 | 1616006.625
33.8686 | 1625306.25
33.869 | 1560955.375
33.8694 | 1573358.25
33.8695 | 1550851.125
33.8718 | 1640605.5
33.8739 | 1680951.125
33.8741 | 1605663.125
33.8756 | 1594480.875
33.8809 | 1501598.625
33.8816 | 1561858.125
33.883 | 1599684.875
33.8842 | 1646501.375
33.8848 | 1608658.125
33.8874 | 1588953.75
33.8881 | 1626655.5
33.8894 | 1602669.75
33.8901 | 1633076
33.8906 | 1560807.375
33.8918 | 1598020.5
33.8919 | 1605180.5
33.8923 | 1549580
33.893 | 1581305.5
33.8937 | 1626352.5
33.8968 | 1518293.25
33.9001 | 1581756.125
33.9012 | 1559797.875
33.9038 | 1590378.125
33.904 | 1592472.125
33.9064 | 1600177.125
33.9066 | 1632337
33.912 | 1585830.125
33.9127 | 1620481.5
33.9129 | 1625977.25
33.9146 | 1574296.125
33.9152 | 1643035.75
33.9155 | 1637608
33.9168 | 1599101.25
33.9172 | 1605460.5
33.9202 | 1643445.875
33.9213 | 1555462
33.9253 | 1572231.375
33.9255 | 1570251.125
33.9296 | 1615440.75
33.9371 | 1626518.5
33.9377 | 1592303.75
33.9381 | 1568254.5
33.939 | 1640358.75
33.9436 | 1539599.875
33.9437 | 1612341.25
33.9477 | 1545497.875
33.9503 | 1614981.375
33.9565 | 1560695
33.9574 | 1626984.75
33.9574 | 1641993.875
33.9582 | 1583602.5
33.9601 | 1616177.875
33.9604 | 1576578
33.9608 | 1606892.625
33.9634 | 1589564.125
33.9649 | 1613021.875
33.9667 | 1563553.625
33.9671 | 1604571.875
33.9699 | 1627109.375
33.9728 | 1551399.25
33.9732 | 1539864.5
33.9792 | 1562175.875
33.9813 | 1539401.75
33.9814 | 1628856.125
33.9834 | 1653725.375
33.9846 | 1601871.75
33.985 | 1557550.5
33.9852 | 1602085.875
33.9875 | 1588730.25
33.9918 | 1535974.875
33.9933 | 1593025.375
33.9954 | 1669958.625
33.9963 | 1637692.125
33.9978 | 1535469.125
33.9997 | 1600708.75
34.0017 | 1634425.75
34.0031 | 1640778.875
34.0034 | 1538275.375
34.0043 | 1604240
34.0052 | 1550408.5
34.0064 | 1587251.875
34.0123 | 1592448
34.0124 | 1702639.75
34.0126 | 1592201
34.0151 | 1512512.75
34.0182 | 1540917.625
34.0212 | 1545254.75
34.0222 | 1531821.75
34.0256 | 1570989.125
34.0286 | 1629646.25
34.0307 | 1554566.625
34.0337 | 1625681.75
34.0348 | 1539611.625
34.0379 | 1618953.875
34.0379 | 1637922
34.0398 | 1687490
34.041 | 1616183.125
34.0421 | 1532333.75
34.0438 | 1568975.875
34.0491 | 1607098.75
34.0502 | 1554426.125
34.0529 | 1569238.375
34.0543 | 1609535.375
34.059 | 1560702.375
34.0595 | 1605637.625
34.0604 | 1521243.125
34.0618 | 1606700.5
34.0626 | 1588011.75
34.0635 | 1576758.25
34.0644 | 1626503.5
34.0697 | 1572584.125
34.0712 | 1557064.625
34.0723 | 1616967.75
34.079 | 1608865.375
34.0804 | 1637113.875
34.0817 | 1568141.125
34.084 | 1592728.125
34.0855 | 1598801.5
34.0897 | 1660397.5
34.0897 | 1616150.5
34.0923 | 1550967.875
34.0931 | 1658138.875
34.0948 | 1550383.625
34.0966 | 1614155.125
34.0969 | 1583767.375
34.0973 | 1578387.625
34.1003 | 1629055.75
34.1045 | 1627845.125
34.1045 | 1554819.875
34.1074 | 1631323.75
34.1075 | 1588887.25
34.1097 | 1611399.75
34.1148 | 1656668.625
34.1152 | 1596422.125
34.1162 | 1628410.875
34.1169 | 1578547.375
34.1197 | 1597089.75
34.1217 | 1592970.875
34.1232 | 1533176.875
34.1234 | 1658645.25
34.1261 | 1566350.625
34.1273 | 1576989
34.1287 | 1671034.5
34.1289 | 1625606.75
34.131 | 1555606.5
34.1316 | 1612967.375
34.1322 | 1594828.125
34.1326 | 1544188.625
34.1327 | 1629051.125
34.1331 | 1671812.5
34.1378 | 1550087.875
34.1396 | 1683310.25
34.1398 | 1578845.5
34.1497 | 1560072.625
34.1554 | 1681313.875
34.1554 | 1644945
34.1594 | 1600134
34.161 | 1585420.375
34.1672 | 1584164.25
34.1732 | 1654247.375
34.1749 | 1605694.375
34.1751 | 1566409.375
34.1776 | 1580774.875
34.1796 | 1637665
34.1827 | 1626842.375
34.1843 | 1568396.5
34.1851 | 1643152.125
34.194 | 1624122.5
34.1946 | 1587114.375
34.1946 | 1583624.75
34.1948 | 1580698.75
34.1951 | 1607212
34.1955 | 1555774.875
34.1988 | 1664627.625
34.2004 | 1613297
34.2011 | 1656123.625
34.2011 | 1621031.5
34.2071 | 1635728.125
34.2078 | 1594314.625
34.2085 | 1592526.875
34.2086 | 1607752.25
34.2108 | 1605889.75
34.2111 | 1610758
34.2136 | 1559649.5
34.2185 | 1576349.625
34.2192 | 1633970
34.2222 | 1603706.375
34.2241 | 1597099.375
34.2249 | 1605166.625
34.225 | 1595332.75
34.2277 | 1591764.5
34.2316 | 1581624.125
34.2327 | 1576160.5
34.2343 | 1630994.875
34.2343 | 1593977.75
34.2351 | 1524516.75
34.2352 | 1567336.75
34.2362 | 1604691
34.2373 | 1627514.625
34.2374 | 1565102.375
34.2376 | 1586362.125
34.2382 | 1597571.375
34.2391 | 1628976.375
34.2406 | 1624077.375
34.2409 | 1567123.875
34.2413 | 1687488.75
34.2418 | 1552210.5
34.2419 | 1636710.625
34.2428 | 1603214.125
34.245 | 1637332.75
34.2456 | 1615296.75
34.2525 | 1630744.625
34.2544 | 1542235.875
34.2554 | 1602286.125
34.2563 | 1590635.875
34.2575 | 1580552
34.2674 | 1602137.375
34.27 | 1584052
34.2706 | 1647034.375
34.2743 | 1632572.25
34.2759 | 1604058.875
34.2774 | 1568767.625
34.2782 | 1581444.625
34.279 | 1622496.625
34.2792 | 1546543
34.2801 | 1562593.875
34.281 | 1571548.75
34.2815 | 1571440.875
34.2817 | 1621921.5
34.2827 | 1567706.875
34.2885 | 1575162.875
34.2902 | 1675090.75
34.2921 | 1635972.625
34.2941 | 1555746.875
34.2969 | 1578328.625
34.31 | 1609997.25
34.3117 | 1607966
34.3117 | 1637515.125
34.312 | 1584147.75
34.3135 | 1589638.125
34.3139 | 1560966.75
34.3168 | 1593090.25
34.3174 | 1599169.625
34.3176 | 1611341
34.3205 | 1582637.5
34.3222 | 1602954.125
34.3249 | 1591373.5
34.3255 | 1591756.375
34.3264 | 1598266.5
34.3266 | 1645563.25
34.3282 | 1548184.25
34.3306 | 1527755
34.331 | 1567021.25
34.3315 | 1599094.25
34.3339 | 1597119.375
34.335 | 1613663.5
34.3429 | 1637485.375
34.3442 | 1644181
34.3464 | 1633156.5
34.3473 | 1670687.375
34.3493 | 1600415.25
34.3496 | 1616449.25
34.3498 | 1598497.5
34.3499 | 1626064.375
34.3501 | 1599505
34.3502 | 1577551.875
34.3515 | 1619761.75
34.3524 | 1580450.25
34.3545 | 1662752.125
34.3545 | 1636469.125
34.3564 | 1583013.5
34.3571 | 1594396.375
34.3611 | 1588334.25
34.3618 | 1559999.125
34.3618 | 1583413.375
34.3654 | 1592315.25
34.3681 | 1573743.75
34.3703 | 1618017.5
34.3707 | 1525665.375
34.371 | 1547583.25
34.3717 | 1633027.625
34.3741 | 1588497.625
34.3761 | 1648738.375
34.3762 | 1585260
34.3779 | 1619883
34.3795 | 1578323.125
34.3797 | 1572276.875
34.3798 | 1588599.375
34.3809 | 1603996.5
34.3809 | 1562184.625
34.3812 | 1557903.125
34.383 | 1532398.875
34.3835 | 1585888.625
34.3851 | 1560127
34.3861 | 1631503.75
34.3862 | 1670529.625
34.3869 | 1561802.75
34.3872 | 1573635.375
34.3901 | 1592175
34.3928 | 1626068.75
34.3936 | 1545682.25
34.395 | 1646064.75
34.396 | 1643693.75
34.3966 | 1566910.875
34.3968 | 1570969.75
34.4 | 1564110.5
34.403 | 1578830.125
34.4048 | 1663446.5
34.4057 | 1521192.25
34.4067 | 1573338
34.4073 | 1629777.125
34.4102 | 1618705.5
34.4106 | 1608417.625
34.4132 | 1572181
34.4134 | 1571197.375
34.4137 | 1603609.875
34.4173 | 1617201.25
34.4184 | 1632069
34.4191 | 1556394.125
34.4205 | 1604860.125
34.4206 | 1575717.375
34.4219 | 1668873.5
34.423 | 1596437.125
34.4246 | 1566162.75
34.4255 | 1628357.125
34.4303 | 1635216.5
34.4308 | 1699838.75
34.4311 | 1647614.625
34.4319 | 1621255.625
34.4324 | 1612432.625
34.4329 | 1608227.25
34.4345 | 1582474.875
34.4359 | 1579002.375
34.4387 | 1562977.625
34.439 | 1584287
34.439 | 1638723.75
34.4401 | 1673721.25
34.4435 | 1566866.25
34.4465 | 1562205.875
34.4476 | 1593693
34.4485 | 1567438.5
34.4497 | 1678519.5
34.4509 | 1546838.125
34.4523 | 1638428.375
34.4529 | 1573185.875
34.4536 | 1584517.5
34.4547 | 1623885.25
34.455 | 1523007.875
34.4636 | 1611989.875
34.4665 | 1647531.625
34.4725 | 1613656.5
34.4749 | 1633322.25
34.477 | 1627271
34.479 | 1546550.125
34.4802 | 1575609.75
34.481 | 1627410.875
34.4819 | 1685268.375
34.4858 | 1639670.125
34.4871 | 1614533.625
34.4899 | 1570773.25
34.4905 | 1614776.75
34.4909 | 1657495.25
34.4926 | 1574126.125
34.4942 | 1590139.625
34.4991 | 1550497.375
34.5014 | 1580226
34.5027 | 1626964.375
34.5047 | 1673000.375
34.5052 | 1628867.75
34.5056 | 1572781.625
34.5091 | 1531017.625
34.5094 | 1564929.75
34.51 | 1660558.375
34.5135 | 1575594.5
34.514 | 1582718.25
34.5142 | 1600118.625
34.5147 | 1564209.5
34.5192 | 1668944.625
34.5226 | 1570811.125
34.5277 | 1650725.5
34.5281 | 1662897.625
34.5346 | 1542053.25
34.5349 | 1573010.625
34.5394 | 1606705.875
34.5396 | 1618015.75
34.5411 | 1591085.25
34.5419 | 1552401
34.5451 | 1665998.875
34.5464 | 1597465.75
34.5481 | 1536045.5
34.5496 | 1585742.5
34.5525 | 1649392.25
34.5547 | 1586329.875
34.5589 | 1551031.25
34.5626 | 1543859.5
34.5634 | 1599524.875
34.5641 | 1637121
34.566 | 1603168.375
34.5673 | 1598069.25
34.578 | 1527886.375
34.5815 | 1536824.875
34.5882 | 1629407.75
34.5898 | 1600441.875
34.5904 | 1582597.125
34.593 | 1607393.625
34.5943 | 1560670.25
34.5966 | 1612393.875
34.5977 | 1652988.375
34.6002 | 1575506
34.6028 | 1561653.75
34.6066 | 1613152.375
34.6083 | 1605380.5
34.6132 | 1603374.375
34.6138 | 1619398.5
34.6254 | 1584168.375
34.631 | 1638098
34.6335 | 1558591.5
34.6336 | 1621209.5
34.6344 | 1551125.375
34.6372 | 1600475.625
34.6384 | 1625536.25
34.6394 | 1671433
34.6427 | 1608926.625
34.6447 | 1657723
34.6472 | 1613907.125
34.6493 | 1620036.875
34.6517 | 1584371
34.6525 | 1625963.125
34.6602 | 1580752.5
34.6613 | 1553137.125
34.6628 | 1535481
34.6629 | 1540730.5
34.6655 | 1553150.5
34.6658 | 1701531.875
34.6659 | 1548527.625
34.669 | 1576324.25
34.6699 | 1613528.125
34.6727 | 1643445.625
34.6729 | 1596377.875
34.673 | 1610706.5
34.6733 | 1612839
34.6739 | 1583185.25
34.6809 | 1565196.875
34.6852 | 1628714
34.6879 | 1611836.75
34.696 | 1604892.125
34.6963 | 1521396.625
34.697 | 1614698.375
34.6983 | 1595779.75
34.6996 | 1560684.375
34.7029 | 1550843.25
34.7052 | 1646884.125
34.7064 | 1588769.5
34.7088 | 1561728.25
34.7099 | 1608100.75
34.7167 | 1655885.5
34.7186 | 1529312.25
34.721 | 1640704.25
34.7215 | 1611905.375
34.7215 | 1578271.375
34.7231 | 1590371.375
34.727 | 1551645.125
34.7291 | 1616041.375
34.7322 | 1601176.875
34.7325 | 1580324.375
34.7326 | 1620768.625
34.7328 | 1634290.875
34.736 | 1655431.375
34.7377 | 1606691
34.7402 | 1603914
34.7429 | 1638702.5
34.7455 | 1564438.75
34.755 | 1543001.5
34.7592 | 1650184.75
34.761 | 1625854.75
34.7617 | 1587354.5
34.7628 | 1635671.625
34.7635 | 1567049.125
34.7652 | 1576914.375
34.7718 | 1594587.375
34.7752 | 1560239.5
34.7768 | 1585592.5
34.7774 | 1568612.875
34.7873 | 1576410.25
34.7897 | 1596210.375
34.795 | 1638384.875
34.7995 | 1575478.75
34.8017 | 1588554.125
34.8051 | 1618845.875
34.8143 | 1557995.375
34.8156 | 1643168.375
34.8184 | 1602359
34.8195 | 1582454.5
34.8213 | 1571628.875
34.8217 | 1567541.375
34.8221 | 1601290.625
34.823 | 1598393.5
34.8282 | 1701565.75
34.8288 | 1645005.125
34.833 | 1658744
34.838 | 1573903.5
34.8409 | 1598604.125
34.8473 | 1610828.75
34.8476 | 1600059.625
34.8638 | 1561785.125
34.8642 | 1610015.125
34.8657 | 1615264.125
34.8667 | 1593001.75
34.8688 | 1624334.875
34.8694 | 1611782.25
34.8744 | 1586495.125
34.8761 | 1595542.625
34.8768 | 1618750.375
34.8875 | 1643234.25
34.8904 | 1577393.25
34.8968 | 1595201.625
34.8981 | 1540622.375
34.8997 | 1596717.5
34.904 | 1637878.75
34.9062 | 1634656.375
34.9075 | 1618490.625
34.9077 | 1604342.75
34.9109 | 1631466.875
34.9123 | 1554918.5
34.9125 | 1608720.375
34.9129 | 1629366.5
34.923 | 1637943.25
34.9235 | 1606519.625
34.9252 | 1585260.5
34.9266 | 1536121
34.9327 | 1604776.125
34.9358 | 1552925.875
34.9369 | 1599525
34.9401 | 1598456.375
34.9402 | 1619815.125
34.9405 | 1608807.5
34.9408 | 1599719.75
34.9436 | 1695177.625
34.9467 | 1658248
34.9468 | 1540173.375
34.9499 | 1635998.375
34.951 | 1624514.875
34.9538 | 1607052.75
34.9539 | 1635611.375
34.9542 | 1611230.875
34.9561 | 1619262.375
34.9566 | 1647390.625
34.9566 | 1601923.375
34.9569 | 1538563.625
34.9577 | 1640768.5
34.9583 | 1651078.5
34.9587 | 1629072.5
34.9594 | 1612224.375
34.9618 | 1610132.875
34.9642 | 1560580.875
34.9648 | 1586870.625
34.9657 | 1531150.875
34.9667 | 1599404.5
34.9669 | 1615979.375
34.9694 | 1659483.5
34.9709 | 1630152.375
34.9716 | 1698293
34.9776 | 1571512.5
34.9778 | 1614636.875
34.9813 | 1536947
34.9841 | 1678710.875
34.9896 | 1574008.125
34.9957 | 1670892.25
35.0044 | 1629912.25
35.0051 | 1602250
35.0062 | 1605427.125
35.0135 | 1603426.5
35.0142 | 1618232.875
35.0147 | 1582265.125
35.0149 | 1619264.25
35.0155 | 1670349.875
35.0169 | 1643384.25
35.0308 | 1609294.875
35.032 | 1556787.875
35.0335 | 1649781
35.0336 | 1609677.375
35.0373 | 1685755.5
35.0414 | 1630113
35.0419 | 1650331.625
35.0441 | 1614694.875
35.0442 | 1577916.125
35.0541 | 1664597.75
35.055 | 1614982.125
35.055 | 1578572
35.0562 | 1631458.25
35.0611 | 1626766
35.0654 | 1666150.125
35.0655 | 1605501.25
35.0675 | 1702312.125
35.0746 | 1613833.875
35.075 | 1600702.375
35.0761 | 1629654.25
35.077 | 1715556.875
35.0772 | 1621025.25
35.0776 | 1613960.125
35.0781 | 1651806
35.0782 | 1615169
35.0843 | 1615096.125
35.0868 | 1582763.625
35.0901 | 1695220.75
35.0903 | 1680478.875
35.0939 | 1583319.25
35.1007 | 1626241
35.1011 | 1615283.25
35.1022 | 1596726.125
35.1022 | 1645611.875
35.1084 | 1613346.625
35.109 | 1655963.375
35.1101 | 1558478.25
35.1133 | 1664093.75
35.1145 | 1599430.875
35.1148 | 1591686.375
35.1163 | 1712223.5
35.1174 | 1678634.5
35.1283 | 1573406.875
35.1298 | 1608448.625
35.1305 | 1613649.75
35.1327 | 1623148.75
35.1346 | 1572165.625
35.1347 | 1675564.125
35.1356 | 1645349
35.1371 | 1716785.25
35.1385 | 1655802.625
35.1417 | 1584423.375
35.1431 | 1642959.25
35.1442 | 1673853.125
35.1446 | 1675336.75
35.1446 | 1668960.75
35.1459 | 1651837.5
35.1471 | 1668413.5
35.1498 | 1639567.125
35.1505 | 1652807.125
35.1561 | 1562394.375
35.1623 | 1593641.5
35.164 | 1667148.875
35.1664 | 1635489.875
35.1665 | 1616167.75
35.1675 | 1569195.625
35.1691 | 1690799.875
35.1701 | 1654395.875
35.1707 | 1636789.625
35.1724 | 1572289.5
35.1732 | 1608993.125
35.1744 | 1633472.375
35.1827 | 1646830.625
35.1852 | 1647631
35.1862 | 1674098.625
35.1866 | 1574735.25
35.1907 | 1581970.625
35.1932 | 1589101.375
35.1978 | 1593776.5
35.2068 | 1697944.75
35.2151 | 1603793.25
35.2184 | 1561808.375
35.2213 | 1628522.625
35.2271 | 1668225
35.2273 | 1618582.75
35.2298 | 1687662
35.2347 | 1614794.25
35.2354 | 1601091.75
35.2365 | 1601960.875
35.2389 | 1666270
35.239 | 1605970.875
35.2418 | 1649044.625
35.2541 | 1620254.75
35.2579 | 1655144.5
35.2592 | 1629834
35.2639 | 1664242.5
35.2729 | 1603919.5
35.2761 | 1603793
35.2807 | 1743011.875
35.2811 | 1609060.25
35.2814 | 1593596.375
35.2939 | 1644841.5
35.294 | 1637212.375
35.2995 | 1658843.625
35.3072 | 1594343.375
35.3081 | 1689322.875
35.309 | 1666437.75
35.3096 | 1608550.875
35.3113 | 1691563.375
35.3122 | 1647476.625
35.3144 | 1639360.125
35.3151 | 1598722.75
35.3172 | 1637573.875
35.3183 | 1580336.25
35.3197 | 1604537.5
35.3303 | 1626787.625
35.3338 | 1609263.125
35.3349 | 1597070.375
35.3355 | 1618154
35.3382 | 1641759
35.3433 | 1627807.375
35.3454 | 1660787.125
35.3568 | 1597394.125
35.3577 | 1609448.375
35.3601 | 1610742.875
35.3601 | 1595357
35.3653 | 1678316.125
35.3654 | 1643274.5
35.3683 | 1627835.75
35.3696 | 1648773.125
35.3698 | 1621567.375
35.3799 | 1633087.75
35.3816 | 1628904.25
35.3816 | 1720083.75
35.3854 | 1581780.125
35.3863 | 1613731.125
35.3905 | 1600289.875
35.393 | 1693713.125
35.4041 | 1683253.25
35.4106 | 1578917
35.4127 | 1612767.375
35.413 | 1625437.125
35.4133 | 1640534.5
35.4259 | 1575648.375
35.4365 | 1659960.75
35.4384 | 1638903.875
35.4405 | 1643784.875
35.4468 | 1665484.625
35.4489 | 1624295.5
35.4528 | 1614431.125
35.4533 | 1585351.5
35.4538 | 1620666.875
35.454 | 1652699.125
35.4541 | 1692592.125
35.455 | 1582008.5
35.4607 | 1657703.625
35.4724 | 1596893.375
35.4783 | 1583586.25
35.4805 | 1674908.875
35.4816 | 1664795.875
35.4987 | 1602346.25
35.4988 | 1585290.125
35.5035 | 1616939.25
35.5038 | 1618550.625
35.5064 | 1583326
35.5069 | 1632334.375
35.512 | 1625146.25
35.5196 | 1593813.875
35.5231 | 1666112.625
35.5246 | 1640083.75
35.5332 | 1617585.375
35.5361 | 1622865.875
35.5461 | 1643595.5
35.5628 | 1618139.75
35.5638 | 1722079.25
35.5639 | 1610204.875
35.5649 | 1689026.875
35.5702 | 1648903
35.581 | 1649651.75
35.5822 | 1615781.75
35.5874 | 1596881.75
35.5931 | 1631681.625
35.5964 | 1659256.75
35.5998 | 1621626.625
35.6016 | 1640803.75
35.6044 | 1656309.5
35.6058 | 1671552.875
35.6064 | 1592024.625
35.6079 | 1690367.375
35.6104 | 1678449.375
35.6123 | 1597384.25
35.6209 | 1624947.75
35.6267 | 1632584.75
35.6267 | 1647007.125
35.6314 | 1673734.125
35.6464 | 1575062.875
35.6599 | 1625508.75
35.668 | 1598698.25
35.6712 | 1656163.625
35.6818 | 1579930.125
35.682 | 1617244.25
35.6826 | 1644398.5
35.6833 | 1685607.125
35.6908 | 1579650.875
35.6909 | 1586619.5
35.6924 | 1579806.625
35.7049 | 1652223.25
35.7102 | 1632259.25
35.7113 | 1648798.625
35.7205 | 1621394.625
35.7274 | 1624540.625
35.7287 | 1610689.125
35.7326 | 1561512.75
35.7336 | 1670755.25
35.7358 | 1646126.75
35.7531 | 1680311
35.7532 | 1661793.25
35.7568 | 1688885.125
35.7666 | 1665639.75
35.7693 | 1612115.25
35.7711 | 1695099.875
35.7749 | 1649332.125
35.7805 | 1594806.5
35.7968 | 1654415.25
35.7974 | 1622866.5
35.8077 | 1625809.125
35.8128 | 1652074.875
35.8221 | 1632637.75
35.8238 | 1669188.375
35.8242 | 1655967.875
35.8256 | 1677051
35.8268 | 1572179.75
35.832 | 1586017.25
35.842 | 1639378.875
35.8458 | 1603608.5
35.8601 | 1597301.375
35.8617 | 1631534.5
35.8633 | 1619369.5
35.8737 | 1682178.375
35.8758 | 1674565.375
35.8762 | 1541971.25
35.8766 | 1584541.25
35.8774 | 1589506.25
35.886 | 1658152.625
35.9016 | 1673070.625
35.91 | 1689188.625
35.9139 | 1641438.75
35.9151 | 1595508.375
35.9157 | 1622859.5
35.9212 | 1645340.25
35.9406 | 1676828.25
35.9423 | 1580515.375
35.9473 | 1675823.625
35.9486 | 1598815.75
35.9516 | 1622419.25
35.9542 | 1677900.875
35.9557 | 1677128.75
35.9579 | 1607101
35.96 | 1662693.375
35.974 | 1641543.625
35.9847 | 1647286
35.9974 | 1735541.75
36.0023 | 1706402.125
36.0156 | 1661423.5
36.0165 | 1656198
36.0217 | 1596229
36.0226 | 1650396.5
36.0271 | 1683919.625
36.0274 | 1601741.5
36.033 | 1689450.875
36.0427 | 1687117.375
36.048 | 1743010.625
36.0537 | 1603839.875
36.0631 | 1707100.625
36.0651 | 1649997.25
36.0779 | 1714609.875
36.0867 | 1679190.375
36.0971 | 1606920.875
36.1011 | 1638039.25
36.1021 | 1590450
36.1065 | 1717569
36.1086 | 1698166.625
36.1127 | 1671463.125
36.1142 | 1715666
36.1158 | 1684308.375
36.1168 | 1606262.125
36.1306 | 1701937.5
36.1549 | 1662205
36.1586 | 1695692.875
36.1619 | 1584925.375
36.1792 | 1639588.5
36.193 | 1652512
36.193 | 1624245.125
36.1972 | 1647335.5
36.2128 | 1709869.125
36.2143 | 1686629.25
36.2355 | 1669614.625
36.2433 | 1630570.625
36.2505 | 1660800.25
36.2567 | 1618198.5
36.2598 | 1674832.875
36.2629 | 1673511.5
36.2652 | 1658722.625
36.2653 | 1652040.75
36.2655 | 1660451.25
36.2658 | 1639642.625
36.2671 | 1633056.5
36.2781 | 1628619.875
36.2891 | 1695723.5
36.3041 | 1611124.625
36.3088 | 1699812.625
36.3123 | 1585508.125
36.3204 | 1647105.125
36.331 | 1663627.125
36.3328 | 1645117.875
36.3562 | 1694961
36.362 | 1695037.625
36.3705 | 1684793.5
36.3828 | 1679280.375
36.406 | 1680443
36.4128 | 1702160.875
36.4168 | 1707293
36.422 | 1587810.5
36.4266 | 1573601.75
36.462 | 1714211.875
36.4651 | 1675221.625
36.4725 | 1637891.75
36.5091 | 1673210.125
36.51 | 1705521.5
36.5146 | 1635242.25
36.5248 | 1658221.75
36.582 | 1683696
36.5897 | 1668936.625
36.6072 | 1670298
36.6161 | 1650149.75
36.6182 | 1697982.25
36.6199 | 1653601.5
36.6325 | 1638590.375
36.6541 | 1648285
36.6651 | 1711544.625
36.6743 | 1707052.125
36.6928 | 1652246.875
36.6963 | 1604083.75
36.7092 | 1613119.625
36.7179 | 1679994
36.7231 | 1706243.875
36.7364 | 1644614.5
36.7544 | 1675772.875
36.7658 | 1636187.625
36.7898 | 1727321.375
36.8343 | 1666498.375
36.849 | 1690751.625
36.8531 | 1676749.75
36.8541 | 1629669.25
36.861 | 1699470.625
36.8967 | 1693415.125
36.9229 | 1665334.25
36.9237 | 1623976.75
36.9265 | 1639251.125
36.9372 | 1643750.75
36.9506 | 1650840.25
36.9538 | 1626390.25
36.9747 | 1692455.125
36.9915 | 1792867
37.0089 | 1699377.875
37.0092 | 1722192.875
37.0303 | 1677242.625
37.0326 | 1649312
37.0985 | 1701083.875
37.1006 | 1723636.75
37.1188 | 1742836.25
37.1441 | 1637855.75
37.1522 | 1696857.5
37.1579 | 1691904.75
37.1634 | 1657116.625
37.1753 | 1722004.75
37.1827 | 1645797.5
37.2532 | 1652865
37.2976 | 1655500.625
37.3044 | 1686374.125
37.3121 | 1687058.625
37.3462 | 1725823
37.3563 | 1721644.625
37.3784 | 1717817.875
37.4593 | 1643442.625
37.4674 | 1653585.25
37.5872 | 1737870.375
37.6224 | 1671252.125
37.6264 | 1697938.375
37.6951 | 1726402.875
37.6981 | 1702458.625
37.7379 | 1740778.25
37.7766 | 1675281.125
37.887 | 1684531.625
37.9777 | 1788643.125
37.989 | 1666073
39.0319 | 1719132.125