## Build a hospital
Build a hospital
Problem: In order to build a hospital, a construction firm needs to finish several stages of different duration. What is the total duration of the project?
Task | Weeks
| Min | M L | Max | Distribution
Design | 24 | 30 | 45 | #NAME?
Planning permission diff | 4.8 | 6 | 9 | #NAME?
Dig holes | 4 | 5 | 7.5 | #NAME?
Archaeological excavation | 2.4 | 3 | 4.5 | #NAME?
Foundations | 9.6 | 12 | 18 | #NAME?
Walls | 17.6 | 22 | 33 | #NAME?
Roof | 5.6 | 7 | 10.5 | #NAME?
Services and finishings | 12 | 15 | 22.5 | #NAME?
Commissioning | 13.6 | 17 | 25.5 | #NAME?
Job over | 93.6 | 117 | 175.5 | #NAME?