## senseInfo (hidden)
selectionIndex | checkSelected | bookName | sheetName | cellAddress | rangeAddress | analysisString | minPercent | maxPercent | minValue | maxValue | baseValue | numIntervals | varyWhenStepping | isInput | groupCount | groupIndex | formulaIndex | ioIndex | [5 empty] | intIndex | intervalMode | useCellBase | tableRange
|  |  |  | #REF! | [13 empty] | 0
senseTotal: | 16 | .
selectionIndex | checkSelected | bookName | sheetName | cellAddress | rangeAddress | analysisString | minPercent | maxPercent | minValue | maxValue | baseValue | numIntervals | varyWhenStepping | isInput | groupCount | groupIndex | formulaIndex | ioIndex | [5 empty] | intIndex | intervalMode | useCellBase | tableRange
1 | TRUE | 0 | Sheet1 | 10.5264 | F3,F4,F5,F6,F7,F8,F9,F10,F11,F12,F13,F14,F15,F16,F17,F18 | Percentile: 1.00% to 99.00% |  |  |  |  | 11 | 7 | TRUE | TRUE | 16 | 0 | 1 | 0 | A / Distribution | =RiskTriang(C3,D3,E3) | RiskTriang(C3,D3,E3) | 0 | 0 | 0 | 4 | TRUE |  | 1.00% | 5.00% | 25.00% | 50.00% | 75.00% | 95.00% | 99.00% | Perc%: 1% | Perc%: 5% | Perc%: 25% | Perc%: 50% | Perc%: 75% | Perc%: 95% | Perc%: 99%
2 | TRUE | 0 | Sheet1 | 12.0099 | F3,F4,F5,F6,F7,F8,F9,F10,F11,F12,F13,F14,F15,F16,F17,F18 | Percentile: 1.00% to 99.00% |  |  |  |  | 13.2 | 7 | TRUE | TRUE | 16 | 1 | 1 | 1 | B / Distribution | =RiskTriang(C4,D4,E4) | RiskTriang(C4,D4,E4) | 0 | 0 | 0 | 4 | TRUE |  | 1.00% | 5.00% | 25.00% | 50.00% | 75.00% | 95.00% | 99.00% | Perc%: 1% | Perc%: 5% | Perc%: 25% | Perc%: 50% | Perc%: 75% | Perc%: 95% | Perc%: 99%
3 | TRUE | 0 | Sheet1 | 13.6959 | F3,F4,F5,F6,F7,F8,F9,F10,F11,F12,F13,F14,F15,F16,F17,F18 | Percentile: 1.00% to 99.00% |  |  |  |  | 14.3 | 7 | TRUE | TRUE | 16 | 2 | 1 | 2 | C / Distribution | =RiskTriang(C5,D5,E5) | RiskTriang(C5,D5,E5) | 0 | 0 | 0 | 4 | TRUE |  | 1.00% | 5.00% | 25.00% | 50.00% | 75.00% | 95.00% | 99.00% | Perc%: 1% | Perc%: 5% | Perc%: 25% | Perc%: 50% | Perc%: 75% | Perc%: 95% | Perc%: 99%
4 | TRUE | 0 | Sheet1 | 7.7106 | F3,F4,F5,F6,F7,F8,F9,F10,F11,F12,F13,F14,F15,F16,F17,F18 | Percentile: 1.00% to 99.00% |  |  |  |  | 8.8 | 7 | TRUE | TRUE | 16 | 3 | 1 | 3 | D / Distribution | =RiskTriang(C6,D6,E6) | RiskTriang(C6,D6,E6) | 0 | 0 | 0 | 4 | TRUE |  | 1.00% | 5.00% | 25.00% | 50.00% | 75.00% | 95.00% | 99.00% | Perc%: 1% | Perc%: 5% | Perc%: 25% | Perc%: 50% | Perc%: 75% | Perc%: 95% | Perc%: 99%
5 | TRUE | 0 | Sheet1 | 9.0685 | F3,F4,F5,F6,F7,F8,F9,F10,F11,F12,F13,F14,F15,F16,F17,F18 | Percentile: 1.00% to 99.00% |  |  |  |  | 7.7 | 7 | TRUE | TRUE | 16 | 4 | 1 | 4 | E / Distribution | =RiskTriang(C7,D7,E7) | RiskTriang(C7,D7,E7) | 0 | 0 | 0 | 4 | TRUE |  | 1.00% | 5.00% | 25.00% | 50.00% | 75.00% | 95.00% | 99.00% | Perc%: 1% | Perc%: 5% | Perc%: 25% | Perc%: 50% | Perc%: 75% | Perc%: 95% | Perc%: 99%
6 | TRUE | 0 | Sheet1 | 9.178 | F3,F4,F5,F6,F7,F8,F9,F10,F11,F12,F13,F14,F15,F16,F17,F18 | Percentile: 1.00% to 99.00% |  |  |  |  | 9.9 | 7 | TRUE | TRUE | 16 | 5 | 1 | 5 | F / Distribution | =RiskTriang(C8,D8,E8) | RiskTriang(C8,D8,E8) | 0 | 0 | 0 | 4 | TRUE |  | 1.00% | 5.00% | 25.00% | 50.00% | 75.00% | 95.00% | 99.00% | Perc%: 1% | Perc%: 5% | Perc%: 25% | Perc%: 50% | Perc%: 75% | Perc%: 95% | Perc%: 99%
7 | TRUE | 0 | Sheet1 | 14.153 | F3,F4,F5,F6,F7,F8,F9,F10,F11,F12,F13,F14,F15,F16,F17,F18 | Percentile: 1.00% to 99.00% |  |  |  |  | 12.1 | 7 | TRUE | TRUE | 16 | 6 | 1 | 6 | G / Distribution | =RiskTriang(C9,D9,E9) | RiskTriang(C9,D9,E9) | 0 | 0 | 0 | 4 | TRUE |  | 1.00% | 5.00% | 25.00% | 50.00% | 75.00% | 95.00% | 99.00% | Perc%: 1% | Perc%: 5% | Perc%: 25% | Perc%: 50% | Perc%: 75% | Perc%: 95% | Perc%: 99%
8 | TRUE | 0 | Sheet1 | 7.2323 | F3,F4,F5,F6,F7,F8,F9,F10,F11,F12,F13,F14,F15,F16,F17,F18 | Percentile: 1.00% to 99.00% |  |  |  |  | 7.7 | 7 | TRUE | TRUE | 16 | 7 | 1 | 7 | H / Distribution | =RiskTriang(C10,D10,E10) | RiskTriang(C10,D10,E10) | 0 | 0 | 0 | 4 | TRUE |  | 1.00% | 5.00% | 25.00% | 50.00% | 75.00% | 95.00% | 99.00% | Perc%: 1% | Perc%: 5% | Perc%: 25% | Perc%: 50% | Perc%: 75% | Perc%: 95% | Perc%: 99%
9 | TRUE | 0 | Sheet1 | 7.5065 | F3,F4,F5,F6,F7,F8,F9,F10,F11,F12,F13,F14,F15,F16,F17,F18 | Percentile: 1.00% to 99.00% |  |  |  |  | 6.6 | 7 | TRUE | TRUE | 16 | 8 | 1 | 8 | I / Distribution | =RiskTriang(C11,D11,E11) | RiskTriang(C11,D11,E11) | 0 | 0 | 0 | 4 | TRUE |  | 1.00% | 5.00% | 25.00% | 50.00% | 75.00% | 95.00% | 99.00% | Perc%: 1% | Perc%: 5% | Perc%: 25% | Perc%: 50% | Perc%: 75% | Perc%: 95% | Perc%: 99%
10 | TRUE | 0 | Sheet1 | 10.3487 | F3,F4,F5,F6,F7,F8,F9,F10,F11,F12,F13,F14,F15,F16,F17,F18 | Percentile: 1.00% to 99.00% |  |  |  |  | 8.8 | 7 | TRUE | TRUE | 16 | 9 | 1 | 9 | J / Distribution | =RiskTriang(C12,D12,E12) | RiskTriang(C12,D12,E12) | 0 | 0 | 0 | 4 | TRUE |  | 1.00% | 5.00% | 25.00% | 50.00% | 75.00% | 95.00% | 99.00% | Perc%: 1% | Perc%: 5% | Perc%: 25% | Perc%: 50% | Perc%: 75% | Perc%: 95% | Perc%: 99%
11 | TRUE | 0 | Sheet1 | 5.3318 | F3,F4,F5,F6,F7,F8,F9,F10,F11,F12,F13,F14,F15,F16,F17,F18 | Percentile: 1.00% to 99.00% |  |  |  |  | 5.5 | 7 | TRUE | TRUE | 16 | 10 | 1 | 10 | K / Distribution | =RiskTriang(C13,D13,E13) | RiskTriang(C13,D13,E13) | 0 | 0 | 0 | 4 | TRUE |  | 1.00% | 5.00% | 25.00% | 50.00% | 75.00% | 95.00% | 99.00% | Perc%: 1% | Perc%: 5% | Perc%: 25% | Perc%: 50% | Perc%: 75% | Perc%: 95% | Perc%: 99%
12 | TRUE | 0 | Sheet1 | 10.3081 | F3,F4,F5,F6,F7,F8,F9,F10,F11,F12,F13,F14,F15,F16,F17,F18 | Percentile: 1.00% to 99.00% |  |  |  |  | 9.9 | 7 | TRUE | TRUE | 16 | 11 | 1 | 11 | L / Distribution | =RiskTriang(C14,D14,E14) | RiskTriang(C14,D14,E14) | 0 | 0 | 0 | 4 | TRUE |  | 1.00% | 5.00% | 25.00% | 50.00% | 75.00% | 95.00% | 99.00% | Perc%: 1% | Perc%: 5% | Perc%: 25% | Perc%: 50% | Perc%: 75% | Perc%: 95% | Perc%: 99%
13 | TRUE | 0 | Sheet1 | 11.9041 | F3,F4,F5,F6,F7,F8,F9,F10,F11,F12,F13,F14,F15,F16,F17,F18 | Percentile: 1.00% to 99.00% |  |  |  |  | 12.1 | 7 | TRUE | TRUE | 16 | 12 | 1 | 12 | M / Distribution | =RiskTriang(C15,D15,E15) | RiskTriang(C15,D15,E15) | 0 | 0 | 0 | 4 | TRUE |  | 1.00% | 5.00% | 25.00% | 50.00% | 75.00% | 95.00% | 99.00% | Perc%: 1% | Perc%: 5% | Perc%: 25% | Perc%: 50% | Perc%: 75% | Perc%: 95% | Perc%: 99%
14 | TRUE | 0 | Sheet1 | 9.9276 | F3,F4,F5,F6,F7,F8,F9,F10,F11,F12,F13,F14,F15,F16,F17,F18 | Percentile: 1.00% to 99.00% |  |  |  |  | 11 | 7 | TRUE | TRUE | 16 | 13 | 1 | 13 | N / Distribution | =RiskTriang(C16,D16,E16) | RiskTriang(C16,D16,E16) | 0 | 0 | 0 | 4 | TRUE |  | 1.00% | 5.00% | 25.00% | 50.00% | 75.00% | 95.00% | 99.00% | Perc%: 1% | Perc%: 5% | Perc%: 25% | Perc%: 50% | Perc%: 75% | Perc%: 95% | Perc%: 99%
15 | TRUE | 0 | Sheet1 | 9.9204 | F3,F4,F5,F6,F7,F8,F9,F10,F11,F12,F13,F14,F15,F16,F17,F18 | Percentile: 1.00% to 99.00% |  |  |  |  | 11 | 7 | TRUE | TRUE | 16 | 14 | 1 | 14 | O / Distribution | =RiskTriang(C17,D17,E17) | RiskTriang(C17,D17,E17) | 0 | 0 | 0 | 4 | TRUE |  | 1.00% | 5.00% | 25.00% | 50.00% | 75.00% | 95.00% | 99.00% | Perc%: 1% | Perc%: 5% | Perc%: 25% | Perc%: 50% | Perc%: 75% | Perc%: 95% | Perc%: 99%
16 | TRUE | 0 | Sheet1 | 6.7458 | F3,F4,F5,F6,F7,F8,F9,F10,F11,F12,F13,F14,F15,F16,F17,F18 | Percentile: 1.00% to 99.00% |  |  |  |  | 8.8 | 7 | TRUE | TRUE | 16 | 15 | 1 | 15 | P / Distribution | =RiskTriang(C18,D18,E18) | RiskTriang(C18,D18,E18) | 0 | 0 | 0 | 4 | TRUE |  | 1.00% | 5.00% | 25.00% | 50.00% | 75.00% | 95.00% | 99.00% | Perc%: 1% | Perc%: 5% | Perc%: 25% | Perc%: 50% | Perc%: 75% | Perc%: 95% | Perc%: 99%

## Schedule model with risks
Schedule model with risks
Problem: There are three identified risks that can influence the duration of certain stages of the project. The GANTT chart below shows the diagram of the project schedule. Calculate the distribution of the total duration for this project.
Risks associated with this project
| Risk | Affecting activity | Min | M L | Max | Notes | Probability
| 1 | G | 20% | 30% | 50% | of G's value | 30%
| 2 | J | 3 | 4 | 6 | weeks | 50%
| 3 | M | 4 | 6 | 7 | weeks | 20% if neither 1 nor 2 occures, otherwise 40%
Model
Task | Min 80% | Most likely | Max 150% | Distribution | Start | Finish | Risk | Triang.Distr. | Extra | A
A | 8 | 10 | 15 | 10.5264 | 0 | 10.5264 |  |  |  |  | B
B | 9.6 | 12 | 18 | 12.0099 | 10.5264 | 22.5363 |  |  |  |  | C
C | 10.4 | 13 | 19.5 | 13.6959 | 10.5264 | 24.2224 |  |  |  |  | D
D | 6.4 | 8 | 12 | 7.7106 | 10.5264 | 18.237 | [5 empty] | E
E | 5.6 | 7 | 10.5 | 9.0685 | 24.2224 | 33.2908 | [6 empty] | F
F | 7.2 | 9 | 13.5 | 9.178 | 33.2908 | 42.4688 | [7 empty] | G
G | 8.8 | 11 | 16.5 | 14.153 | 42.4688 | 56.6218 | 0 | 38.92% | 0 |  |  | H
H | 5.6 | 7 | 10.5 | 7.2323 | 24.2224 | 31.4546 | [6 empty] | I
I | 4.8 | 6 | 9 | 7.5065 | 31.4546 | 38.9611 | [7 empty] | J
J | 6.4 | 8 | 12 | 10.3487 | 38.9611 | 53.3577 | 1 | 4.048 | 4.048 |  |  | K
K | 4 | 5 | 7.5 | 5.3318 | 24.2224 | 29.5541 | [6 empty] | L
L | 7.2 | 9 | 13.5 | 10.3081 | 29.5541 | 39.8623 | [7 empty] | M
M | 8.8 | 11 | 16.5 | 11.9041 | 39.8623 | 57.9266 | 1 | 6.1603 | 6.1603 | [5 empty] | N
N | 8 | 10 | 15 | 9.9276 | 57.9266 | 67.8542 | [8 empty] | O
O | 8 | 10 | 15 | 9.9204 | 57.9266 | 67.847 | [9 empty] | P
P | 6.4 | 8 | 12 | 6.7458 | 67.8542 | 74.5999
[6 empty] | P (in cell I30) | 0.4
E, H, K can only start when all of B, C, and D are finished
N, O can only start when all of G, J, and M are finished
GANTT chart