## Build a silo
Build a silo
Problem: In order to build a silo, a construction firm needs to finish several inter-related stages of different duration. What is the total duration of the project?
Task | Weeks
| Min | M L | Max | Distribution | Task
Main building | [5 empty] | start | finish
build walls | 6 | 8 | 14 | 9.5268 | Main building | 1 | 1
build roof | 3 | 4 | 6 | 4.5224 | build walls | 0 | 9.5268 | 1 | 1
[5 empty] | build roof | 9.5268 | 14.0492 | 14.0492 | 14.7032
Left wing
build walls | 3 | 5 | 9 | 4.2196 | Left wing | 0.8 | 0.8
buils roof | 5 | 7 | 12 | 6.9057 | build walls | 0 | 4.2196
plaster the walls | 1 | 2 | 5 | 1.816 | buils roof | 4.2196 | 11.1253 | 0.8 | 0.8
[5 empty] | plaster the walls | 11.1253 | 12.9413 | 12.9413 | 14.7032
Right wing
build walls | 2 | 3 | 7 | 5.6471 | Right wing | 0.6 | 0.6
buils roof | 2 | 4 | 8 | 3.287 | build walls | 0 | 5.6471
plaster the walls | 3 | 4 | 5 | 3.9678 | buils roof | 5.6471 | 8.934 | 0.6 | 0.6
[5 empty] | plaster the walls | 8.934 | 14.7032 | 14.7032 | 14.7032
Build fence | 2 | 3 | 6 | 5.7691
[6 empty] | 0.4 | 0.4
Total duration | 11 | 17 | 32 | 19.8183 | Build fence | 14.7032 | 20.4723
[6 empty] | 14.7032 | 14.7032
[6 empty] | 1 | 0.4
Main
Left
Right
Fence