## Risk portfolio
Risk portfolio
Problem: Model a portfolio of risks that can influence the base estimated project cost and calculate the total cost of a project including inflation. There are 5 risk factors, some of which are correlated, plus the risk coming from the inflation. The probability of a strike doubles if the "bad weather" factor occurs. If both the "H&S" and "Strike" factors occur, the "Insolvency of sub-contractor" risk factor rises from 5% to 75%.
Base project cost | 110
Risks | Extra cost
| Probability | M L | Min | Max | Risk occurs? | Distribution | Extra cost
H&S | 10% | 20 | 16 | 30 | 0 | 24.2796 | 0
Strike | 30% | 5 | 4 | 7.5 | 0 | 5.1311 | 0
Bad weather | 30% | 20 | 16 | 30 | 1 | 19.5806 | 19.5806
Insolvency of sub-contractor | 5% | 10 | 8 | 15 | 0 | 12.9745 | 0
Political change | 2% | 20 | 16 | 30 | 0 | 24.546 | 0
Total cost excl inflation | 129.5806
Inflation | 1.0644
Total cost including inflation | 137.9242
Use of the Yes-No (Bernoulli) distribution