## Risk portfolio
Risk portfolio
Problem: Model a portfolio of risks that can influence the base estimated project cost and calculate the total cost of a project including inflation. There are 5 risk factors, some of which are correlated, plus the risk coming from the inflation. The probability of a strike doubles if the "bad weather" factor occurs. If both the "H&S" and "Strike" factors occur, the "Insolvency of sub-contractor" risk factor rises from 5% to 75%.
Base project cost | #NAME?
Risks | Extra cost
| Probability | M L | Risk occurs? | Distribution
H&S | 10% | 20 | #NAME? | #NAME?
Strike | #NAME? | 5 | #NAME? | #NAME?
Bad weather | 30% | 20 | #NAME? | #NAME?
Insolvency of sub-contractor | #NAME? | 10 | #NAME? | #NAME?
Political change | 2% | 20 | #NAME? | #NAME?
Total cost excl inflation | #NAME?
Inflation | #NAME?
Total cost including inflation | #NAME?