## Build a silo
Build a silo
Problem: In order to build a silo, a construction firm needs to finish several inter-related stages of different duration. What is the total duration of the project?
Task | Weeks |  |  |  | Task
| Min | M L | Max | Distribution |  | start | finish
Main building |  |  |  |  | Main building | 1 | 1
build walls | 6 | 8 | 14 | #NAME? | build walls | 0 | #NAME? | 1 | 1
build roof | 3 | 4 | 6 | #NAME? | build roof | #NAME? | #NAME? | #NAME? | #NAME?
Left wing |  |  |  |  | Left wing | 0.8 | 0.8
build walls | 3 | 5 | 9 | #NAME? | build walls | 0 | #NAME?
buils roof | 5 | 7 | 12 | #NAME? | buils roof | #NAME? | #NAME? | 0.8 | 0.8
plaster the walls | 1 | 2 | 5 | #NAME? | plaster the walls | #NAME? | #NAME? | #NAME? | #NAME?
Right wing |  |  |  |  | Right wing | 0.6 | 0.6
build walls | 2 | 3 | 7 | #NAME? | build walls | 0 | #NAME?
buils roof | 2 | 4 | 8 | #NAME? | buils roof | #NAME? | #NAME? | 0.6 | 0.6
plaster the walls | 3 | 4 | 5 | #NAME? | plaster the walls | #NAME? | #NAME? | #NAME? | #NAME?
Build fence | 2 | 3 | 6 | #NAME? |  | 0.4 | 0.4
[5 empty] | Build fence | #NAME? | #NAME?
Total duration | 11 | 17 | 32 | #NAME?
[6 empty] | #NAME? | #NAME?
[6 empty] | 1 | 0.4
Main
Left
Right
Fence