## Cost and schedule
Cost and schedule
Problem: A new building is to be constructed by a consortium for a client. The project is divided into seven sections. The client wishes to see a risk analysis of the schedule and cost risks and how these relate to each other.
Contract award date | 2018-04-10
| Start | Duration d (weeks) |  |  |  | Finish | Probability | Start | Start lag (weeks) |  |  |  | Finish | Finish lag (weeks) |  |  |  |  | Cost |  |  |  | Probability | Crystal Ball format
| Date St | Dist | Min | ML | Max | Date Fin |  | logic | Dist | Min | ML | Max | logic | Dist | Min | ML | Max |  | Dist | Min | ML | Max |  | Dist | Probability
DESIGN (Task1) | [17 empty] | DESIGN (Task1)
Detail (a) | 2018-04-10 | 17.8434 | 12 | 16 | 25 | 2018-08-12 21:42 | 80% | Start logic: =Start date; Finish logic: St+d | Detail | 160000 |  | 160000 |  | 80% | 160000 | 80%
Rework risk (b) | 2018-08-12 21:42 | 4.6119 | 3 | 4 | 6 | 2018-09-14 04:30 | 20% | Start logic: Fin1a; Finish logic: St+d | +Rework risk | 215343.1344 |  | 12000 | per week | 20% | 215343.1344 | 20%
Total (c) | [5 empty] | 2005-10-26 04:30 |  | Finish logic: Discrete | Total | 160000
EARTHWORKS (Task2) | [17 empty] | EARTHWORKS (Task2) | 4500 | <-- per week
Normal (a) | 2018-04-10 | 4.1825 | 3 | 4 | 7 | 2018-05-09 06:39 | 70% | Start logic: =Start date; Finish logic: St+d | Normal | 18821.0684 | 4200 | 4500 | 4700 | per week
Archaeo risk (b) | 2018-05-09 06:39 | 11.3564 | 8 | 10 | 14 | 2018-07-27 18:31 | 30% | Start logic: Fin2a; Finish logic: St+d
Total (c) | [5 empty] | 2018-07-27 18:31 | 0 | Finish logic: Discrete | FOUNDATIONS (Task3) | 3000 | <-- per week
[18 empty] | Labour | 21381.3361 | 2800 | 3000 | 3300 | per week
FOUNDATIONS (Task3) | [17 empty] | Materials | 38500 | 37000 | 38500 | 40000
| 2018-07-27 18:31 | 7.1271 | 6 | 7 | 8 | 2018-09-15 15:53 |  | Start logic: MAX(Fin1c, Fin2c); Finish logic: St+d | Total | 59881.3361
STRUCTURE (Task4) | [17 empty] | STRUCTURE (Task4) | [5 empty] | Per week or floor
Floor1 (a) | 2018-11-05 04:36 | 4.6222 | 4 | 4.5 | 6 | 2018-12-07 13:07 |  | Fin3+lag | 7.2186 | 6 | 7 | 8 | St+d |  |  |  |  | Floor1 labour | 50657.8814 | 4700 | 5200 | 5500 | per week | 5200
Floor2 (b) | 2018-12-07 13:07 | 5.241 | 4 | 4.5 | 6 | 2019-01-13 05:36 |  | Start logic: Fin4a; Finish logic: St+d | Floor2 labour | 54044.4184 | 4700 | 5200 | 5500 | per week | 5200
Floor3 (c) | 2019-01-13 05:36 | 4.6331 | 4 | 4.5 | 6 | 2019-02-14 15:58 |  | Start logic: Fin4b; Finish logic: St+d | Floor3 labour | 61668.401 | 4700 | 5200 | 5500 | per week | 5200
Roofing (d) | 2019-02-14 15:58 | 7.4656 | 7 | 8 | 10 | 2019-04-07 22:11 |  | Finish logic: St+d | Floor materials | 52700 | 17200 | 17500 | 18000 | per floor
[18 empty] | Roofing | 172000
ENVELOPE (Task5) | [17 empty] | Total | 391070.7008
Brown Bros | [6 empty] | 90% | [16 empty] | Crystal Ball format
Floor1 (a) | 2018-12-28 13:07 | 8.2624 | 7 | 8 | 9 | 2019-02-24 09:12 |  | Start logic: Fin4a+lag; Start lag (weeks) Dist: 3; Start lag (weeks) ML: 3; Finish logic: St+d | ENVELOPE (Task5) | [5 empty] | Dist | Probability
Floor2 (b) | 2019-02-24 09:12 | 7.1229 | 7 | 8 | 9 | 2019-04-15 05:51 |  | Start logic: Fin5a; Finish logic: St+d | Labour
Floor3 (c) | 2019-04-15 05:51 | 8.1814 | 7 | 8 | 9 | 2019-06-11 12:19 |  | Start logic: Fin5b; Finish logic: St+d | Brown Bros | 197000 |  |  |  | 90% | 197000 | 90%
Redd&Greene | [6 empty] | 10% | [10 empty] | Redd&Greene | 209000 |  |  |  | 10% | 209000 | 10%
Floor1 (d) | 2018-12-28 13:07 | 8.1607 | 6 | 8 | 11 | 2019-02-23 16:08 |  | Start logic: Fin4a+lag; Start lag (weeks) Dist: 3; Start lag (weeks) ML: 3; Finish logic: St+d | Labour total | 200000 |  |  |  |  | Per floor
Floor2 (e) | 2019-02-23 16:08 | 8.5687 | 6 | 8 | 11 | 2019-04-24 15:40 |  | Start logic: Fin5d; Finish logic: St+d | Floor | 111000 | 36000 | 37000 | 40000 | per floor | 37000
Floor3 (f) | 2019-04-24 15:40 | 8.793 | 6 | 8 | 11 | 2019-06-25 04:53 |  | Start logic: Fin5e; Finish logic: St+d | Doors | 9800 |  | 9800
Totals | Brown Bros |  |  |  |  | 2019-06-11 12:19 | 90% | [10 empty] | Total | 320800
| Redd&Greene |  |  |  |  | 2019-06-25 04:53 | 10%
(g) | Combined |  |  |  |  | 2006-09-09 22:18 |  | Finish logic: Discrete | SERVICES AND FINISHINGS (Task6)
[18 empty] | Services | 258000 | 82000 | 86000 | 91000 |  | 86000
SERVICES AND FINISHINGS (Task6) | [17 empty] | Finishings | 285000 | 92000 | 95000 | 107000 |  | 95000
Services | [17 empty] | Total | 543000
Floor1 (a) | 2019-02-23 16:08 | 9.7419 | 8 | 10 | 13 | 2019-05-02 20:46 |  | Start logic: Fin5a or 5d; Finish logic: St+d
Floor2 (b) | 2019-05-02 20:46 | 10.3932 | 8 | 10 | 13 | 2019-07-14 14:49 |  | Start logic: Fin5b or 5e; Finish logic: St+d | COMMISSIONING (Task7)
Floor3 (c) | 2019-07-14 14:49 | 11.8593 | 8 | 10 | 13 | 2019-10-05 15:11 |  | Start logic: Fin5c or 5f; Finish logic: St+d | Tidy up site | 4000 |  | 4000
Finishings
Floor1 (d) | 2019-02-23 16:08 | 10.3044 | 9 | 11 | 13 | 2019-05-23 20:46 |  | St6a |  |  |  |  | Max | 3 | 2 | 3 | 4 | GRAND TOTAL | 1497573.1053
Floor2 (e) | 2019-05-02 20:46 | 10.649 | 9 | 11 | 13 | 2019-08-04 14:49 |  | St6b |  |  |  |  | Max | 3 | 2 | 3 | 4
Floor3 (f) | 2019-07-14 14:49 | 10.7989 | 9 | 11 | 13 | 2019-10-26 15:11 |  | St6c |  |  |  |  | Max | 3 | 2 | 3 | 4
COMMISSIONING (Task7)
Tidy up site (a) | 2019-10-26 15:11 | 2 |  | 2 |  | 2019-11-09 15:11 | 60% | Start logic: Fin6f; Finish logic: St+d
1st call back (b) | 2019-11-09 15:11 | 0.8227 | 0.5 | 2 | 5 | 2019-11-15 09:24 | 35% | Start logic: Fin7a; Finish logic: St+d
2nd call back (c) | 2019-11-15 09:24 | 1.1178 | 0.5 | 1 | 1.5 | 2019-11-23 05:11 | 5% | Start logic: Fin7b; Finish logic: St+d
Total | [5 empty] | 1899-12-31 |  | Finish logic: Discrete
FINISH DATE | 2019-11-23 05:11
Formulas:
Start = [Finish, row above]
Start = H22+7*[Start lag (weeks)]
Finish = [Start]+[Duration d (weeks)]*7
Finish = IF([Probability]=1,H17,[Finish, row above])