## CB_DATA_ (hidden)
Crystal Ball Data
0
Workbook Variables | Last Var Column | 0
Name:
Value:
Worksheet Data | Last Data Column Used
0
Sheet Ref
Sheet Guid
Deleted sheet count
Last row used
Data blocks

## Pylons - Not correlated
Pylons
Problem: Your company has been invited to bid for a project to design and construct a line of 16 electricity pylons. Estimates are based on PERT distributions (using absolute minimum, most likely and absolute maximum) unless indicated. Produce distributions of the total project cost and duration. Use a scatter plot to illustrate the relationship between the project’s cost and duration. Plot iterations above and below 35 weeks separately on the same graph and fit regression lines through the two data sets.
|  | Number of pylons | 16
Summary costs: | USD | Design: | Min | Most likely | Max |  |  | Actual
Design: | 165000 | In-house design | 150000 | 165000 | 190000 |  |  | 165000 | Binomial
Construction foundation: | 485681.6765 | Sub-contracted | 180000 | 200000 | 235000 |  |  | 200000 | 0
Construction pylon: | 913920 | Prob in house
Penalty: | 0 | Prob. of French job |  | 40%
Sum: | 1564601.6765 |  |  | Total costs |  |  |  | 165000
Project duration: | 32.5
|  | Construction foundation: | Min | Most likely | Max |  |  | Actual
|  | Material/pylon | 6200 | 7000 | 7900 |  |  | 7000
|  | Man hours for all pylons |  | 9600 |  | StDev | 320 | 9824.2235
Total time | 32.5 | Cost/man hour |  | 7.5 |  |  |  | 7.5
Over time | 0 | Total plant cost | 250000 | 300000 | 380000 |  |  | 300000
Weeks | 0
Penalty/wk | 25000 |  |  | Total costs |  |  |  | 485681.6765
Penalty | 0
|  | Construction pylon: | Min | Most likely | Max |  |  | Actual
|  | Steel cost/pylon | 52000 | 54000 | 58500 |  |  | 54000
|  | Man hours/pylon | 200 | 240 | 270 |  |  | 240
|  | Cost/man hour |  | 13 |  |  |  | 13
|  |  |  | Total costs |  |  |  | 913920
|  | Time constraints: | Min | Most likely | Max |  |  | Actual
|  | Design | 10 | 12 | 15 |  |  | 12
|  | Foundations | 14 | 16 | 21 |  |  | 16
|  | Time foundation-last pylon | 4 | 4.5 | 5.5 |  |  | 4.5

## Scatter plot - no correlation
Project duration: | Sum:
29.0909 | 1543518.286
29.1349 | 1595302.5245
29.2241 | 1628717.0094
29.3052 | 1662047.9681
29.3541 | 1590850.1386
29.3682 | 1553655.8476
29.4619 | 1530349.8581
29.4662 | 1587201.9245
29.5577 | 1643452.8175
29.7116 | 1510228.6196
29.7152 | 1579638.5292
29.7242 | 1584737.6434
29.7326 | 1594785.6593
29.7484 | 1608200.253
29.7559 | 1632507.2944
29.7755 | 1570247.5773
29.7818 | 1568589.5981
29.8215 | 1590049.0455
29.8303 | 1598566.6181
29.8931 | 1674867.6484
29.9143 | 1585473.3622
29.9267 | 1552380.0135
29.9366 | 1528800.6083
29.9551 | 1584958.209
29.9626 | 1633666.9656
29.9627 | 1586682.3625
29.9737 | 1600670.2788
29.979 | 1539913.2434
29.9791 | 1591986.08
29.9869 | 1552619.1669
30.0167 | 1606510.2425
30.0311 | 1591759.4798
30.0315 | 1604720.592
30.0396 | 1574496.8766
30.0425 | 1598778.9458
30.0511 | 1586709.7835
30.0589 | 1578231.8458
30.0826 | 1631557.5439
30.1035 | 1579840.6349
30.1118 | 1611285.7426
30.1221 | 1593797.721
30.1463 | 1521805.8822
30.1564 | 1546413.1227
30.1595 | 1549006.8832
30.1751 | 1527322.1614
30.1852 | 1575535.4408
30.1909 | 1591099.3441
30.2149 | 1597058.4698
30.2162 | 1587486.8072
30.218 | 1583513.4787
30.2359 | 1623324.0511
30.2382 | 1590664.2984
30.246 | 1517724.6819
30.249 | 1564874.0856
30.2499 | 1552635.4828
30.2696 | 1633743.9865
30.2696 | 1558603.7235
30.287 | 1641184.7887
30.2922 | 1584708.1861
30.2935 | 1641341.3534
30.2942 | 1559853.8276
30.303 | 1616670.3843
30.307 | 1614724.6491
30.3154 | 1646862.4901
30.3248 | 1566606.4904
30.332 | 1607593.2597
30.3408 | 1662806.6789
30.351 | 1594080.8134
30.3515 | 1538394.1002
30.3544 | 1683812.1552
30.3575 | 1504158.0095
30.362 | 1573566.6876
30.3645 | 1617491.3994
30.382 | 1567055.1628
30.3927 | 1567961.1095
30.3986 | 1596897.8674
30.3999 | 1592515.7914
30.4006 | 1561241.0048
30.4051 | 1626626.3073
30.4153 | 1621588.7096
30.418 | 1578338.6646
30.4229 | 1547043.1491
30.4343 | 1608178.491
30.4501 | 1659586.9005
30.456 | 1557270.4023
30.461 | 1637006.5635
30.4623 | 1604529.5362
30.4631 | 1528807.595
30.4796 | 1604009.9347
30.4827 | 1626510.8467
30.4883 | 1582688.4412
30.4929 | 1530517.324
30.4931 | 1535036.0442
30.4991 | 1573836.5183
30.508 | 1523777.15
30.5099 | 1575498.0535
30.5237 | 1556668.5135
30.535 | 1669517.6129
30.5434 | 1611009.1979
30.5439 | 1642815.6258
30.5555 | 1622683.5736
30.5711 | 1639189.0108
30.5773 | 1575478.7688
30.579 | 1543360.5119
30.5827 | 1547002.019
30.5886 | 1630493.1474
30.5957 | 1623104.2423
30.5999 | 1552053.2169
30.61 | 1624101.7032
30.6137 | 1556460.059
30.6192 | 1577114.9547
30.6242 | 1536050.8758
30.6258 | 1571913.1359
30.6353 | 1588727.782
30.6482 | 1603835.2604
30.6531 | 1612538.5558
30.6557 | 1576117.726
30.6561 | 1558844.2026
30.6609 | 1585294.6816
30.6656 | 1611636.1853
30.6658 | 1589416.5836
30.6717 | 1582921.4237
30.6807 | 1548770.4074
30.6835 | 1542465.3099
30.6899 | 1588286.2061
30.7027 | 1604251.9817
30.703 | 1572466.6474
30.7224 | 1508156.4728
30.723 | 1565260.3379
30.7261 | 1572443.0966
30.7272 | 1550965.5681
30.7302 | 1586125.1151
30.7375 | 1673330.8598
30.7407 | 1553235.1698
30.7413 | 1581771.9806
30.7416 | 1581615.0967
30.7511 | 1654036.889
30.7555 | 1620481.2936
30.7581 | 1543783.6634
30.7615 | 1660824.3021
30.7836 | 1602254.614
30.7858 | 1584991.2046
30.7972 | 1687519.3259
30.7972 | 1578523.9648
30.7985 | 1641852.3383
30.8054 | 1555721.2517
30.8075 | 1544626.1716
30.8144 | 1663184.4257
30.8209 | 1578947.939
30.8255 | 1674108.2982
30.8387 | 1622786.0643
30.8418 | 1562567.2044
30.8539 | 1602763.9697
30.8543 | 1545376.3183
30.8576 | 1557529.9406
30.8581 | 1581160.5582
30.8601 | 1565315.8014
30.8724 | 1549128.3268
30.8737 | 1573975.2879
30.8766 | 1600383.4212
30.8767 | 1578079.6829
30.879 | 1688622.5256
30.8828 | 1638347.4983
30.884 | 1664387.6323
30.8873 | 1594513.8556
30.8894 | 1557209.6103
30.892 | 1578200.7915
30.8927 | 1533618.1991
30.8928 | 1599089.1462
30.8961 | 1621181.1898
30.8977 | 1629299.2518
30.904 | 1576986.5878
30.9043 | 1615381.4682
30.9122 | 1582822.0964
30.9172 | 1634153.5485
30.92 | 1532491.3795
30.9211 | 1544383.2979
30.9228 | 1604251.0271
30.9228 | 1554704.0582
30.9249 | 1551445.528
30.9279 | 1597002.0256
30.933 | 1563813.802
30.9348 | 1527670.6414
30.9364 | 1622464.5881
30.9401 | 1563607.9744
30.9421 | 1544149.6566
30.9427 | 1598727.9425
30.9501 | 1528758.2174
30.9541 | 1606705.4282
30.9575 | 1651172.5069
30.9575 | 1544666.8129
30.9597 | 1596680.0221
30.9669 | 1630070.1172
30.9689 | 1606137.8837
30.9707 | 1559793.815
30.9712 | 1643751.7934
30.9766 | 1558634.2722
30.9795 | 1670548.0694
30.9808 | 1675608.8249
30.9827 | 1546740.9682
30.9831 | 1606048.3193
30.9867 | 1578300.5011
30.9879 | 1606255.0788
30.9929 | 1631245.2947
30.9933 | 1541923.511
31.0011 | 1630539.7667
31.0052 | 1585352.5529
31.0059 | 1562458.5717
31.0151 | 1593980.5004
31.0234 | 1594607.4961
31.0269 | 1554691.5828
31.0281 | 1608615.6047
31.0319 | 1591715.5169
31.032 | 1595785.2057
31.0432 | 1576342.8318
31.0461 | 1631511.3206
31.0471 | 1634699.7711
31.0481 | 1540427.2513
31.0493 | 1628524.8422
31.0497 | 1589552.2589
31.0512 | 1628529.0692
31.0537 | 1665624.2024
31.0601 | 1588763.5312
31.0666 | 1581916.2157
31.0698 | 1618934.2396
31.0705 | 1629382.9178
31.0753 | 1639427.7113
31.0763 | 1555170.3163
31.0774 | 1553739.4286
31.0795 | 1571917.7631
31.0893 | 1618805.4191
31.0894 | 1577245.6367
31.0911 | 1548790.814
31.0996 | 1609863.2571
31.1 | 1562656.0288
31.102 | 1602080.8135
31.1045 | 1520764.1694
31.1153 | 1553363.4191
31.1155 | 1558131.5829
31.117 | 1631859.198
31.1186 | 1614101.99
31.1205 | 1546020.6483
31.1212 | 1573352.6913
31.122 | 1609146.747
31.1228 | 1636054.5643
31.1249 | 1640572.8553
31.1255 | 1634910.5818
31.1305 | 1599845.2828
31.1324 | 1558138.6314
31.1364 | 1534638.2816
31.1365 | 1630255.6546
31.1366 | 1545541.4587
31.1369 | 1588387.2003
31.141 | 1645839.9963
31.1421 | 1558099.8641
31.1504 | 1642723.7299
31.1506 | 1577121.8429
31.1588 | 1685776.6415
31.1663 | 1581096.9033
31.1724 | 1595854.778
31.1738 | 1612790.0737
31.1756 | 1680280.21
31.176 | 1553853.9153
31.1769 | 1622526.6576
31.1834 | 1614635.5847
31.1846 | 1639660.2135
31.186 | 1575347.1804
31.19 | 1584523.6607
31.1935 | 1580921.7647
31.1938 | 1609495.6181
31.2073 | 1565917.8692
31.21 | 1574833.42
31.2151 | 1602836.6918
31.216 | 1606715.0799
31.2216 | 1629489.8267
31.2226 | 1555015.832
31.2233 | 1605166.3284
31.2291 | 1598776.4012
31.23 | 1579482.1345
31.231 | 1590246.6577
31.2332 | 1655140.9059
31.2348 | 1594410.8232
31.2357 | 1546287.6634
31.2371 | 1628826.7061
31.2409 | 1624494.5927
31.2429 | 1590137.0205
31.243 | 1612623.6745
31.2433 | 1626522.6901
31.244 | 1604143.1242
31.2444 | 1651331.7929
31.2477 | 1506272.2485
31.2513 | 1537441.8314
31.2533 | 1558613.275
31.2627 | 1614301.0348
31.2631 | 1549382.5193
31.2642 | 1589273.5929
31.2674 | 1593400.8921
31.2689 | 1633301.5046
31.2696 | 1603122.099
31.2699 | 1596319.5863
31.2714 | 1668305.5397
31.2716 | 1599590.3053
31.2774 | 1592814.9084
31.2831 | 1587128.3935
31.2889 | 1603890.3211
31.2903 | 1558287.6287
31.291 | 1550125.2918
31.2951 | 1580891.9542
31.3007 | 1577485.3946
31.3012 | 1583431.9913
31.3039 | 1539935.2828
31.3095 | 1589972.1009
31.3121 | 1560676.7691
31.3157 | 1643681.9227
31.3164 | 1626788.6502
31.323 | 1540216.7066
31.3236 | 1551179.5448
31.3254 | 1565462.7476
31.3261 | 1581606.1638
31.3271 | 1591514.0224
31.328 | 1552194.4679
31.3281 | 1590372.7976
31.3306 | 1527234.452
31.3322 | 1554189.4527
31.3378 | 1632762.5155
31.3452 | 1564016.4312
31.3492 | 1551477.1425
31.3541 | 1667622.7333
31.3553 | 1622853.779
31.3592 | 1545020.6663
31.3605 | 1568737.2551
31.3615 | 1643380.2106
31.3623 | 1627948.1898
31.3639 | 1560744.1174
31.3712 | 1630819.5892
31.3716 | 1633439.5444
31.3719 | 1613699.9508
31.3804 | 1624505.2125
31.3824 | 1639034.8168
31.3847 | 1615504.6972
31.3905 | 1574664.338
31.3931 | 1568960.9882
31.395 | 1561443.7195
31.3954 | 1594086.1773
31.3995 | 1607464.4364
31.4049 | 1595365.8358
31.4076 | 1547951.2572
31.4144 | 1556337.3682
31.4151 | 1655219.6916
31.4154 | 1595057.0158
31.4158 | 1556720.3292
31.4192 | 1671778.188
31.4202 | 1613293.7935
31.4206 | 1563329.936
31.4238 | 1606788.9739
31.425 | 1492735.6719
31.4309 | 1598413.2155
31.4314 | 1591605.0149
31.4317 | 1616042.0381
31.4318 | 1610277.4839
31.4331 | 1576054.1863
31.4339 | 1673099.2859
31.4381 | 1545347.8694
31.4395 | 1606003.1111
31.4415 | 1525515.2872
31.4433 | 1525814.1919
31.4453 | 1538908.7973
31.4469 | 1577786.6141
31.4487 | 1550080.1107
31.4543 | 1614025.3522
31.4548 | 1622561.154
31.4591 | 1537701.022
31.4625 | 1589787.9782
31.4649 | 1647484.3088
31.4733 | 1539511.8682
31.4765 | 1656964.8588
31.4791 | 1635097.2987
31.4799 | 1620739.9089
31.4808 | 1584460.5279
31.4812 | 1565615.2451
31.4813 | 1551169.7095
31.4817 | 1585599.5726
31.4871 | 1541247.6377
31.4881 | 1573496.8136
31.4882 | 1553383.2669
31.4913 | 1562992.4483
31.4915 | 1612373.1171
31.4925 | 1531251.988
31.495 | 1597390.3412
31.4961 | 1611235.5625
31.4989 | 1615790.0288
31.4992 | 1592957.646
31.5002 | 1583521.5922
31.5005 | 1575033.8393
31.5033 | 1580036.5641
31.5065 | 1580094.6289
31.5127 | 1608354.6481
31.5128 | 1591253.7972
31.5169 | 1644003.387
31.517 | 1651404.6964
31.5179 | 1592917.6987
31.5183 | 1578579.2181
31.5237 | 1587454.4291
31.5251 | 1582621.2933
31.5252 | 1549484.3543
31.5254 | 1569779.5577
31.5258 | 1628159.6205
31.5262 | 1612076.3989
31.5276 | 1642573.7337
31.5291 | 1587151.3883
31.5299 | 1596848.8234
31.5329 | 1631001.0848
31.533 | 1593313.3684
31.5338 | 1556552.3216
31.5348 | 1584313.2174
31.5351 | 1558943.6111
31.5355 | 1501947.9096
31.5366 | 1625342.0687
31.5398 | 1588015.3702
31.5403 | 1556418.795
31.5403 | 1605186.2911
31.5416 | 1610362.811
31.5422 | 1601295.8704
31.5526 | 1625334.8861
31.5547 | 1583429.6769
31.5551 | 1575907.1742
31.5728 | 1597740.461
31.5759 | 1658855.5415
31.5769 | 1546827.3369
31.5774 | 1499478.8169
31.5776 | 1670018.4208
31.5778 | 1553512.4569
31.5779 | 1598550.5612
31.5824 | 1642975.4624
31.5837 | 1611854.2423
31.584 | 1540217.9009
31.5879 | 1599415.1305
31.588 | 1597496.2746
31.5897 | 1632929.8046
31.5929 | 1564460.6574
31.5957 | 1586708.6935
31.6011 | 1537102.4834
31.6038 | 1525665.7524
31.6048 | 1538517.1516
31.6051 | 1649426.3395
31.6059 | 1633901.36
31.6081 | 1612617.6693
31.6085 | 1592759.1841
31.612 | 1693800.1771
31.6126 | 1585019.7182
31.6126 | 1689979.8273
31.618 | 1570877.8036
31.6209 | 1571438.5273
31.6223 | 1579528.2733
31.6246 | 1603736.2871
31.6266 | 1608047.4139
31.6298 | 1573593.142
31.6303 | 1622831.0598
31.6304 | 1590841.0849
31.6382 | 1590758.6862
31.6408 | 1548972.951
31.6452 | 1578314.8728
31.647 | 1541859.1331
31.6573 | 1592034.2608
31.6681 | 1570356.9911
31.669 | 1644161.5528
31.6696 | 1581327.8427
31.6708 | 1540047.217
31.6718 | 1541136.4744
31.6733 | 1541959.8855
31.6744 | 1580010.0766
31.6763 | 1575234.0811
31.6766 | 1546502.2263
31.6769 | 1613527.701
31.6776 | 1604754.0123
31.6802 | 1539116.5412
31.6818 | 1653276.5963
31.684 | 1572927.611
31.6886 | 1588400.719
31.6887 | 1616191.3704
31.6891 | 1553199.1261
31.6913 | 1609671.2197
31.695 | 1634730.9284
31.6952 | 1581290.0726
31.6952 | 1610622.6411
31.6984 | 1568578.9489
31.7051 | 1582576.3181
31.7058 | 1621698.1594
31.7066 | 1602843.9784
31.707 | 1623713.6543
31.7085 | 1625325.2701
31.7111 | 1594283.9171
31.7145 | 1587787.168
31.7146 | 1647998.4814
31.7148 | 1583187.92
31.7197 | 1600788.3574
31.7227 | 1536726.7304
31.7248 | 1605686.3768
31.7261 | 1612536.3841
31.7308 | 1595698.4361
31.7309 | 1634497.512
31.7312 | 1573006.8688
31.7312 | 1559479.5606
31.7366 | 1598051.9344
31.7373 | 1563230.8459
31.7381 | 1611133.3259
31.7444 | 1567937.9424
31.7452 | 1609042.2558
31.7479 | 1659839.7578
31.7482 | 1608402.6577
31.7519 | 1505756.7593
31.754 | 1561710.9777
31.7546 | 1592822.5682
31.7569 | 1622980.0045
31.7573 | 1584874.7142
31.7608 | 1644674.6431
31.7624 | 1574376.08
31.7642 | 1624963.7895
31.7655 | 1590698.1255
31.7666 | 1611586.5587
31.7668 | 1626708.9297
31.7689 | 1586210.8273
31.7696 | 1621984.312
31.771 | 1587475.1673
31.7728 | 1587330.775
31.7731 | 1574856.1089
31.7779 | 1555176.7917
31.7783 | 1560789.0991
31.7794 | 1578231.0405
31.7801 | 1652902.2725
31.7819 | 1586679.7958
31.7843 | 1606284.1685
31.787 | 1634292.2889
31.7874 | 1630112.705
31.7875 | 1623779.7333
31.7877 | 1577940.3692
31.7891 | 1633667.4541
31.7924 | 1610456.5108
31.794 | 1541277.8124
31.7954 | 1640722.5903
31.7963 | 1576341.6675
31.7985 | 1544712.0495
31.8001 | 1579652.2447
31.8015 | 1597130.5375
31.8035 | 1569340.4332
31.8035 | 1591783.7917
31.8088 | 1636548.2429
31.809 | 1606239.8961
31.8098 | 1574380.6703
31.8099 | 1576254.0685
31.8104 | 1572739.5143
31.8107 | 1659935.3428
31.8151 | 1580880.6511
31.8158 | 1528035.1891
31.8174 | 1538354.6261
31.8197 | 1597154.0976
31.8206 | 1536276.1217
31.8238 | 1594969.5427
31.8248 | 1667764.8356
31.8263 | 1589181.2171
31.8283 | 1553458.046
31.8302 | 1642642.8455
31.8348 | 1562847.8928
31.8358 | 1629707.8325
31.8373 | 1571584.1133
31.8447 | 1580296.0729
31.8455 | 1626918.9092
31.8457 | 1584148.8674
31.8458 | 1672531.4422
31.8489 | 1588194.4747
31.8497 | 1591887.1554
31.8498 | 1624527.8754
31.8538 | 1563546.6551
31.8546 | 1587824.2085
31.8556 | 1568520.7584
31.8568 | 1630291.9696
31.8584 | 1580146.8954
31.8585 | 1635934.9947
31.8592 | 1537991.8051
31.8609 | 1542204.515
31.8625 | 1615524.4435
31.8665 | 1578806.8359
31.8666 | 1544581.8142
31.867 | 1545901.7218
31.8674 | 1593148.9825
31.8683 | 1585094.1244
31.8698 | 1599446.0742
31.8714 | 1560410.0376
31.8737 | 1566844.9425
31.8746 | 1568570.1472
31.8768 | 1601476.7169
31.882 | 1621044.84
31.8829 | 1589016.2935
31.8835 | 1608672.8849
31.8864 | 1558805.912
31.8872 | 1651575.5705
31.8886 | 1531937.8622
31.8924 | 1562612.0638
31.8938 | 1598935.271
31.8954 | 1564559.0359
31.8979 | 1595771.221
31.8981 | 1577837.5048
31.8984 | 1640361.0491
31.8989 | 1566135.1043
31.9038 | 1604613.562
31.9069 | 1559435.2567
31.9093 | 1601161.0671
31.9119 | 1625794.0678
31.9128 | 1588688.1084
31.9147 | 1501525.9318
31.9152 | 1645233.0172
31.918 | 1555908.1449
31.9192 | 1573084.2484
31.9196 | 1621390.2903
31.9198 | 1570974.1012
31.9207 | 1540409.9326
31.9257 | 1637255.8362
31.9261 | 1562603.4643
31.9265 | 1595988.3456
31.927 | 1600513.6835
31.9273 | 1609932.5029
31.9319 | 1597121.5333
31.9326 | 1575724.4609
31.9331 | 1621401.3437
31.9382 | 1643816.536
31.942 | 1600300.2852
31.9434 | 1554093.7871
31.9445 | 1592185.5593
31.9462 | 1558979.6381
31.9489 | 1606682.9247
31.9511 | 1570457.6753
31.9523 | 1651687.2942
31.9548 | 1625563.5107
31.9556 | 1632198.4518
31.9572 | 1572353.012
31.9597 | 1525510.9477
31.9631 | 1614435.1154
31.9681 | 1578116.6411
31.9684 | 1548578.4438
31.9687 | 1611476.6776
31.9702 | 1566818.0934
31.972 | 1667277.8703
31.9726 | 1567193.0967
31.9751 | 1549982.549
31.9761 | 1599002.3215
31.9789 | 1579358.2618
31.9838 | 1622362.2762
31.9856 | 1526720.0051
31.9856 | 1643943.3577
31.9906 | 1535039.9098
31.9926 | 1615271.581
31.9955 | 1645416.6323
31.9959 | 1625609.4486
31.9984 | 1561228.699
32.0006 | 1600512.1861
32.001 | 1587895.8202
32.002 | 1533959.5128
32.0029 | 1541471.0174
32.0045 | 1543329.0264
32.0093 | 1621244.8386
32.011 | 1605625.4829
32.0131 | 1614852.8433
32.017 | 1574034.7802
32.0186 | 1579752.5655
32.0194 | 1580555.2191
32.0196 | 1596034.5018
32.0241 | 1719974.5164
32.0255 | 1574947.581
32.0268 | 1535628.2155
32.0279 | 1570466.5203
32.03 | 1616045.8678
32.0301 | 1585337.4405
32.0311 | 1610643.2052
32.036 | 1596108.4753
32.0376 | 1590296.8926
32.0382 | 1649691.9179
32.0384 | 1580756.1899
32.0415 | 1616329.6491
32.043 | 1559534.9726
32.0434 | 1571037.3237
32.0446 | 1564601.4743
32.0459 | 1604650.8702
32.0496 | 1563957.6668
32.0497 | 1581597.1262
32.0506 | 1551684.3138
32.0533 | 1561009.6483
32.0546 | 1537742.8325
32.0554 | 1526255.3051
32.0567 | 1636570.9345
32.0571 | 1589658.7152
32.0575 | 1535275.9283
32.0578 | 1591779.0399
32.0597 | 1540084.9501
32.0606 | 1569444.4597
32.0618 | 1552722.025
32.0643 | 1596461.2536
32.0654 | 1560602.3706
32.066 | 1536549.2044
32.0688 | 1623998.5312
32.0692 | 1671727.6947
32.0693 | 1630128.6322
32.0693 | 1592518.4599
32.0708 | 1572800.3235
32.0732 | 1534317.5893
32.0742 | 1614917.9898
32.0756 | 1606740.1175
32.0774 | 1555073.4638
32.0796 | 1548189.3262
32.0806 | 1570459.2711
32.0811 | 1569722.3755
32.0824 | 1607431.6398
32.0829 | 1550208.8856
32.0834 | 1564092.2407
32.0878 | 1629673.0702
32.0898 | 1604772.4287
32.0903 | 1616880.7849
32.0968 | 1600772.9648
32.1021 | 1552243.8703
32.1025 | 1605326.9048
32.1043 | 1597859.4666
32.1045 | 1529109.5342
32.105 | 1605308.2507
32.107 | 1554603.1763
32.1082 | 1591161.5024
32.1129 | 1636276.7854
32.1141 | 1529267.9202
32.115 | 1598189.3701
32.1154 | 1592605.5946
32.1196 | 1561261.712
32.1198 | 1575770.8968
32.1199 | 1553971.156
32.1238 | 1607635.1936
32.1246 | 1628119.0429
32.1265 | 1590005.853
32.1285 | 1577160.3658
32.1298 | 1621361.7658
32.1304 | 1590706.3142
32.1312 | 1562389.8793
32.1332 | 1566628.7496
32.135 | 1595016.8912
32.1351 | 1531168.7438
32.1377 | 1573792.9432
32.1379 | 1610440.8491
32.1435 | 1564917.0772
32.1458 | 1623692.0608
32.1458 | 1566226.8486
32.1464 | 1543366.3813
32.147 | 1619918.0857
32.1502 | 1583213.9436
32.1544 | 1562831.6207
32.1551 | 1649685.48
32.1568 | 1649147.6237
32.157 | 1558932.1202
32.157 | 1636370.7787
32.1578 | 1582526.4238
32.1582 | 1605087.405
32.1596 | 1562579.232
32.161 | 1642637.3839
32.1614 | 1619392.6662
32.1647 | 1629102.3362
32.1652 | 1607588.9233
32.1679 | 1544884.8209
32.1682 | 1576137.6171
32.1691 | 1633351.8813
32.173 | 1578463.1912
32.1762 | 1636742.9136
32.1815 | 1585291.8796
32.1838 | 1640223.6739
32.1855 | 1621585.3927
32.1873 | 1643221.4429
32.1883 | 1606930.8696
32.1925 | 1634903.554
32.193 | 1568780.9418
32.1952 | 1579701.4693
32.1954 | 1594693.3044
32.1961 | 1515507.6047
32.2017 | 1615368.1569
32.2022 | 1549045.1917
32.2024 | 1579998.2551
32.2067 | 1652448.2098
32.2073 | 1699830.2724
32.2073 | 1572164.9327
32.2114 | 1612445.9488
32.2116 | 1538821.3789
32.2118 | 1604920.9618
32.2125 | 1611566.9867
32.2129 | 1569976.0394
32.2181 | 1602513.2763
32.2199 | 1629169.2105
32.2213 | 1584194.6266
32.2244 | 1578959.2391
32.2255 | 1590623.441
32.2268 | 1584822.7508
32.2283 | 1624740.2389
32.2304 | 1655229.7346
32.2309 | 1577605.2128
32.2328 | 1561829.1196
32.2345 | 1577989.2748
32.2398 | 1598140.6817
32.2408 | 1586760.8681
32.2448 | 1587187.5458
32.2462 | 1554828.6006
32.247 | 1581730.7258
32.2481 | 1633454.2511
32.251 | 1552298.8069
32.2545 | 1658427.9478
32.2549 | 1670851.266
32.2555 | 1602053.5719
32.256 | 1612061.4417
32.2587 | 1527433.9726
32.2592 | 1653922.6367
32.2595 | 1536049.111
32.26 | 1619604.5933
32.2602 | 1613730.9725
32.2606 | 1579566.8337
32.2614 | 1553579.5492
32.2636 | 1626950.1648
32.2647 | 1637698.3179
32.2662 | 1571292.4739
32.2665 | 1574466.7121
32.268 | 1564785.7028
32.2685 | 1542762.9604
32.2685 | 1596771.0274
32.27 | 1605374.9538
32.2717 | 1542749.008
32.2737 | 1578248.5184
32.275 | 1578252.3784
32.2763 | 1578858.8229
32.2779 | 1573012.5435
32.279 | 1571509.0815
32.2794 | 1598310.6802
32.2808 | 1613323.5057
32.2823 | 1586517.1837
32.2838 | 1514973.8592
32.2838 | 1570186.8585
32.2843 | 1625938.5548
32.2843 | 1584190.2879
32.2843 | 1561754.2306
32.2845 | 1598837.9054
32.2863 | 1620431.0743
32.2888 | 1661528.4704
32.2904 | 1555960.86
32.2914 | 1546348.2322
32.2916 | 1557443.3559
32.2964 | 1529901.3663
32.3002 | 1575625.6373
32.3006 | 1651283.2349
32.3081 | 1604508.9749
32.309 | 1639052.2507
32.3101 | 1618205.5526
32.3104 | 1529872.9428
32.3105 | 1553623.8028
32.3118 | 1566129.0187
32.3119 | 1615012.5967
32.3161 | 1638723.5481
32.3167 | 1622916.4257
32.3183 | 1523955.2125
32.3195 | 1558998.8144
32.3206 | 1620803.9081
32.3214 | 1605907.0741
32.3224 | 1607428.772
32.3245 | 1561414.6356
32.3308 | 1554763.6347
32.3319 | 1580577.2652
32.332 | 1573557.2532
32.3347 | 1607791.4042
32.3368 | 1590620.7286
32.34 | 1596737.965
32.3417 | 1585070.9646
32.3436 | 1594325.0814
32.3444 | 1555023.2055
32.3444 | 1524531.4081
32.3459 | 1674981.7227
32.3486 | 1582602.5024
32.353 | 1630230.3949
32.3533 | 1618474.8884
32.355 | 1648261.6955
32.3561 | 1543307.2836
32.3564 | 1608656.1358
32.3565 | 1571373.7298
32.3575 | 1623912.0597
32.358 | 1572051.3237
32.3682 | 1628886.694
32.3687 | 1607561.1715
32.3723 | 1574469.7338
32.3728 | 1615069.9766
32.3731 | 1571412.8699
32.3735 | 1549118.7503
32.3757 | 1605987.2118
32.3765 | 1581604.1119
32.3781 | 1631934.7778
32.3794 | 1531429.4755
32.3794 | 1552147.6073
32.3795 | 1615111.5623
32.3798 | 1611773.4052
32.3848 | 1592663.6273
32.3852 | 1537657.4751
32.3863 | 1570102.3939
32.387 | 1573952.4346
32.3898 | 1550974.8232
32.39 | 1488435.6146
32.3906 | 1546154.4991
32.391 | 1552327.6505
32.3915 | 1579093.3175
32.3937 | 1584976.4328
32.3944 | 1603454.7239
32.3947 | 1550274.9669
32.396 | 1520753.1954
32.3972 | 1578227.4141
32.3982 | 1554261.6997
32.3983 | 1585156.6456
32.4013 | 1563822.9381
32.4044 | 1625849.5317
32.4046 | 1619109.4347
32.407 | 1567992.6187
32.409 | 1607818.0383
32.4096 | 1630864.1591
32.4111 | 1598972.0034
32.4122 | 1614485.0824
32.4147 | 1566417.7751
32.4157 | 1574023.2826
32.4179 | 1585042.8754
32.4185 | 1542377.0378
32.419 | 1587746.7088
32.4206 | 1645426.3482
32.4253 | 1597340.9758
32.4266 | 1586141.9706
32.4271 | 1575193.1871
32.4292 | 1596091.3838
32.4307 | 1540800.2707
32.4312 | 1596430.3586
32.4318 | 1596419.5219
32.4351 | 1602032.6493
32.436 | 1573541.8464
32.4367 | 1614951.2571
32.4378 | 1622963.9402
32.4388 | 1588735.2454
32.4432 | 1530925.5206
32.4446 | 1568143.6533
32.4456 | 1522164.0384
32.4465 | 1528013.7054
32.4472 | 1579716.6682
32.4473 | 1645642.5998
32.4479 | 1569016.9188
32.4487 | 1642136.1596
32.4533 | 1596488.5624
32.4551 | 1567037.418
32.4553 | 1560681.4818
32.4568 | 1622455.9993
32.4572 | 1616085.9451
32.4588 | 1633135.1007
32.4589 | 1637066.5323
32.4592 | 1578652.2447
32.4603 | 1613021.3621
32.4618 | 1557186.7068
32.4625 | 1567749.1912
32.4625 | 1578331.568
32.4634 | 1565172.257
32.4644 | 1595560.5024
32.4644 | 1583977.3161
32.4672 | 1603903.4454
32.4675 | 1680977.2899
32.4695 | 1626984.4317
32.4697 | 1547785.8451
32.4741 | 1582243.785
32.4743 | 1660405.5718
32.4753 | 1557489.4519
32.4763 | 1554438.1887
32.4786 | 1625846.5884
32.4786 | 1574858.5114
32.4805 | 1575260.4962
32.4837 | 1611369.1261
32.4874 | 1600616.3009
32.4889 | 1586562.9389
32.4891 | 1612222.9286
32.4892 | 1517724.9441
32.4918 | 1543146.1708
32.4951 | 1544562.943
32.4977 | 1557306.3823
32.4986 | 1617837.9921
32.4992 | 1578553.377
32.503 | 1582785.728
32.5067 | 1651787.8202
32.5079 | 1648582.0936
32.5088 | 1539451.5016
32.5108 | 1598656.9021
32.5112 | 1586029.9659
32.5126 | 1562481.4994
32.5131 | 1661441.4724
32.5135 | 1668779.7257
32.5139 | 1611986.8216
32.5146 | 1608172.0167
32.515 | 1547262.7754
32.515 | 1559598.503
32.516 | 1652803.4154
32.5165 | 1627025.9441
32.5166 | 1635271.0674
32.5174 | 1579683.8989
32.5184 | 1582314.8566
32.5199 | 1595338.9645
32.5206 | 1625334.8659
32.5208 | 1596575.6247
32.5233 | 1645252.3524
32.5236 | 1536442.6916
32.5238 | 1587196.1067
32.524 | 1525134.0732
32.5264 | 1583334.7124
32.5274 | 1529482.9246
32.5275 | 1550214.6625
32.5281 | 1626773.221
32.5293 | 1577646.7283
32.5303 | 1657878.2701
32.5307 | 1544837.7176
32.5336 | 1626217.4271
32.5343 | 1606717.4605
32.5357 | 1593679.4538
32.5373 | 1614421.6855
32.5376 | 1648692.3177
32.5391 | 1603499.1334
32.5391 | 1663910.7278
32.5391 | 1571505.6272
32.5392 | 1546323.7652
32.5424 | 1625802.087
32.5447 | 1642412.5878
32.5449 | 1606604.9538
32.5461 | 1618532.4482
32.5476 | 1642460.8876
32.5481 | 1527733.5591
32.5497 | 1618717.6953
32.5498 | 1570856.5151
32.551 | 1523032.442
32.5516 | 1572622.6795
32.5517 | 1577368.406
32.5518 | 1612080.5407
32.5575 | 1627696.9665
32.5605 | 1540616.9242
32.5612 | 1552380.6529
32.5638 | 1611695.27
32.5644 | 1652322.6519
32.5659 | 1577831.4772
32.5707 | 1555614.8514
32.5709 | 1686548.5583
32.5723 | 1505956.145
32.5746 | 1596795.3251
32.5784 | 1576229.023
32.5795 | 1637014.0702
32.5798 | 1570850.8491
32.5814 | 1563665.67
32.5817 | 1649962.2873
32.5822 | 1558254.1702
32.5823 | 1581606.6844
32.5843 | 1572541.9917
32.5843 | 1600382.4225
32.5844 | 1560413.1817
32.5845 | 1564453.5485
32.5851 | 1607701.07
32.586 | 1561041.4039
32.5868 | 1591740.5805
32.5874 | 1622881.326
32.5875 | 1584755.2504
32.5929 | 1608174.4244
32.5941 | 1542277.5788
32.5966 | 1615640.1569
32.5974 | 1599735.7396
32.6034 | 1555848.4126
32.6064 | 1580425.8278
32.607 | 1586095.1584
32.6083 | 1557840.984
32.6087 | 1637708.1012
32.6099 | 1586588.5602
32.6104 | 1542089.3758
32.6109 | 1550850.1001
32.6123 | 1648294.4508
32.6154 | 1556837.1627
32.6168 | 1567101.4227
32.6185 | 1619892.7327
32.6194 | 1580311.9249
32.6216 | 1557292.217
32.6218 | 1568448.0453
32.6267 | 1549812.2374
32.6293 | 1624011.2406
32.6296 | 1646415.4923
32.6304 | 1598334.329
32.6305 | 1586315.4088
32.6308 | 1607746.7263
32.6383 | 1589575.356
32.6392 | 1649693.525
32.6395 | 1541821.6463
32.6462 | 1613588.605
32.6463 | 1577940.8237
32.6475 | 1671273.5251
32.6492 | 1563922.7421
32.6515 | 1598181.0872
32.6519 | 1598472.2422
32.6525 | 1571613.3156
32.6558 | 1652354.4765
32.6567 | 1583655.5987
32.6574 | 1537154.5078
32.6587 | 1626039.8777
32.6596 | 1553895.7219
32.6607 | 1578119.6875
32.6626 | 1552121.9595
32.664 | 1580769.8376
32.6661 | 1580770.4864
32.6662 | 1652232.7367
32.6671 | 1583447.9677
32.6684 | 1590886.5548
32.6685 | 1687762.3941
32.6697 | 1614238.3411
32.6723 | 1508083.7337
32.6754 | 1647472.6416
32.6784 | 1614194.9109
32.6796 | 1618494.9274
32.6796 | 1522646.1946
32.6798 | 1637120.6302
32.6803 | 1566871.1277
32.6827 | 1589354.4693
32.6849 | 1527081.6209
32.6853 | 1562639.4833
32.6866 | 1536703.5305
32.6882 | 1605929.4348
32.6894 | 1583991.8289
32.6903 | 1514553.6719
32.6906 | 1558667.6391
32.6907 | 1659821.2603
32.693 | 1615742.8486
32.6949 | 1575061.0656
32.6953 | 1548496.0555
32.6972 | 1602020.9715
32.6993 | 1608902.1246
32.7014 | 1668593.7922
32.7017 | 1582084.1606
32.702 | 1640956.7846
32.7022 | 1653395.7909
32.7032 | 1651501.3108
32.7035 | 1571870.2927
32.7039 | 1582307.6142
32.7048 | 1570665.4104
32.7062 | 1500728.8941
32.7067 | 1593101.3175
32.7071 | 1622778.6046
32.7073 | 1635278.1141
32.708 | 1573434.0407
32.7085 | 1589289.9452
32.7086 | 1594762.2683
32.7088 | 1615429.3668
32.7105 | 1551094.1634
32.711 | 1612366.8047
32.7127 | 1578190.6533
32.7141 | 1621190.119
32.7153 | 1494645.3616
32.7162 | 1632455.8192
32.7202 | 1682545.8593
32.721 | 1568368.3976
32.7222 | 1606304.5367
32.7233 | 1573060.788
32.7242 | 1601083.7706
32.7247 | 1585847.3351
32.7248 | 1604702.1869
32.7313 | 1569503.3728
32.7325 | 1613384.8096
32.7326 | 1593198.8514
32.7333 | 1555319.1645
32.7351 | 1589687.019
32.7353 | 1571439.4512
32.7363 | 1583965.0846
32.7385 | 1570097.3737
32.7421 | 1573280.4592
32.7426 | 1583173.7697
32.7427 | 1593612.1786
32.7448 | 1572254.0987
32.7461 | 1597828.846
32.7468 | 1594488.2198
32.7486 | 1645203.4228
32.7498 | 1611159.7276
32.7506 | 1526898.1723
32.7511 | 1578882.6597
32.7553 | 1646690.3069
32.7557 | 1592676.4628
32.7562 | 1637035.2579
32.7586 | 1582758.7929
32.7588 | 1624282.4881
32.7594 | 1555233.6774
32.7604 | 1556687.02
32.7612 | 1535792.3758
32.7627 | 1588892.9374
32.7635 | 1607877.022
32.7652 | 1572073.5383
32.7669 | 1621068.1432
32.7675 | 1590455.583
32.7696 | 1546346.4776
32.7696 | 1576160.2895
32.7702 | 1579361.2102
32.7759 | 1608607.3699
32.7777 | 1570695.6617
32.7788 | 1579534.206
32.7791 | 1575935.2429
32.7803 | 1600741.3884
32.7811 | 1601496.9396
32.7823 | 1585946.3256
32.7838 | 1581694.306
32.7854 | 1519662.5517
32.7856 | 1565384.005
32.7866 | 1580925.8825
32.7877 | 1550429.5402
32.7888 | 1630369.4803
32.7892 | 1591085.0813
32.7899 | 1583347.8289
32.7926 | 1583265.0465
32.7938 | 1638710.7917
32.7947 | 1640637.2351
32.7973 | 1550039.1238
32.7984 | 1605254.3317
32.7992 | 1647342.659
32.7998 | 1596797.391
32.8014 | 1603114.4667
32.8018 | 1569457.7275
32.805 | 1569627.4717
32.8058 | 1569991.7914
32.8062 | 1592940.4699
32.808 | 1562493.1173
32.8088 | 1583535.4119
32.8094 | 1567259.68
32.8102 | 1692764.4127
32.8123 | 1530503.8079
32.8125 | 1543450.6093
32.8128 | 1564133.1944
32.8145 | 1579348.9286
32.8152 | 1529850.1041
32.8167 | 1547324.5068
32.8213 | 1574535.2156
32.8245 | 1592809.7992
32.825 | 1565241.7787
32.8271 | 1545449.4223
32.8272 | 1616202.2757
32.8276 | 1597333.6119
32.8295 | 1597749.2277
32.8334 | 1522041.7073
32.8338 | 1628358.7573
32.8356 | 1598218.179
32.8358 | 1563347.5812
32.8362 | 1575009.5398
32.8369 | 1610346.3094
32.837 | 1608730.4597
32.8375 | 1558677.8684
32.8399 | 1584615.7648
32.8413 | 1604834.7411
32.842 | 1539672.3796
32.8483 | 1650515.0784
32.8486 | 1658822.7401
32.8496 | 1531809.116
32.8497 | 1608839.7857
32.8503 | 1624629.4788
32.8507 | 1592997.2135
32.8515 | 1610886.8597
32.8528 | 1551324.1835
32.8547 | 1626819.1478
32.8567 | 1549523.0542
32.859 | 1518645.3051
32.8593 | 1549381.0023
32.8606 | 1621799.6396
32.8612 | 1581575.4879
32.8616 | 1639070.081
32.8649 | 1603164.4548
32.8664 | 1513790.8594
32.8684 | 1590162.937
32.8689 | 1613992.374
32.8694 | 1607649.9329
32.8699 | 1597206.0366
32.8717 | 1672135.7937
32.8781 | 1540554.2214
32.8811 | 1610405.7446
32.882 | 1529111.353
32.885 | 1568779.4406
32.888 | 1648007.4559
32.8888 | 1642595.881
32.8888 | 1563243.821
32.89 | 1594839.996
32.892 | 1557554.049
32.8924 | 1645174.8599
32.8926 | 1608597.9108
32.8932 | 1589153.4476
32.8938 | 1573589.8862
32.8943 | 1621706.4212
32.8945 | 1554937.901
32.8951 | 1590491.7837
32.8972 | 1564840.7162
32.8985 | 1575151.4631
32.8985 | 1603921.6337
32.8988 | 1578381.696
32.8994 | 1573827.9167
32.8994 | 1540332.2865
32.9013 | 1598921.1427
32.9041 | 1594108.4412
32.9046 | 1570103.6193
32.9052 | 1530920.5745
32.9057 | 1619165.8969
32.906 | 1595534.3064
32.9068 | 1555040.2451
32.9071 | 1591110.8085
32.9085 | 1553457.042
32.9091 | 1580627.4684
32.9108 | 1657497.5295
32.9118 | 1618575.7625
32.9127 | 1558816.4615
32.9132 | 1593933.0279
32.9153 | 1601511.7237
32.9178 | 1576766.4274
32.9184 | 1621011.9677
32.9187 | 1574577.8529
32.9192 | 1639718.4806
32.9205 | 1584017.5782
32.9217 | 1609107.4526
32.9236 | 1607695.4541
32.9243 | 1588581.6566
32.9265 | 1612593.7524
32.9275 | 1654039.2277
32.9277 | 1566361.0934
32.9282 | 1589913.3179
32.9286 | 1551275.5329
32.9291 | 1575930.69
32.9308 | 1606845.1391
32.9312 | 1580490.6326
32.9321 | 1576608.4888
32.9339 | 1649377.8877
32.9352 | 1592997.4894
32.9352 | 1575900.3984
32.9379 | 1606754.8558
32.9385 | 1505414.0647
32.9413 | 1613188.975
32.9418 | 1607222.0939
32.942 | 1637969.3663
32.9422 | 1580117.4379
32.943 | 1571855.7503
32.9438 | 1605388.0508
32.9461 | 1611884.1827
32.9567 | 1559201.2429
32.958 | 1538630.0383
32.9591 | 1657954.2953
32.9591 | 1625675.573
32.9596 | 1527070.5174
32.9623 | 1605902.8782
32.9635 | 1583414.9617
32.9645 | 1628535.4101
32.9649 | 1549932.3982
32.9653 | 1629554.4153
32.9657 | 1616908.404
32.9667 | 1582290.9956
32.9668 | 1554758.2105
32.9674 | 1603097.6133
32.9687 | 1614927.0484
32.9721 | 1542367.4195
32.9728 | 1678369.9427
32.9728 | 1533738.3737
32.9739 | 1631512.9082
32.9743 | 1613858.1674
32.9743 | 1560424.1624
32.9744 | 1525090.8316
32.9752 | 1577989.8501
32.9756 | 1611999.3868
32.9792 | 1605208.4248
32.9801 | 1625967.2635
32.9804 | 1585423.4859
32.9805 | 1603398.4314
32.981 | 1601440.9397
32.9813 | 1635413.6264
32.9829 | 1557855.8796
32.9835 | 1656357.3107
32.9844 | 1620037.1122
32.9865 | 1574320.7774
32.9892 | 1545576.5599
32.991 | 1530405.6657
32.9919 | 1590758.985
32.9921 | 1622635.5621
32.9938 | 1634801.5253
32.9964 | 1623216.3111
33.0015 | 1579021.8135
33.0018 | 1606746.509
33.0019 | 1563561.3873
33.0025 | 1534649.5258
33.0055 | 1529401.0693
33.0074 | 1606240.3853
33.0082 | 1564610.2192
33.0146 | 1551942.9016
33.0156 | 1607684.8206
33.0171 | 1536664.4456
33.018 | 1546522.9397
33.0185 | 1614790.5428
33.0194 | 1551269.1205
33.0195 | 1572844.6956
33.0198 | 1603405.5103
33.0206 | 1580320.3835
33.0225 | 1573031.3783
33.0237 | 1566868.2836
33.0259 | 1594454.5897
33.026 | 1595594.367
33.0295 | 1644248.5098
33.0299 | 1627234.4316
33.032 | 1609191.7256
33.0343 | 1574576.7723
33.0354 | 1620284.1683
33.0368 | 1587480.1234
33.0372 | 1649433.151
33.0388 | 1622279.7149
33.039 | 1555962.0817
33.0416 | 1638949.3232
33.0424 | 1608755.1746
33.0424 | 1510515.8371
33.0426 | 1582895.7535
33.044 | 1621660.1491
33.044 | 1715920.7703
33.0472 | 1599228.4549
33.0486 | 1569794.9977
33.0534 | 1615014.0828
33.0538 | 1575427.0375
33.0546 | 1569351.1237
33.0575 | 1530380.7763
33.0579 | 1676846.4389
33.0595 | 1579236.9507
33.0607 | 1659248.118
33.0617 | 1626964.6005
33.062 | 1610661.3586
33.0629 | 1574085.0902
33.0633 | 1540538.9781
33.0645 | 1530053.9584
33.0661 | 1574783.3548
33.067 | 1679651.2686
33.068 | 1565528.7203
33.0686 | 1513204.8379
33.0688 | 1585827.4951
33.0707 | 1577764.1072
33.0711 | 1540905.7351
33.0729 | 1533451.2291
33.0732 | 1567719.4709
33.0737 | 1554569.2109
33.0744 | 1618638.9461
33.0746 | 1664984.4996
33.0749 | 1617291.4291
33.0773 | 1534364.9351
33.0776 | 1626605.1114
33.078 | 1615480.2893
33.0781 | 1623815.7023
33.0829 | 1498174.4624
33.0851 | 1559079.4358
33.0859 | 1582971.7747
33.0886 | 1601495.534
33.0894 | 1553035.7421
33.0895 | 1617733.3188
33.0899 | 1548991.3646
33.0912 | 1534215.7439
33.0968 | 1633900.4769
33.0973 | 1590253.0454
33.0997 | 1553887.1445
33.1006 | 1614403.0174
33.1018 | 1559623.5633
33.1057 | 1579469.9258
33.1066 | 1534035.6194
33.107 | 1578157.2228
33.1092 | 1600159.6849
33.1092 | 1544710.9641
33.1092 | 1566603.69
33.1106 | 1558911.6931
33.1108 | 1536310.8241
33.112 | 1590815.7855
33.1134 | 1616102.0598
33.1146 | 1545281.2812
33.1157 | 1534213.297
33.1161 | 1601828.8795
33.1165 | 1564906.9345
33.1166 | 1625404.3713
33.1168 | 1524918.2036
33.1182 | 1618902.8643
33.1193 | 1588009.1292
33.1195 | 1600289.0933
33.1224 | 1587768.036
33.1241 | 1657006.6962
33.1267 | 1586236.7021
33.1267 | 1551004.7925
33.1294 | 1631799.3436
33.13 | 1604692.7264
33.1314 | 1569893.6622
33.1325 | 1552270.206
33.1328 | 1578092.4696
33.1351 | 1583604.4618
33.1361 | 1587311.1396
33.1374 | 1610560.694
33.1393 | 1555548.6303
33.1395 | 1596155.6002
33.141 | 1589738.5842
33.1411 | 1629854.2679
33.1518 | 1580043.8541
33.1531 | 1582447.7412
33.1532 | 1556783.7008
33.1544 | 1509826.4181
33.1546 | 1600833.2939
33.1585 | 1594545.8742
33.159 | 1603723.7879
33.161 | 1580558.9948
33.1669 | 1615617.6011
33.1673 | 1534803.3555
33.1674 | 1519748.4419
33.1678 | 1634242.533
33.1682 | 1611636.3412
33.1683 | 1591137.9111
33.1702 | 1526243.5463
33.173 | 1613643.1014
33.1746 | 1587537.0183
33.1761 | 1533657.4113
33.1792 | 1613898.8569
33.1793 | 1571743.3526
33.1795 | 1611799.4968
33.1796 | 1577890.347
33.1817 | 1603634.7991
33.185 | 1569013.1725
33.1852 | 1594689.7646
33.1865 | 1619742.9928
33.1881 | 1538488.3354
33.1881 | 1534401.9272
33.1895 | 1587988.9129
33.1918 | 1579909.8051
33.1934 | 1572209.9305
33.1966 | 1565604.7789
33.1973 | 1652584.5672
33.2006 | 1643484.2574
33.2015 | 1612922.2866
33.2028 | 1604278.4323
33.2048 | 1646838.7176
33.208 | 1612128.3211
33.2082 | 1611150.3519
33.209 | 1557643.8944
33.2093 | 1573644.1542
33.2096 | 1573481.521
33.2097 | 1517519.1058
33.2113 | 1639967.2234
33.212 | 1558328.336
33.2147 | 1627846.2505
33.2181 | 1534030.9556
33.2201 | 1600000.0024
33.2204 | 1615487.1062
33.2234 | 1616239.3277
33.2237 | 1629204.1262
33.2292 | 1552568.5761
33.2331 | 1562171.7635
33.2337 | 1632946.9112
33.2342 | 1600134.884
33.2349 | 1619931.143
33.2366 | 1576282.7495
33.2396 | 1594567.9717
33.2441 | 1528351.7969
33.2458 | 1589852.7879
33.246 | 1593906.8548
33.2461 | 1590995.2423
33.2466 | 1631772.3514
33.2477 | 1645286.7465
33.2488 | 1604178.8412
33.2496 | 1590160.5337
33.2513 | 1575798.2438
33.2522 | 1540964.0819
33.2524 | 1585624.4169
33.253 | 1588380.5315
33.2536 | 1579880.126
33.2553 | 1609861.2931
33.2574 | 1545039.8816
33.2589 | 1628040.1619
33.2593 | 1573134.3282
33.2595 | 1561822.5921
33.262 | 1560465.8315
33.2639 | 1646765.8289
33.2656 | 1618122.5538
33.266 | 1591817.6711
33.2661 | 1621700.5533
33.2663 | 1551436.1039
33.2708 | 1569260.6136
33.272 | 1636677.9091
33.2726 | 1633948.1633
33.2784 | 1573168.9181
33.2786 | 1599891.8127
33.2801 | 1559276.8222
33.2828 | 1633151.124
33.2841 | 1557088.1503
33.2842 | 1571203.2645
33.2898 | 1594526.5516
33.2943 | 1561869.1778
33.295 | 1658002.3456
33.2971 | 1614150.2688
33.2988 | 1638345.2197
33.2995 | 1572849.8717
33.2995 | 1637470.9749
33.3035 | 1609648.715
33.3048 | 1538114.5722
33.3059 | 1652765.7764
33.308 | 1520113.6221
33.311 | 1583132.6367
33.3135 | 1598376.6922
33.3135 | 1594869.0742
33.314 | 1583352.7962
33.3206 | 1582712.6664
33.3215 | 1563762.3519
33.322 | 1594528.5228
33.3245 | 1597339.6642
33.3245 | 1586675.0466
33.3286 | 1641874.0455
33.3299 | 1593867.9481
33.3321 | 1587781.766
33.3328 | 1534073.8014
33.3331 | 1588987.3033
33.3362 | 1627086.6996
33.338 | 1652837.5987
33.3381 | 1573133.937
33.3389 | 1642041.2665
33.3395 | 1548755.8108
33.3396 | 1555084.1587
33.3422 | 1577239.1305
33.3427 | 1569299.4138
33.344 | 1566273.8679
33.3442 | 1563727.1623
33.3463 | 1555919.285
33.3464 | 1554912.9761
33.3469 | 1652856.4015
33.3471 | 1572760.1369
33.3496 | 1565249.584
33.3555 | 1601139.201
33.3563 | 1572271.1878
33.3579 | 1599737.6958
33.3582 | 1616552.7572
33.3607 | 1612575.7575
33.3608 | 1582312.5831
33.3621 | 1602642.4514
33.3631 | 1603364.9566
33.3634 | 1679252.0432
33.3652 | 1616405.038
33.3656 | 1593879.0749
33.3667 | 1616957.0702
33.3675 | 1628756.7006
33.3752 | 1568023.5194
33.3758 | 1580374.2334
33.3761 | 1571943.2786
33.3765 | 1576737.0745
33.3768 | 1623314.6642
33.3769 | 1602919.5242
33.3778 | 1661459.0868
33.3778 | 1625140.832
33.3803 | 1586181.753
33.3821 | 1616634.9742
33.3823 | 1622046.2063
33.3836 | 1567762.7918
33.3864 | 1565245.9203
33.3875 | 1591428.3756
33.3877 | 1627183.1616
33.3899 | 1620095.2618
33.3907 | 1571817.3734
33.3936 | 1519562.2454
33.3949 | 1582595.4981
33.3951 | 1612300.2646
33.3963 | 1605572.087
33.3967 | 1558748.3036
33.3972 | 1596789.7245
33.3999 | 1622186.1701
33.4001 | 1623425.4111
33.401 | 1556951.0747
33.4016 | 1624510.8843
33.4022 | 1671107.0558
33.4028 | 1618648.1453
33.4046 | 1548297.887
33.4058 | 1569706.5709
33.4063 | 1694043.7296
33.4069 | 1548928.88
33.4072 | 1528544.1994
33.4074 | 1674117.0013
33.408 | 1565044.7045
33.41 | 1547889.7858
33.4113 | 1597785.256
33.4117 | 1586949.2651
33.4124 | 1604790.8752
33.416 | 1581988.7233
33.4161 | 1566415.5819
33.4164 | 1551666.8973
33.4169 | 1564075.7041
33.4175 | 1595389.236
33.4181 | 1638642.3504
33.4182 | 1660231.0815
33.4189 | 1574370.0814
33.4194 | 1629744.7855
33.4199 | 1552501.1279
33.4204 | 1604635.9604
33.4205 | 1683754.9398
33.4215 | 1607456.6094
33.4225 | 1600136.8739
33.4248 | 1603625.8715
33.4258 | 1528790.8768
33.426 | 1553314.5567
33.4279 | 1539566.2536
33.4281 | 1621628.2051
33.4288 | 1553632.7087
33.4299 | 1576650.3166
33.4316 | 1591075.7772
33.432 | 1623409.2359
33.4321 | 1589389.9198
33.4351 | 1556767.5826
33.436 | 1632043.5831
33.4383 | 1592246.1783
33.4384 | 1605158.4159
33.4437 | 1545828.6799
33.4455 | 1639291.341
33.4471 | 1554994.9558
33.4474 | 1569015.1663
33.4496 | 1585714.6706
33.451 | 1575305.6807
33.451 | 1590947.4082
33.4512 | 1576106.6614
33.453 | 1587884.6036
33.455 | 1598329.1917
33.4551 | 1611235.8668
33.4577 | 1658838.4346
33.4586 | 1633972.5908
33.4618 | 1634854.0745
33.4633 | 1596814.0884
33.4653 | 1544812.4239
33.4657 | 1594852.8155
33.4687 | 1619733.4491
33.4696 | 1633769.3553
33.4723 | 1550454.2012
33.4738 | 1598515.9808
33.4746 | 1596451.5321
33.4788 | 1601097.2243
33.4804 | 1592628.8516
33.481 | 1533657.9409
33.4813 | 1541156.5331
33.4816 | 1585943.1657
33.4825 | 1554793.7027
33.4843 | 1598762.4698
33.4874 | 1605025.7405
33.4891 | 1561144.2817
33.4902 | 1554952.3648
33.4903 | 1601221.7927
33.4931 | 1595016.8354
33.4949 | 1587126.1894
33.4951 | 1546926.9217
33.4985 | 1602966.6217
33.4992 | 1605001.5288
33.5 | 1542212.9173
33.5015 | 1558206.5326
33.502 | 1561453.1664
33.504 | 1549371.7832
33.5079 | 1561170.1665
33.5103 | 1605125.8566
33.5104 | 1565975.4476
33.5133 | 1541446.7737
33.5137 | 1603061.5435
33.5165 | 1617423.9676
33.5165 | 1557813.0975
33.5172 | 1543507.0341
33.5196 | 1527743.494
33.5205 | 1603874.1231
33.5259 | 1583365.2226
33.5271 | 1633964.7808
33.5286 | 1600559.0435
33.5303 | 1617928.2154
33.533 | 1570773.9337
33.5334 | 1564917.3018
33.5336 | 1657684.5351
33.5351 | 1624481.3439
33.5353 | 1567711.9058
33.5382 | 1601643.1822
33.5399 | 1655147.6049
33.5403 | 1552727.2109
33.5409 | 1528538.9202
33.5411 | 1647449.3728
33.5419 | 1573286.8059
33.5434 | 1562645.0139
33.5435 | 1520922.431
33.5443 | 1659641.3619
33.5486 | 1670456.5067
33.5497 | 1538585.6293
33.5502 | 1568426.75
33.5522 | 1583436.1784
33.5529 | 1614559.2138
33.5561 | 1509534.1194
33.5569 | 1623951.1654
33.5589 | 1583419.9666
33.559 | 1581170.3979
33.5613 | 1582773.4255
33.5616 | 1583035.1757
33.5654 | 1570247.4104
33.5663 | 1578684.5987
33.5671 | 1541909.1549
33.5674 | 1614042.5873
33.5692 | 1585890.6376
33.5698 | 1626376.3735
33.5717 | 1540652.2357
33.5735 | 1633066.6529
33.5736 | 1563067.842
33.575 | 1595231.6904
33.5757 | 1530682.4489
33.5767 | 1624204.6462
33.5776 | 1586208.4169
33.578 | 1615190.722
33.5788 | 1631008.3429
33.5796 | 1565608.7697
33.5808 | 1582828.0713
33.5832 | 1533364.8419
33.5836 | 1566553.2524
33.5862 | 1608874.2652
33.5868 | 1571522.8048
33.5873 | 1634787.7449
33.5879 | 1549902.3023
33.5885 | 1651521.7284
33.5902 | 1607525.3362
33.5941 | 1676146.4211
33.5954 | 1553554.8107
33.596 | 1683894.0211
33.5968 | 1643041.8755
33.5977 | 1679128.3717
33.5977 | 1586034.4874
33.5987 | 1511270.6767
33.6 | 1603789.2428
33.6023 | 1570432.4477
33.6032 | 1585339.844
33.6033 | 1636724.3106
33.6046 | 1586429.0836
33.6048 | 1566261.3175
33.605 | 1535412.1293
33.6059 | 1589752.3264
33.6062 | 1584481.3783
33.6077 | 1663878.1271
33.6089 | 1657029.7789
33.6105 | 1563245.6189
33.6116 | 1567155.2864
33.6117 | 1560773.3614
33.6126 | 1655631.8016
33.613 | 1617992.9221
33.615 | 1558876.6222
33.6152 | 1557642.6378
33.6154 | 1595332.5359
33.6176 | 1591425.3761
33.6206 | 1656888.4456
33.6218 | 1614954.6124
33.6234 | 1579847.663
33.6264 | 1530049.7748
33.6282 | 1674836.4864
33.6283 | 1556715.4246
33.6287 | 1578336.2302
33.6289 | 1528546.9703
33.6303 | 1557844.924
33.6318 | 1587826.3294
33.6333 | 1563966.1692
33.6343 | 1656557.6441
33.636 | 1585625.4545
33.636 | 1623298.4546
33.636 | 1618010.6711
33.6367 | 1568462.8977
33.6387 | 1503112.3282
33.6392 | 1646666.5592
33.6404 | 1540021.907
33.6407 | 1637684.1579
33.6409 | 1614651.047
33.6415 | 1553043.133
33.6429 | 1590253.9683
33.6438 | 1658540.1681
33.6445 | 1622317.2723
33.645 | 1633854.1862
33.6477 | 1541893.2095
33.6493 | 1570507.6849
33.6502 | 1582539.8065
33.6514 | 1638730.4135
33.6519 | 1661774.7361
33.6519 | 1553558.6611
33.6522 | 1603058.4679
33.6568 | 1573021.5447
33.6569 | 1529979.9453
33.657 | 1620412.6618
33.6576 | 1634230.5077
33.6576 | 1536514.0765
33.6584 | 1568519.3279
33.6584 | 1635047.739
33.6589 | 1603383.3068
33.6612 | 1549489.7159
33.6625 | 1614106.809
33.6626 | 1635581.6717
33.6629 | 1630548.157
33.6713 | 1592236.199
33.6722 | 1592414.7757
33.6738 | 1584791.5068
33.6743 | 1595561.243
33.6756 | 1595205.3828
33.6768 | 1599867.3249
33.6802 | 1590157.067
33.6847 | 1594170.9894
33.6862 | 1569768.4332
33.6885 | 1618700.8313
33.6936 | 1550826.3429
33.6967 | 1588060.9754
33.6968 | 1640511.9031
33.6969 | 1618015.6446
33.6988 | 1628461.8456
33.6993 | 1584223.7069
33.6999 | 1679937.4896
33.7009 | 1630414.3653
33.702 | 1582651.5774
33.7051 | 1610375.972
33.7122 | 1631714.4534
33.7126 | 1539062.8417
33.7131 | 1610314.1231
33.7182 | 1682496.2335
33.7188 | 1540857.3632
33.7223 | 1553643.6389
33.7243 | 1608211.6486
33.7257 | 1583519.9192
33.7259 | 1569329.2928
33.7265 | 1551906.1092
33.7337 | 1591993.4874
33.736 | 1608162.407
33.7383 | 1599060.4742
33.7383 | 1570167.6037
33.7416 | 1598359.9162
33.7424 | 1607402.6229
33.7425 | 1606450.9601
33.7441 | 1584473.426
33.7442 | 1540445.3102
33.7445 | 1595577.8483
33.7454 | 1604272.5544
33.7502 | 1503590.6426
33.7505 | 1556452.5059
33.751 | 1566123.9087
33.7523 | 1564029.5278
33.7523 | 1573596.5957
33.7524 | 1586828.8331
33.7558 | 1607812.1455
33.7563 | 1630015.4652
33.7574 | 1591742.9674
33.7603 | 1627367.0136
33.7615 | 1582914.4624
33.7665 | 1563166.0017
33.768 | 1581061.3418
33.77 | 1544996.6186
33.77 | 1523226.7415
33.7766 | 1623099.5751
33.7775 | 1598708.0378
33.7776 | 1590145.753
33.7787 | 1570397.8087
33.7796 | 1551684.0504
33.7804 | 1522939.3359
33.7809 | 1513027.9723
33.7814 | 1561964.9989
33.7834 | 1540073.1173
33.7843 | 1596968.986
33.7857 | 1617117.2124
33.786 | 1512771.382
33.7872 | 1603270.3076
33.7874 | 1554733.68
33.7901 | 1581534.9613
33.7916 | 1555255.4131
33.792 | 1600700.1218
33.7926 | 1663687.5528
33.7936 | 1580214.9721
33.797 | 1631393.9991
33.7985 | 1588388.1858
33.8006 | 1610414.0004
33.8015 | 1572896.7351
33.8034 | 1536611.8731
33.8059 | 1552973.7868
33.808 | 1612826.7801
33.8096 | 1619492.148
33.8106 | 1615397.9959
33.8108 | 1530989.9139
33.8121 | 1538062.9992
33.8126 | 1580397.3382
33.8136 | 1639807.4791
33.8144 | 1583006.7036
33.8161 | 1570427.0601
33.817 | 1564297.6075
33.8171 | 1604020.7412
33.8195 | 1561339.3706
33.8202 | 1570712.2207
33.8203 | 1579318.6949
33.8231 | 1604097.1395
33.8247 | 1578940.9844
33.828 | 1664902.3959
33.8282 | 1629366.0473
33.8284 | 1665959.6786
33.8308 | 1550755.3095
33.8314 | 1586421.1594
33.839 | 1631417.1284
33.8396 | 1659409.9456
33.8399 | 1581471.0315
33.8435 | 1568532.6287
33.8456 | 1609736.7903
33.8488 | 1584658.9719
33.8496 | 1675767.5735
33.8513 | 1633222.1202
33.8524 | 1583580.6366
33.856 | 1534469.1258
33.8574 | 1625409.2637
33.859 | 1616126.5738
33.8635 | 1573914.3847
33.8645 | 1609329.3074
33.8685 | 1583335.5154
33.87 | 1575356.3469
33.8706 | 1635858.7518
33.8715 | 1558026.7793
33.872 | 1561925.8633
33.8734 | 1542038.2706
33.8739 | 1681612.8824
33.8748 | 1548209.5748
33.875 | 1631666.5658
33.8754 | 1563996.5295
33.877 | 1589608.2114
33.8781 | 1521975.4765
33.8806 | 1527778.4851
33.8815 | 1649005.1002
33.8858 | 1600832.1693
33.8867 | 1567517.1423
33.888 | 1565585.7912
33.8912 | 1600590.6608
33.8957 | 1559752.4655
33.8977 | 1524559.6231
33.898 | 1585038.525
33.899 | 1622063.1494
33.8999 | 1572358.7137
33.9034 | 1600015.7165
33.9055 | 1630584.2254
33.9072 | 1604046.3059
33.9075 | 1589314.5492
33.9086 | 1534449.8056
33.9125 | 1518667.3701
33.9164 | 1684031.4055
33.9187 | 1618617.6392
33.919 | 1565602.866
33.9194 | 1539163.776
33.9196 | 1621719.0251
33.9213 | 1561652.6617
33.9226 | 1508110.5147
33.9238 | 1602823.7878
33.9271 | 1576437.2544
33.9317 | 1605292.5547
33.9329 | 1648749.1411
33.933 | 1613764.3286
33.9339 | 1634374.7704
33.9368 | 1578266.7965
33.9378 | 1598728.5041
33.9394 | 1592941.1413
33.9407 | 1593688.7106
33.9408 | 1639936.5668
33.9414 | 1565249.4076
33.9417 | 1572353.1609
33.9421 | 1599567.0705
33.9475 | 1669841.7757
33.9476 | 1560457.2002
33.9483 | 1658062.1264
33.9494 | 1600566.2762
33.9499 | 1630312.8892
33.9535 | 1562289.0323
33.9555 | 1562381.8236
33.9558 | 1504374.8048
33.9625 | 1563066.9328
33.9638 | 1587667.2102
33.9665 | 1583691.6709
33.9672 | 1572627.425
33.9702 | 1599985.5499
33.9721 | 1583858.9938
33.9733 | 1546768.0344
33.9747 | 1604436.5754
33.9748 | 1605997.9615
33.9774 | 1557256.5292
33.9788 | 1636094.9552
33.9819 | 1580656.8321
33.9825 | 1525476.8827
33.9838 | 1533137.5988
33.9857 | 1605695.8053
33.9861 | 1569971.7276
33.9872 | 1577343.5178
33.9876 | 1601851.8586
33.9888 | 1570508.4963
33.993 | 1603446.5242
33.994 | 1592811.6621
33.9956 | 1565129.25
33.9956 | 1558984.5974
33.9963 | 1620969.1368
33.9969 | 1605608.82
33.9983 | 1582265.3468
33.9998 | 1604565.5904
34.0023 | 1579046.9274
34.0037 | 1573930.0494
34.0059 | 1646257.5433
34.007 | 1589421.2679
34.0117 | 1541384.6522
34.0123 | 1528149.4713
34.0128 | 1599413.9419
34.0151 | 1618805.6966
34.0152 | 1663342.6992
34.0177 | 1628750.1819
34.0186 | 1537282.6754
34.019 | 1597572.0073
34.0198 | 1650868.5346
34.0226 | 1586820.9329
34.0273 | 1630282.8275
34.0287 | 1556630.75
34.0287 | 1588165.6019
34.0304 | 1574537.5474
34.0309 | 1554026.8965
34.0369 | 1558101.1494
34.0416 | 1598184.6145
34.0424 | 1583829.0664
34.0452 | 1607610.9901
34.0467 | 1528352.0207
34.0495 | 1576367.4268
34.0504 | 1576167.0555
34.0546 | 1603464.3242
34.0553 | 1619996.3157
34.0553 | 1611480.1957
34.0579 | 1615809.115
34.0596 | 1584222.7198
34.0603 | 1527950.9469
34.0615 | 1569460.2916
34.0622 | 1549972.1067
34.0623 | 1608066.3366
34.0636 | 1583239.5864
34.0666 | 1542606.0463
34.0673 | 1576118.5427
34.0691 | 1553143.6425
34.075 | 1530843.4941
34.0757 | 1583689.2743
34.078 | 1555590.7739
34.0797 | 1553787.405
34.0799 | 1600377.3377
34.0832 | 1630221.2859
34.0833 | 1573175.2034
34.0879 | 1556573.7508
34.0887 | 1600622.638
34.0894 | 1605763.338
34.0905 | 1554203.9644
34.0907 | 1622067.2485
34.0965 | 1626932.1949
34.0967 | 1563012.2551
34.1016 | 1528864.9161
34.1043 | 1544574.3482
34.1073 | 1543124.8829
34.1156 | 1581210.5665
34.1182 | 1584229.7062
34.1197 | 1549818.1706
34.1198 | 1641777.3261
34.12 | 1546392.1111
34.1215 | 1552526.9899
34.1223 | 1607734.9718
34.1226 | 1623700.4382
34.1249 | 1556628.0084
34.1257 | 1627434.0185
34.1318 | 1589823.1153
34.1322 | 1576282.6424
34.1387 | 1589557.1806
34.1411 | 1598761.8374
34.1414 | 1571758.6394
34.1442 | 1599848.621
34.1447 | 1574486.57
34.1555 | 1591997.1912
34.1572 | 1664684.3713
34.1586 | 1668125.824
34.1589 | 1587663.0179
34.1617 | 1581349.9524
34.1625 | 1645739.4218
34.1644 | 1602383.2752
34.1648 | 1599065.1496
34.1662 | 1539810.0642
34.1666 | 1609000.7172
34.1667 | 1629110.9954
34.1771 | 1557486.634
34.1777 | 1566740.5692
34.1793 | 1584408.4551
34.1812 | 1593683.3559
34.1819 | 1539764.1308
34.1822 | 1592424.3919
34.1837 | 1544409.6303
34.1838 | 1549111.4022
34.1855 | 1617717.804
34.1869 | 1624542.7025
34.1879 | 1592098.8869
34.1887 | 1625482.4457
34.1933 | 1553645.3073
34.196 | 1526877.0675
34.1972 | 1606396.9798
34.1985 | 1560356.5124
34.2009 | 1660868.4791
34.2018 | 1615605.6597
34.203 | 1561087.7822
34.2041 | 1531294.6322
34.2055 | 1622513.7797
34.2058 | 1545792.9022
34.2059 | 1631049.6281
34.2071 | 1552288.2069
34.2095 | 1644389.5573
34.2109 | 1580830.6647
34.2109 | 1533803.5913
34.2152 | 1584662.0691
34.218 | 1616090.2458
34.2186 | 1560497.559
34.2205 | 1589338.9562
34.2208 | 1608034.1593
34.2209 | 1645589.9252
34.222 | 1555185.0318
34.2233 | 1606461.5109
34.2267 | 1606682.6678
34.2296 | 1600725.6777
34.2301 | 1590556.5649
34.2329 | 1562668.3686
34.2381 | 1648204.2982
34.2382 | 1595086.9341
34.2389 | 1568649.2102
34.2432 | 1509974.7605
34.2437 | 1614064.929
34.2442 | 1643225.8169
34.2464 | 1650265.8805
34.2473 | 1607278.6299
34.2474 | 1657247.1271
34.2476 | 1573216.4718
34.2522 | 1669709.0889
34.2595 | 1542230.1289
34.2614 | 1530240.9259
34.2618 | 1602903.6318
34.2623 | 1568819.1827
34.265 | 1506645.0836
34.2725 | 1576553.7394
34.2747 | 1547695.548
34.2747 | 1542785.8331
34.275 | 1636642.4075
34.2751 | 1663788.0254
34.2753 | 1555935.6661
34.2757 | 1567761.8312
34.278 | 1562168.9674
34.2789 | 1575856.9916
34.2791 | 1560101.6257
34.2797 | 1521826.8072
34.2809 | 1593593.0381
34.2819 | 1589655.0929
34.2831 | 1603006.1337
34.2854 | 1586351.5224
34.2862 | 1564708.2954
34.2887 | 1532683.4393
34.2895 | 1585299.3489
34.2945 | 1644776.4971
34.2954 | 1637378.3214
34.2956 | 1616110.2708
34.2959 | 1574745.88
34.2962 | 1619695.3143
34.3008 | 1592555.7124
34.311 | 1586496.3532
34.3115 | 1547179.1919
34.3117 | 1582613.3685
34.312 | 1542262.4255
34.3149 | 1600371.6985
34.3199 | 1560902.8908
34.3203 | 1580564.6119
34.3208 | 1619043.1507
34.3231 | 1632284.9026
34.3257 | 1551785.6679
34.3278 | 1562793.037
34.3278 | 1639040.1765
34.3314 | 1591975.4408
34.3323 | 1642643.083
34.3335 | 1559791.3657
34.337 | 1525562.2304
34.3381 | 1542900.3063
34.3382 | 1571332.1805
34.3407 | 1675176.4924
34.3409 | 1577046.3682
34.3432 | 1623442.2585
34.3435 | 1582904.3747
34.3448 | 1609402.9342
34.3481 | 1548480.8089
34.3487 | 1559590.9359
34.3514 | 1575451.4605
34.3523 | 1663850.8466
34.355 | 1584602.7044
34.3553 | 1679864.1412
34.3556 | 1595314.5977
34.3574 | 1642357.9673
34.3574 | 1583604.8153
34.367 | 1597718.6632
34.3675 | 1576470.0821
34.3705 | 1600333.9946
34.3718 | 1519202.3902
34.3726 | 1596647.4389
34.3795 | 1571998.9484
34.3802 | 1555127.4246
34.3814 | 1555403.8744
34.3815 | 1612556.491
34.3823 | 1643532.9042
34.3836 | 1550026.5737
34.3851 | 1605584.5313
34.3946 | 1552753.6658
34.3994 | 1607494.4626
34.4033 | 1570317.5315
34.4041 | 1553603.2392
34.4055 | 1543328.0382
34.4058 | 1596383.7611
34.409 | 1569028.8541
34.409 | 1636819.9282
34.4096 | 1539762.8045
34.4132 | 1589220.9516
34.4143 | 1584308.9112
34.4153 | 1625402.4631
34.4163 | 1565522.5982
34.4174 | 1541497.3823
34.4176 | 1612601.4541
34.4187 | 1587872.3087
34.419 | 1575697.601
34.4198 | 1595736.7947
34.4206 | 1571828.8823
34.422 | 1532573.1778
34.4225 | 1615376.5943
34.4233 | 1537899.2833
34.424 | 1574292.8121
34.4276 | 1617221.7506
34.4279 | 1604155.0282
34.429 | 1532775.7137
34.4292 | 1570534.0352
34.4312 | 1605424.1126
34.4317 | 1623864.1622
34.4357 | 1623280.6167
34.4364 | 1559002.4824
34.4371 | 1608728.0756
34.4388 | 1634434.8936
34.4407 | 1597883.3216
34.4428 | 1571063.9144
34.4461 | 1539729.5632
34.4548 | 1549576.8906
34.4578 | 1666681.3219
34.4598 | 1609933.1046
34.4599 | 1574151.0118
34.4599 | 1580297.4525
34.46 | 1524806.4713
34.46 | 1541693.5389
34.4692 | 1633227.4831
34.4727 | 1625478.6589
34.4734 | 1528234.8338
34.4773 | 1530553.9957
34.4802 | 1551634.2345
34.4808 | 1603202.045
34.4817 | 1680275.6401
34.4825 | 1539693.2193
34.4882 | 1593058.3658
34.4885 | 1567180.9451
34.4898 | 1628370.0296
34.4904 | 1613106.3778
34.491 | 1620027.4909
34.4948 | 1566890.4344
34.4965 | 1628872.6242
34.4991 | 1670397.1993
34.4995 | 1554142.7348
34.4996 | 1580554.2331
34.4999 | 1584498.7559
34.501 | 1620972.9048
34.5031 | 1586740.5211
34.5039 | 1559376.2539
34.5048 | 1604017.7613
34.5057 | 1545662.7751
34.5081 | 1618124.501
34.5145 | 1599987.0756
34.5151 | 1609531.8379
34.5198 | 1607942.1997
34.5209 | 1589353.923
34.5242 | 1632541.4669
34.5253 | 1583883.644
34.5276 | 1589516.8443
34.5317 | 1598691.7515
34.5352 | 1603337.7369
34.5375 | 1614526.9164
34.5407 | 1585277.2747
34.5425 | 1596074.4765
34.5461 | 1545864.5347
34.5493 | 1607477.8385
34.5517 | 1570145.999
34.5518 | 1570948.285
34.5521 | 1581723.9384
34.5521 | 1516518.5341
34.5537 | 1564255.3836
34.5542 | 1641172.9173
34.5547 | 1629549.2054
34.5571 | 1556407.2284
34.5597 | 1693368.716
34.5684 | 1631275.1291
34.5712 | 1554354.8897
34.5714 | 1555785.3518
34.5718 | 1618989.8776
34.574 | 1610976.4466
34.581 | 1528568.7643
34.5812 | 1624041.8925
34.5828 | 1592793.304
34.5832 | 1552746.77
34.5859 | 1560867.1646
34.5901 | 1601967.9148
34.5921 | 1521678.6836
34.5922 | 1540824.6895
34.5941 | 1575874.7367
34.5944 | 1624572.2845
34.5946 | 1537365.6301
34.5976 | 1606562.5559
34.6012 | 1616900.3443
34.6014 | 1566636.9536
34.6017 | 1555748.6545
34.6018 | 1605829.8547
34.6047 | 1608351.3784
34.6069 | 1617436.7119
34.6084 | 1581302.5465
34.6149 | 1618855.9187
34.6157 | 1588673.8683
34.6158 | 1606922.6175
34.6197 | 1669442.7972
34.6205 | 1586288.5847
34.6239 | 1585562.2733
34.628 | 1563345.5883
34.629 | 1594721.6909
34.6303 | 1549944.9705
34.632 | 1592900.7556
34.6365 | 1645328.9905
34.6367 | 1608464.973
34.6374 | 1662248.6411
34.6397 | 1604769.2038
34.6423 | 1562171.034
34.644 | 1621604.1085
34.6443 | 1623496.8441
34.6449 | 1645799.7746
34.6462 | 1548273.1122
34.6463 | 1609582.8177
34.6554 | 1577621.3693
34.6577 | 1533165.3088
34.6588 | 1511034.7867
34.659 | 1624172.3536
34.6602 | 1641696.6963
34.6674 | 1661719.6153
34.6755 | 1559072.0219
34.6764 | 1607775.4851
34.6765 | 1578159.1541
34.6839 | 1645296.8665
34.6842 | 1579810.8541
34.6846 | 1571330.1323
34.692 | 1578151.7036
34.6945 | 1616058.366
34.6946 | 1621460.1224
34.6966 | 1607253.0773
34.6985 | 1668418.7333
34.6988 | 1571074.8042
34.7006 | 1621406.6969
34.7029 | 1554606.8528
34.7041 | 1590456.0333
34.7045 | 1638961.3919
34.7076 | 1607375.7251
34.7079 | 1576679.6199
34.7089 | 1598689.1836
34.7132 | 1567928.4216
34.7148 | 1603878.5607
34.7166 | 1593728.6988
34.7189 | 1562509.0334
34.7197 | 1597013.4536
34.7204 | 1608139.7928
34.7216 | 1558578.6271
34.7234 | 1611207.0075
34.7239 | 1629126.8772
34.7297 | 1566246.9268
34.7321 | 1613202.0822
34.7339 | 1574458.4399
34.7392 | 1617761.272
34.7434 | 1626840.5857
34.7457 | 1652773.2017
34.7462 | 1607828.7404
34.7494 | 1561782.7938
34.7496 | 1529277.4447
34.7505 | 1568492.3523
34.7564 | 1590717.8566
34.7582 | 1566563.3242
34.7595 | 1588915.7682
34.7596 | 1553846.898
34.7671 | 1664592.9623
34.7695 | 1640002.6364
34.7726 | 1611625.9158
34.7829 | 1602773.3277
34.7844 | 1560974.1947
34.786 | 1668850.6133
34.787 | 1522743.2607
34.7882 | 1625413.3133
34.789 | 1593068.2766
34.7893 | 1633642.077
34.7947 | 1585296.3419
34.7962 | 1577035.0007
34.799 | 1533626.3552
34.7999 | 1604155.8314
34.8014 | 1558619.1136
34.804 | 1602737.8945
34.8046 | 1588736.7251
34.8064 | 1624546.5938
34.8065 | 1611166.0392
34.8137 | 1617078.4118
34.8147 | 1571173.7213
34.8157 | 1580965.6684
34.8162 | 1638401.9307
34.8217 | 1593949.8601
34.8229 | 1632075.8054
34.8236 | 1617321.7168
34.8255 | 1642724.3446
34.8268 | 1520494.1962
34.8303 | 1544545.2718
34.831 | 1511110.3803
34.8318 | 1592005.8981
34.8331 | 1579803.3915
34.8336 | 1556661.2183
34.8345 | 1593565.4209
34.8419 | 1546321.1008
34.8424 | 1525875.3094
34.8429 | 1584992.0697
34.8429 | 1547813.6144
34.8441 | 1603463.4544
34.8454 | 1566290.5025
34.8471 | 1547211.9484
34.8557 | 1639817.8838
34.8568 | 1524744.4789
34.8587 | 1626734.3272
34.8601 | 1579683.2966
34.8617 | 1591339.1246
34.8669 | 1552867.8057
34.8692 | 1601811.294
34.8724 | 1652452.5802
34.8727 | 1624177.6696
34.8753 | 1543568.3348
34.8834 | 1538939.6776
34.8835 | 1609274.2261
34.8839 | 1576293.2596
34.8869 | 1555823.4562
34.8877 | 1605223.007
34.889 | 1547982.1264
34.8913 | 1618433.1502
34.8922 | 1537625.79
34.8954 | 1545872.5653
34.8961 | 1620854.1768
34.905 | 1556910.8161
34.9104 | 1615075.3115
34.9131 | 1564317.5551
34.9275 | 1622498.7759
34.9292 | 1574102.4937
34.9307 | 1543304.7795
34.9319 | 1538142.9491
34.9331 | 1590695.2719
34.9359 | 1609899.0235
34.9359 | 1578981.2152
34.9373 | 1579305.4422
34.9454 | 1607816.0674
34.9484 | 1568746.0278
34.9589 | 1617683.6591
34.9592 | 1641297.4407
34.9613 | 1603431.8848
34.9666 | 1568807.8994
34.9671 | 1576928.9788
34.9676 | 1554452.4569
34.9699 | 1632188.8307
34.9718 | 1621910.0819
34.9734 | 1575054.8683
34.9744 | 1603258.9343
34.978 | 1596452.4667
34.979 | 1565849.4532
34.98 | 1602231.8439
34.9816 | 1588801.9419
34.9827 | 1540232.94
34.9832 | 1544547.7578
34.9845 | 1651065.7433
34.9852 | 1639333.7429
34.9872 | 1583780.9139
34.9878 | 1559629.9944
34.9962 | 1633473.7034
34.9971 | 1566113.6703
34.9993 | 1587899.0572
35.0004 | 1550554.504
35.001 | 1589649.7209
35.0018 | 1618372.1048
35.0025 | 1572436.7201
35.0049 | 1645170.7559
35.007 | 1565983.1249
35.0079 | 1644967.7449
35.009 | 1649700.7818
35.0103 | 1674347.3246
35.0117 | 1651933.7833
35.017 | 1656385.5039
35.0211 | 1610943.3044
35.0211 | 1615651.9595
35.0212 | 1649960.3617
35.0216 | 1569161.9416
35.0238 | 1653228.824
35.0241 | 1600486.6134
35.0269 | 1629710.0887
35.0286 | 1624923.7195
35.0295 | 1606504.0994
35.0301 | 1619080.0674
35.0307 | 1578596.0344
35.0309 | 1617667.1971
35.0337 | 1570921.5929
35.0412 | 1590162.5923
35.0413 | 1622957.2574
35.0429 | 1609707.5467
35.0477 | 1641337.4778
35.0504 | 1638422.2804
35.052 | 1672855.0485
35.0535 | 1614400.5787
35.0544 | 1649317.5292
35.0545 | 1567457.8719
35.0572 | 1674618.1163
35.0575 | 1640432.4143
35.059 | 1640768.7458
35.0634 | 1612225.3545
35.0724 | 1576282.6505
35.0773 | 1655212.5386
35.0815 | 1593655.485
35.0833 | 1579701.9069
35.086 | 1726475.7125
35.0937 | 1684952.3292
35.1005 | 1633102.9877
35.1083 | 1659783.5873
35.11 | 1635209.2137
35.1174 | 1676393.2003
35.1229 | 1642663.2876
35.1235 | 1649894.5702
35.1236 | 1667066.2526
35.1269 | 1547894.3057
35.1272 | 1636840.701
35.134 | 1634408.0812
35.1385 | 1549310.2742
35.1392 | 1634460.8812
35.1403 | 1634965.9855
35.1429 | 1664366.3903
35.143 | 1630375.9992
35.1446 | 1677040.1426
35.1452 | 1656445.5676
35.146 | 1626375.8001
35.1509 | 1589868.6863
35.157 | 1589898.4441
35.1677 | 1582423.5031
35.1739 | 1579350.7517
35.1786 | 1641087.2691
35.1832 | 1630420.72
35.1865 | 1709492.4164
35.1909 | 1610617.7505
35.1929 | 1601271.4841
35.1998 | 1591259.3235
35.2012 | 1609514.7705
35.2091 | 1558097.5242
35.2131 | 1636351.3875
35.214 | 1639438.4646
35.2164 | 1579303.1106
35.2167 | 1586797.6675
35.2168 | 1579613.5126
35.2199 | 1632758.8169
35.2233 | 1673334.3585
35.2246 | 1597148.593
35.2324 | 1654366.8196
35.2336 | 1603179.1953
35.2441 | 1627480.8518
35.247 | 1563571.4469
35.248 | 1628504.6854
35.251 | 1604746.2032
35.2581 | 1586548.9689
35.2585 | 1646835.628
35.2596 | 1656427.3619
35.2638 | 1635787.41
35.2677 | 1645144.2267
35.2733 | 1642570.7863
35.2801 | 1637489.0087
35.2821 | 1635858.4028
35.2821 | 1630728.9505
35.2856 | 1566942.4462
35.2963 | 1641261.5644
35.2968 | 1568154.1227
35.2974 | 1668893.4878
35.2977 | 1577853.9838
35.3047 | 1611950.1238
35.3056 | 1625339.2931
35.3088 | 1625175.4797
35.3096 | 1586597.9138
35.3122 | 1637267.3726
35.3167 | 1604329.0788
35.3232 | 1626782.7255
35.333 | 1638701.3822
35.3399 | 1596999.7662
35.342 | 1651298.8375
35.3451 | 1667819.5975
35.3512 | 1590421.1789
35.3539 | 1568519.2165
35.3592 | 1592986.6328
35.3672 | 1571328.2204
35.3734 | 1639716.0852
35.3761 | 1650195.6813
35.3762 | 1698468.7676
35.3843 | 1616695.4729
35.3852 | 1550748.9786
35.3954 | 1609718.8067
35.3961 | 1638682.8182
35.4 | 1645669.3011
35.4034 | 1589844.9884
35.4037 | 1586372.4237
35.405 | 1644187.4116
35.4076 | 1635992.8013
35.4094 | 1618773.6642
35.4102 | 1621473.5413
35.4105 | 1610824.4166
35.4109 | 1605114.6088
35.4117 | 1583291.8718
35.4135 | 1608915.978
35.4136 | 1610691.673
35.4229 | 1605850.3011
35.4254 | 1661865.6552
35.4266 | 1601483.6351
35.4281 | 1590021.3709
35.431 | 1603397.64
35.4384 | 1626884.8295
35.4512 | 1593745.6699
35.4513 | 1544360.9953
35.4525 | 1598658.1745
35.4625 | 1637742.9485
35.4642 | 1638800.0137
35.4662 | 1622100.0146
35.4725 | 1617535.6208
35.4735 | 1573613.0166
35.4768 | 1605063.2837
35.4772 | 1614041.8706
35.4831 | 1565422.0734
35.4854 | 1670043.5961
35.4887 | 1598266.9812
35.5056 | 1627587.4574
35.5061 | 1578197.003
35.5115 | 1595061.0181
35.5123 | 1654249.1851
35.5143 | 1612718.2712
35.5157 | 1540379.3186
35.519 | 1603195.8965
35.53 | 1539034.9611
35.5309 | 1653107.6681
35.5326 | 1594875.163
35.5329 | 1602838.21
35.5332 | 1593626.0216
35.5333 | 1558818.1204
35.5348 | 1655140.3011
35.5367 | 1593772.2936
35.544 | 1635644.8432
35.546 | 1568407.4657
35.5572 | 1600438.5454
35.5625 | 1639800.3444
35.5663 | 1696496.1456
35.5692 | 1652385.6777
35.5703 | 1676029.5991
35.5726 | 1665521.3321
35.5841 | 1638938.1631
35.5852 | 1655558.858
35.5883 | 1642305.8882
35.5899 | 1581264.1408
35.5946 | 1644869.3032
35.5946 | 1607453.2266
35.5948 | 1635364.1588
35.6002 | 1575500.2116
35.607 | 1609718.3942
35.6103 | 1550990.2587
35.617 | 1561059.2386
35.6196 | 1567841.8715
35.621 | 1574322.0466
35.6229 | 1568022.7504
35.6233 | 1678642.4734
35.6286 | 1635695.8912
35.6313 | 1601960.2917
35.6322 | 1580258.072
35.6343 | 1575311.9748
35.6372 | 1656545.5719
35.6372 | 1602559.0377
35.64 | 1606071.7264
35.6419 | 1538386.7973
35.6462 | 1627119.7445
35.6503 | 1643138.5602
35.6514 | 1573540.8924
35.6577 | 1633261.9058
35.6619 | 1584142.712
35.6734 | 1634137.7069
35.677 | 1652848.4928
35.6779 | 1614396.4295
35.6789 | 1632448.0637
35.6804 | 1572006.8689
35.6827 | 1700740.138
35.6876 | 1659069.3352
35.6943 | 1604918.936
35.6985 | 1587045.2922
35.7 | 1606324.9827
35.7023 | 1645521.0332
35.703 | 1693269.2729
35.7203 | 1588363.0039
35.7242 | 1627062.4661
35.7252 | 1675063.0822
35.7257 | 1607801.7259
35.7395 | 1563780.8722
35.742 | 1649531.863
35.7477 | 1639987.8868
35.7494 | 1567110.576
35.7517 | 1712896.442
35.7725 | 1617221.2174
35.7825 | 1611849.895
35.8028 | 1656550.8398
35.8218 | 1608475.044
35.8386 | 1629805.5216
35.8416 | 1620295.926
35.8433 | 1639755.6761
35.8487 | 1550555.3239
35.8507 | 1642701.2369
35.8517 | 1675471.6102
35.8582 | 1637475.6452
35.86 | 1619030.6085
35.8631 | 1677122.8097
35.8651 | 1615050.9434
35.8708 | 1628533.2363
35.8717 | 1617527.3908
35.8718 | 1636684.83
35.8769 | 1616980.296
35.8798 | 1639415.0967
35.8918 | 1622167.3933
35.8957 | 1640762.3384
35.899 | 1589537.318
35.9055 | 1608428.1376
35.9067 | 1631491.9001
35.9092 | 1602118.0646
35.9107 | 1619148.7056
35.9141 | 1611667.5242
35.9197 | 1647679.2633
35.9209 | 1648058.7088
35.9224 | 1591253.1777
35.9284 | 1660602.7535
35.9289 | 1547060.6624
35.9399 | 1620657.7975
35.9401 | 1599022.1114
35.946 | 1594511.894
35.9468 | 1653915.3572
35.9469 | 1630033.321
35.9953 | 1620056.0108
35.9988 | 1659428.6124
36.0005 | 1588915.2536
36.0042 | 1706506.1362
36.0089 | 1600476.8368
36.013 | 1656234.5038
36.0173 | 1621751.3605
36.0183 | 1611320.8812
36.023 | 1616089.7242
36.024 | 1611717.0283
36.0242 | 1636748.9768
36.035 | 1646712.799
36.036 | 1644829.1642
36.041 | 1683079.4782
36.0483 | 1625212.4429
36.0529 | 1601123.2215
36.0564 | 1664596.6026
36.068 | 1621553.5371
36.0692 | 1623430.9888
36.0703 | 1622131.7114
36.084 | 1644551.2054
36.0841 | 1662178.3618
36.0842 | 1610055.4374
36.0856 | 1638237.4765
36.0883 | 1593488.9998
36.0922 | 1665080.6059
36.0968 | 1660051.2097
36.1001 | 1671770.7089
36.1028 | 1623387.2236
36.1065 | 1664003.5693
36.1134 | 1579355.9232
36.1246 | 1730441.4442
36.1278 | 1614975.4351
36.142 | 1636387.6891
36.1483 | 1634193.8741
36.1559 | 1591218.6025
36.1674 | 1671985.5297
36.1676 | 1694045.2896
36.1734 | 1654583.4086
36.1742 | 1665338.3876
36.1798 | 1651674.6412
36.1862 | 1624472.0612
36.187 | 1673971.5039
36.1887 | 1716136.2899
36.2035 | 1685140.6621
36.2117 | 1602061.8741
36.2159 | 1738072.4776
36.2196 | 1674972.2692
36.2271 | 1602748.3164
36.2337 | 1572870.0408
36.234 | 1661170.2332
36.2358 | 1634737.6645
36.2471 | 1638333.232
36.2559 | 1615720.3615
36.2591 | 1609079.2902
36.2658 | 1684575.042
36.2678 | 1648135.191
36.2686 | 1606155.9326
36.2761 | 1638684.7599
36.2812 | 1647562.1517
36.2908 | 1662455.1723
36.3036 | 1693450.7179
36.3122 | 1655689.6597
36.3146 | 1600853.3639
36.3299 | 1626027.1542
36.3358 | 1622336.4519
36.3378 | 1601968.8588
36.347 | 1668899.5638
36.3509 | 1634255.5092
36.3523 | 1618056.15
36.3577 | 1635403.2156
36.3613 | 1614958.3459
36.3621 | 1648372.3982
36.366 | 1687912.9137
36.3712 | 1615892.3269
36.3739 | 1596971.5898
36.3761 | 1617802.6293
36.3796 | 1689406.8801
36.3811 | 1648185.0592
36.3814 | 1689701.9995
36.3909 | 1676867.7006
36.4003 | 1614811.582
36.4016 | 1665325.7413
36.4069 | 1641636.8343
36.4081 | 1580323.6639
36.421 | 1611948.9648
36.4545 | 1591220.5377
36.4553 | 1634634.2266
36.4555 | 1659825.4915
36.4604 | 1654896.931
36.4665 | 1604260.66
36.4679 | 1563557.627
36.4783 | 1645476.1664
36.4817 | 1574002.1654
36.4948 | 1614434.5068
36.511 | 1613461.8747
36.532 | 1611988.7116
36.5348 | 1612420.9351
36.5484 | 1642132.531
36.5681 | 1603175.7885
36.5765 | 1641061.2912
36.5879 | 1617006.0417
36.5919 | 1636335.4994
36.5957 | 1610360.8326
36.597 | 1665727.1565
36.6014 | 1657441.5956
36.6171 | 1602017.0182
36.629 | 1596830.3291
36.639 | 1599816.3932
36.6716 | 1632315.7628
36.6802 | 1619708.9418
36.6913 | 1631755.8409
36.7448 | 1605181.2455
36.7648 | 1675534.204
36.7757 | 1630689.5068
36.7819 | 1649249.2517
36.7867 | 1592122.0405
36.7993 | 1671420.8556
36.8049 | 1584345.9856
36.809 | 1682448.7938
36.8099 | 1602504.4918
36.8157 | 1642349.6254
36.8307 | 1630886.3393
36.8498 | 1648565.0818
36.8617 | 1708788.6212
36.868 | 1616810.4391
36.8768 | 1692673.7976
36.8905 | 1569211.6088
36.9055 | 1624714.6782
36.9279 | 1597443.9584
36.953 | 1610023.9814
36.9575 | 1604241.2336
36.9741 | 1624089.0921
37.0116 | 1661272.9653
37.0406 | 1713374.2482
37.0717 | 1655852.0929
37.0736 | 1697255.0918
37.1075 | 1635768.7982
37.1088 | 1651579.1132
37.1269 | 1696020.629
37.1589 | 1642997.57
37.1606 | 1664451.5148
37.1625 | 1660360.1956
37.1633 | 1697890.2731
37.1834 | 1674201.331
37.2807 | 1666762.6588
37.3027 | 1640961.4441
37.3135 | 1638661.7019
37.3293 | 1691591.0575
37.3501 | 1633962.4412
37.3674 | 1632283.8394
37.5941 | 1651889.1604
37.627 | 1677610.0548
37.6518 | 1651165.6719
37.695 | 1627258.3203
37.7156 | 1635395.4376
37.7375 | 1743962.3398
37.7491 | 1680556.1051
37.7529 | 1626963.1364
37.7778 | 1696571.3142
37.7794 | 1716265.7295
37.858 | 1648543.1548
37.951 | 1722873.7096
37.9544 | 1667646.9039
38.0154 | 1637255.0603
38.059 | 1707891.6437
38.1247 | 1674141.6351
38.5073 | 1760327.9497
38.6446 | 1667192.587